## West Coast LNG Projects Only
North America West Coast LNG Terminal Proposals
June 2005
Cost
|  |  |  | Estimate | MMcf/d | Bcf | Number
Name | City | Region | Sponsor | ($ millions) | Base Rate | Storage | of Tanks | Type | Startup | Application | Status | Comments
Colonet | Colonet | Baja, Mexico | Baja Government | [8 empty] | More interest from Baja government than companies
Costa Azul | Costa Azul | Baja, Mexico | Sempra | 1000 | 1000 | 6.8368 | 2 | Single | 2007 | Yes | Environmental and storage permits received | Project plus pipeline cost increased to $1 billion
GNL Mar Adentro | Baja Ca Offsh | Baja, Mexico | ChevronTexaco | 650 | 700 | 5.3412 |  |  | 2008 | Yes | Received two of three federal permits | CRE said permit approval likely by April/May
Lazaro Cardenas | Lazaro Cardenas | Mexico |  | 500 | 400 |  |  |  | 2008 | Yes | Repsol won CRE bid for site option | Tractebel bid was only 2% lower than Repsol's
Manzanillo | Manzanillo | Mexico | Tractebel | 400 | 500 |  |  |  | 2008? |  | CFE will issue supply tender for 1200 MW plant | Tractebel has MOU with Camisea LNG
Puerto Libertad | Puerto Libertad | Sonora, Mexico | DKRW Energy |  | 1300 | 6.9 | 2 |  | 2008 |  |  | Purchased site
Cabrillo Port | California Offsh | California | BHP Billiton | 600 | 1500 | 5.8754 | 3 | FPSO | 2008 | Yes | Application made in March | Oxnard city council voted to oppose pipelines to shore
Clearwater Port | Ventura | California | Woodside | 300 | 800 |  |  | No storage | 2007 | Yes | Refiled USCG application on 7/27/04 | Taken over by Woodside
Sound Energy Solutions | Long Beach | California | Mitsubishi and ConocoPhillips | 450 | 700 | 6.8 | 2 | Full | 2008 | Yes | Filed for FERC permit in 1/2004 | Will focus on 'lean' LNG supply
Bradwoood | Bradwood | Oregon | Northern Star | 520 | 1000 | 7.1 | 2 |  | 2010 |  |  | A 35 mile lateral will connect to Northwest Pipeline
Jordan Cove | Coos Bay | Oregon | Energy Projects Development | 275 | 275 | 3.4 | 1 |  |  |  | Filed NOI with Oregon for necessary permits | Tied to power plant development by same firm
Port of Astoria | Port of Astoria | Oregon | Calpine | 500 | 1000 | 5.8
Port Westward | Pt. St. Helens | Oregon | Port Westward LNG | 325 | 750 |  |  |  | 2009 |  |  | Previous known as Clatskanie
Kitimat | Kitimat | BC, Canada | Galveston LNG | 225 | 340 |  |  |  | 2008 | No
Prince Rupert | Prince Rupert | BC, Canada | Westpac Terminals | 225 | 300 |  |  |  | 2009 |  |  | NEPA to be filed by November 15
CANCELLED PROJECTS
Cherry Point | Cherry Point | Washington | Cherry Point Energy |  | 500 |  |  |  | 2008 | No | Project cancelled according to CEC | Project sponsors now leading Port Westward
Humboldt Bay | Humboldt | California | Calpine | [6 empty] | No | Project cancelled after negative town vote
Mare Island | Vallejo City | San Francisco | Shell/Bechtel |  | 1300 | 4.3 | 2 |  | 2007 | No | Cancelled | Cancelled due to strong local opposition
Rosarito | Rosarito | Baja, Mexico | ConocoPhillips |  | 680 | 3.6 | 2 |  | 2007 | Yes | Environmental permit denied, project is dead | CRE has announced Baja tender in Q1 2004
Tijuana Energy Center | Tijuana | Baja, Mexico | Marathon |  | 750 |  |  |  | 2007 | Yes | Marathon has cancelled project | Marathon site expropriated by Baja state government
Sources:
Kyle Sawyer of El Paso Corporation compiled this list from a variety of sources including Poten & Partners LNG, Wood Mackenzie LNG Service, PIRA LNG Service,
World Gas Intelligence, LNG Daily in addition to various other trade journals.