## Summary
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 1 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
Summary
Estimated
Cost
I. | Pipeline Retirement | [5 empty] | (Jan 2008$)
| A. | Clean and purge transmission lines |  |  |  |  | 7144625
| B. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  |  |  | 142106904
|  | 2 | Uncased railroad crossings |  |  |  | 29931966
| C. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  |  |  | 46985968
|  | 2 | Cased railroad crossings |  |  |  | 24483652
| D. | Small stream crossings |  |  |  |  | 78233394
| E. | River crossings |  |  |  |  | 18279080
| F. | Mainline valve sites |  |  |  |  | 12190097
| G. | Pipeline drips |  |  |  |  | 4455518
| H. | Cathodic protection facilities
|  | 1 | Remove test sites |  |  |  | 3391344
|  | 2 | Remove rectifiers |  |  |  | 1352802
| I. | Pipeline markers |  |  |  |  | 2434600
| J. | M&R stations
|  | 1 | Small |  |  |  | 35310728
|  | 2 | Medium |  |  |  | 9813360
| K. | Compressor stations
|  | 1 | Large |  |  |  | 3046722.6866
|  | 2 | Medium |  |  |  | 3111641.448
|  | 3 | Small |  |  |  | 9088326.7694
|  | 4 | Very small |  |  |  | 10519741.0922
| L. | Communication towers |  |  |  |  | 2580283.3713
[6 empty] | Total I. | 444460753.3675
II. | Salvage
| A. | Equipment |  |  |  |  | -2826263.7634
| B. | Scrap steel |  |  |  |  | -5314150.224
[6 empty] | Total II. | -8140414
III. | Contingency |  |  | (10% of I above) |  |  | 44446075.3367
[6 empty] | Total III. | 44446075
[5 empty] | Grand Total: |  | 480766414.3675

## Clean and Purge
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 2 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
A. Clean and purge transmission lines
Description of Work:
Prior to its last delivery, pipeline company conducts a series of pigging operations to ensure that its transmission
lines are clean and free of liquids. After the last delivery to its customers, pipeline company operating staff
isolates the pipeline system from gas supply inputs and delivery points. Abandonment pressure is estimated to
be 200 psig. Line pack is evacuated by flaring or venting. At this point pipeline is filled with natural gas at
atmospheric pressure. Pipeline company staff evacuates sections of pipeline using pipeline evacuation
equipment. At this point pipeline is filled with air at atmospheric pressure. Pipeline is ready for demolition work.
1 |  | Estimated cost to clean and purge 100-mile pipeline segment of hydrocarbons:
|  |  |  | Unit | No. | Days | Rate | Total
| a. |  | Pigging operation prior to final shutdown | each | 2 |  | 10000 | 20000
| b. |  | Isolate pipeline from input and delivery points | person | 3 | 5 | 1000 | 15000
| c. |  | Blowdown system at M/L valves (10 sites) | person | 3 | 10 | 1000 | 30000
| d. |  | Pipeline evacuation (10 sites) | person | 3 | 20 | 1000 | 60000
125000
[5 empty] | Estimated cost per mile: |  |  | 1250
2 |  | Estimated cost to clean and purge pipeline company transmission lines:
Cost Per
[6 empty] | Miles | Mile | Total
| a. |  | Transmission pipelines |  |  | 5715.7 | 1250 | 7144625

## Uncased Hwy-RR Crossings
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 3 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
B. Uncased highway/railroad crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical uncased highway/railroad crossing (100 ft).
Work includes ROW fence removal, excavation and shoring of trench, capping pipe ends, filling pipe with grout,
backfilling, and restoration of area. Estimate also includes environmental inspection, pipeline company inspection,
and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 849.6066
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3219.5516
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 64.391
|  |  |  | Total Direct Costs (1) = |  |  | 4133.5492
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 232.3692
[6 empty] | Subtotal: | 2368.0012
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 4 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. B. Uncased highway/railroad crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 1 | 20 | 53.9872 | 1079.7439
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 11618.4624
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 232.3692
[6 empty] | Subtotal: | 232.3692
|  |  |  | Total Direct Costs (2) = |  |  | 14218.8329
3. Fill pipe with grout, backfill trench, grade disturbed areas (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
dump truck 8 cy |  |  |  | 1 | 10 | 22.2809 | 222.8088
grout pump, trailer mounted |  |  |  | 1 | 10 | 11.3995 | 113.9952
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 88.3191
[6 empty] | Subtotal: | 1057.0751
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 4415.9536
Material | [6 empty] | Total
Grout/cy | 84 | 6 | cy | (Note: assumes 16" pipe) |  |  | 504
Sales tax @ | 7% | [5 empty] | 35.28
Miscellaneous (2% of labor) | [6 empty] | 88.3191
[6 empty] | Subtotal: | 627.5991
|  |  |  | Total Direct Costs (3) = |  |  | 6100.6277
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 5 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. B. Uncased highway/railroad crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 37.4213
[6 empty] | Subtotal: | 241.3325
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 1871.0635
Material | [6 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 1000
sales tax @ | 7% | [5 empty] | 70
[6 empty] | Subtotal: | 1070
|  |  |  | Total Direct Costs (4) = |  |  | 3182.396
Summary: Uncased Highway/Railroad Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 4133.5492
2. Excavate and cap pipe ends | [6 empty] | 14218.8329
3. Fill pipe with grout, backfill trench, grade disturbed areas | [6 empty] | 6100.6277
4. Restore sites | [6 empty] | 3182.396
|  |  |  | Pipeline contractor direct costs: |  |  | 27635.4058
|  |  |  | 5% Mobilization |  |  | 1381.7703
[6 empty] | Subtotal: | 29017.1761
|  |  |  | 15% Contractor overhead: |  |  | 4352.5764
[6 empty] | Subtotal: | 33369.7525
|  |  |  | 10% Contractor profit: |  |  | 3336.9753
|  |  |  | Total pipeline contractor costs: |  |  | 36706.7278
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
1835.3364
|  |  |  | Total environmental contractor cost: |  |  | 1835.3364
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 4
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2000
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 6 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. B. Uncased highway/railroad crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
6081.3096
|  |  |  | Total management and overhead cost: |  |  | 6081.3096
|  | Total cost to retire an uncased crossing (A + B + C + D): |  |  |  |  | 46623
|  | No. of uncased highway/road crossings |  |  |  |  | 3048
| Item B. 1. | Total estimated cost to retire uncased highway crossings: |  |  |  |  | 142106904
|  | No. of uncased railroad crossings: |  |  |  |  | 642
| Item B. 2. | Total estimated cost to retire uncased railroad crossings: |  |  |  |  | 29931966

## Cased Hwy-RR Crossings
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 7 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
C. Cased highway/railroad crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical cased highway/railroad crossing (100 feet).
Work includes ROW fence removal, excavation and shoring of trench, removal of pipe from casing, filling casing
with grout, removal of vent pipes, and restoration of area. Estimate also includes environmental inspection,
pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 849.6066
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3219.5516
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 64.391
|  |  |  | Total Direct Costs (1) = |  |  | 4133.5492
2. Excavate and remove pipe from casing (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
dozer, Cat D-6R w winch |  |  |  | 1 | 20 | 88.1583 | 1763.1664
hydrocrane, Grove, 25 ton |  |  |  | 1 | 20 | 53.3806 | 1067.6128
pipe truck |  |  |  | 1 | 20 | 46.6039 | 932.0784
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 315.0095
[6 empty] | Subtotal: | 6213.4991
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 8 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. C. Cased highway/railroad crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (dozer, backhoe) |  |  |  | 2 | 20 | 58.3827 | 2335.3064
operator (hydrocrane) |  |  |  | 1 | 20 | 67.2307 | 1344.6136
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 12 |  | 90 | 2160
[6 empty] | Subtotal: | 15750.4731
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 315.0095
[6 empty] | Subtotal: | 315.0095
|  |  |  | Total Direct Costs (2) = |  |  | 22278.9816
3. Fill casing with grout, backfill trench, grade disturbed areas (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
dump truck 8 cy |  |  |  | 1 | 20 | 22.2809 | 445.6176
grout pump, trailer mounted |  |  |  | 1 | 20 | 11.3995 | 227.9904
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 176.6381
[6 empty] | Subtotal: | 2114.1501
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 1 | 20 | 53.9872 | 1079.7439
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 7 |  | 90 | 1260
[6 empty] | Subtotal: | 8831.9072
Material | [6 empty] | Total
Grout/cy | 84 | 6 | cy | (Note: assumes 16" pipe) |  |  | 504
Sales tax @ | 7% | [5 empty] | 35.28
Miscellaneous 2% of labor | [6 empty] | 176.6381
[6 empty] | Subtotal: | 715.9181
|  |  |  | Total Direct Costs (3) = |  |  | 11661.9755
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 9 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. C. Cased highway/railroad crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 37.4213
[6 empty] | Subtotal: | 241.3325
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 1871.0635
Material | [6 empty] | Total
allow $2000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 2000
Sales tax @ | 7% | [5 empty] | 140
[6 empty] | Subtotal: | 2140
|  |  |  | Total Direct Costs (4) = |  |  | 4252.396
Summary: Cased Highway/Railroad Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 4133.5492
2. Excavate and remove pipe from casing | [6 empty] | 22278.9816
3. Fill casing with grout, backfill trench, grade disturbed areas | [6 empty] | 11661.9755
4. Restore sites | [6 empty] | 4252.396
|  |  |  | Pipeline contractor direct costs: |  |  | 42326.9023
|  |  |  | 5% Mobilization |  |  | 2116.3451
[6 empty] | Subtotal: | 44443.2474
|  |  |  | 15% Contractor overhead: |  |  | 6666.4871
[6 empty] | Subtotal: | 51109.7345
|  |  |  | 10% Contractor profit: |  |  | 5110.9734
|  |  |  | Total pipeline contractor costs: |  |  | 56220.7079
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
2811.0354
|  |  |  | Total environmental contractor cost: |  |  | 2811.0354
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2500
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 10 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. C. Cased highway/railroad crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
9229.7615
|  |  |  | Total management and overhead cost: |  |  | 9229.7615
|  | Total cost to retire a cased crossing (A + B + C + D): |  |  |  |  | 70762
|  | No. of cased highway crossings: |  |  |  |  | 664
| Item C. 1. | Total estimated cost to retire cased highway crossings: |  |  |  |  | 46985968
|  | No. of cased railroad crossings: |  |  |  |  | 346
| Item C. 2. | Total estimated cost to retire cased railroad crossings: |  |  |  |  | 24483652

## Small Stream Crossings
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 11 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
D. Small stream crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical small stream crossing (100 feet). River
crossings are not included in this line item. Work includes, excavation and shoring of trench, capping pipe
ends, filling pipe with grout, and restoration of area. Estimate also includes environmental inspection, pipeline
company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 849.6066
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3219.5516
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 64.391
|  |  |  | Total Direct Costs (1) = |  |  | 4133.5492
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 232.3692
[6 empty] | Subtotal: | 2368.0012
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 12 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. D. Small stream crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 1 | 20 | 53.9872 | 1079.7439
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 11618.4624
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 232.3692
[6 empty] | Subtotal: | 232.3692
|  |  |  | Total Direct Costs (2) = |  |  | 14218.8329
3. Fill pipe with grout, backfill trench, grade disturbed areas (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
dump truck 8 cy |  |  |  | 1 | 10 | 22.2809 | 222.8088
grout pump, trailer mounted |  |  |  | 1 | 10 | 11.3995 | 113.9952
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 88.3191
[6 empty] | Subtotal: | 1057.0751
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster (dump) |  |  |  | 1 | 10 | 53.9872 | 539.8719
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 4415.9536
Material | [6 empty] | Total
Grout/cy | 84 | 6 | cy | (Note: assumes 16" pipe) |  |  | 504
Sales tax @ | 7% | [5 empty] | 35.28
Miscellaneous (2% of labor) | [6 empty] | 88.3191
[6 empty] | Subtotal: | 627.5991
|  |  |  | Total Direct Costs (3) = |  |  | 6100.6277
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 13 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. D. Small stream crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 37.4213
[6 empty] | Subtotal: | 241.3325
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 1871.0635
Material | [6 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 1000
Sales tax @ | 7% | [5 empty] | 70
[6 empty] | Subtotal: | 1070
|  |  |  | Total Direct Costs (4) = |  |  | 3182.396
Summary: Small Stream Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 4133.5492
2. Excavate and cap pipe ends | [6 empty] | 14218.8329
3. Fill pipe with grout, backfill trench, grade disturbed areas | [6 empty] | 6100.6277
4. Restore sites | [6 empty] | 3182.396
|  |  |  | Pipeline contractor direct costs: |  |  | 27635.4058
|  |  |  | 5% Mobilization |  |  | 1381.7703
[6 empty] | Subtotal: | 29017.1761
|  |  |  | 15% Contractor overhead: |  |  | 4352.5764
[6 empty] | Subtotal: | 33369.7525
|  |  |  | 10% Contractor profit: |  |  | 3336.9753
|  |  |  | Total pipeline contractor costs: |  |  | 36706.7278
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
1835.3364
|  |  |  | Total environmental contractor cost: |  |  | 1835.3364
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 4
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2000
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 14 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. D. Small stream crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
6081.3096
|  |  |  | Total management and overhead cost: |  |  | 6081.3096
|  | Total cost to retire a small stream crossing (A + B + C + D): |  |  |  |  | 46623
|  | No. of small stream crossings: |  |  |  |  | 1678
|  | Total estimated cost to retire small stream crossings: |  |  |  |  | 78233394

## River Crossings
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 15 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
E. River crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical river crossing (500 feet). Work
includes ROW fence removal, excavation and shoring of trench, capping pipe ends, filling pipe with grout, and
restoration of area. Estimate also includes environmental inspection, pipeline company inspection, and pipeline
company management and overhead.
1. Remove ROW fence and access work sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
lowboy |  |  |  | 1 | 20 | 50.2615 | 1005.2304
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 3398.4265
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 12878.2063
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 257.5641
|  |  |  | Total Direct Costs (1) = |  |  | 16534.1969
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
lowboy |  |  |  | 1 | 20 | 50.2615 | 1005.2304
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 3398.4265
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 16 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. E. River crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 12878.2063
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 257.5641
|  |  |  | Total Direct Costs (2) = |  |  | 16534.1969
3. Fill pipe with grout (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
grout pump, trailer mounted |  |  |  | 1 | 10 | 26.4465 | 264.4648
lights, trailer mounted |  |  |  | 1 | 10 | 6.0757 | 60.7568
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 75.4248
[6 empty] | Subtotal: | 582.9168
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 56.8985 | 568.9848
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 6 |  | 90 | 540
[6 empty] | Subtotal: | 3771.2398
Material | [6 empty] | Total
Grout/cy | 84 | 28 | cy | (Note: assumes 16" pipe) |  |  | 2352
Sales tax @ | 7% | [5 empty] | 164.64
Miscellaneous (2% of labor) | [6 empty] | 75.4248
[6 empty] | Subtotal: | 2592.0648
|  |  |  | Total Direct Costs (3) = |  |  | 6946.2214
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 17 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. E. River crossings (continued)
4. Backfill trench, grade disturbed areas (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
dump truck 8 cy |  |  |  | 1 | 20 | 22.2809 | 445.6176
lowboy |  |  |  | 1 | 20 | 50.2615 | 1005.2304
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 201.833
[6 empty] | Subtotal: | 2916.585
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 8 |  | 90 | 1440
[6 empty] | Subtotal: | 10091.651
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 201.833
[6 empty] | Subtotal: | 201.833
|  |  |  | Total Direct Costs (4) = |  |  | 13210.0691
5. Restore sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 149.6851
[6 empty] | Subtotal: | 965.3299
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 20 | 53.9872 | 1079.7439
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 6 |  | 90 | 1080
[6 empty] | Subtotal: | 7484.254
Material | [6 empty] | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 2000
Sales tax @ | 7% | [5 empty] | 140
[6 empty] | Subtotal: | 2140
|  |  |  | Total Direct Costs (5) = |  |  | 10589.5838
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 18 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. E. River crossings (continued)
Summary: River Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 16534.1969
2. Excavate and cap pipe ends | [6 empty] | 16534.1969
3. Fill pipe with grout | [6 empty] | 6946.2214
4. Backfill trench, grade disturbed areas | [6 empty] | 13210.0691
5. Restore sites | [6 empty] | 10589.5838
|  |  |  | Pipeline contractor direct costs: |  |  | 63814.2681
|  |  |  | 5% Mobilization |  |  | 3190.7134
[6 empty] | Subtotal: | 67004.9815
|  |  |  | 15% Contractor overhead: |  |  | 10050.7472
[6 empty] | Subtotal: | 77055.7288
|  |  |  | 10% Contractor profit: |  |  | 7705.5729
|  |  |  | Total pipeline contractor costs: |  |  | 84761.3017
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
4238.0651
|  |  |  | Total environmental contractor cost: |  |  | 4238.0651
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 9
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 4500
D. Pipeline company management and overhead costs (15% of A + B + C)
14024.905
|  |  |  | Total management and overhead cost: |  |  | 14024.905
|  | Total cost to retire a river crossing (A + B + C + D): |  |  |  |  | 107524
|  | No. of river crossings: |  |  |  |  | 170
|  | Total estimated cost to retire river crossings: |  |  |  |  | 18279080

## Mainline Valves
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 19 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
F. Mainline valve sites
Description of Work:
Detailed cost estimate below reflects work required to retire a typical mainline valve site. Work includes
ROW fence removal, excavation, removal of valves and blowdowns, capping pipelines, excavation of gravel,
and restoration of area. Estimate also includes environmental inspection, pipeline company inspection, and
pipeline company management and overhead.
1. Remove ROW fence and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 52.7126
[6 empty] | Subtotal: | 792.3606
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 8 |  | 90 | 360
[6 empty] | Subtotal: | 2635.6323
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 52.7126
[6 empty] | Subtotal: | 52.7126
|  |  |  | Total Direct Costs (1) = |  |  | 3480.7055
2. Excavate, remove valves and blowdowns, cap pipe ends (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
crane, Grove 25 ton |  |  |  | 1 | 10 | 53.3806 | 533.8064
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 108.074
[6 empty] | Subtotal: | 1618.5612
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 20 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. F. Mainline valve sites (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
operator (crane) |  |  |  | 1 | 10 | 67.2307 | 672.3068
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 10 | 71.3693 | 713.6927
helper |  |  |  | 1 | 10 | 49.9585 | 499.5849
laborer |  |  |  | 2 | 10 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 8 |  | 90 | 720
[6 empty] | Subtotal: | 5403.6994
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 108.074
[6 empty] | Subtotal: | 108.074
|  |  |  | Total Direct Costs (2) = |  |  | 7130.3346
3. Remove gravel and miscellaneous debris, grade disturbed area (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
dump truck, 8 cy |  |  |  | 1 | 5 | 22.2809 | 111.4044
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 32.4811
[6 empty] | Subtotal: | 414.2939
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 5 |  | 90 | 225
[6 empty] | Subtotal: | 1624.0575
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 32.4811
[6 empty] | Subtotal: | 32.4811
|  |  |  | Total Direct Costs (3) = |  |  | 2070.8326
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 21 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. F. Mainline valve sites (continued)
4. Restore site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 26.1824
[6 empty] | Subtotal: | 184.526
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 58.3827 | 291.9133
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 4 |  | 90 | 180
[6 empty] | Subtotal: | 1309.1215
Material | [6 empty] | Total
allow $ 500 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 500
Sales tax @ | 7% | [5 empty] | 35
[6 empty] | Subtotal: | 535
|  |  |  | Total Direct Costs (4) = |  |  | 2028.6476
Summary: Mainline Valve Sites
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 3480.7055
2. Excavate and remove valves and blowdowns | [6 empty] | 7130.3346
3. Remove gravel and miscellaneous debris | [6 empty] | 2070.8326
4. Restore site | [6 empty] | 2028.6476
|  |  |  | Pipeline contractor direct costs: |  |  | 14710.5202
|  |  |  | 5% Mobilization |  |  | 735.526
[6 empty] | Subtotal: | 15446.0463
|  |  |  | 15% Contractor overhead: |  |  | 2316.9069
[6 empty] | Subtotal: | 17762.9532
|  |  |  | 10% Contractor profit: |  |  | 1776.2953
|  |  |  | Total pipeline contractor costs: |  |  | 19539.2485
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
976.9624
|  |  |  | Total environmental contractor cost: |  |  | 976.9624
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 22 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. F. Mainline valve sites (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 2.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 1250
D. Pipeline company management and overhead costs (15% of A + B + C)
3264.9316
|  |  |  | Total management and overhead cost: |  |  | 3264.9316
|  | Total cost to retire a mainline valve site (A + B + C + D): |  |  |  |  | 25031
|  | No. of mainline valve sites: |  |  |  |  | 487
|  | Total estimated cost to retire mainline valve sites: |  |  |  |  | 12190097

## Pipeline Drips
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 23 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
G. Pipeline Drips
Description of Work:
Detailed cost estimate below reflects work required to retire a typical pipeline drip. Work includes ROW fence
removal, excavation, removal of section of pipeline and drip tank, capping pipelines, excavation of gravel,
and restoration of area. Estimate also includes environmental inspection, pipeline company inspection, and
pipeline company management and overhead.
1. Remove ROW fence and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 52.7126
[6 empty] | Subtotal: | 792.3606
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 8 |  | 90 | 360
[6 empty] | Subtotal: | 2635.6323
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 52.7126
[6 empty] | Subtotal: | 52.7126
|  |  |  | Total Direct Costs (1) = |  |  | 3480.7055
2. Excavate and remove section of pipeline and drip tank (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
crane, Grove 25 ton |  |  |  | 1 | 10 | 53.3806 | 533.8064
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 108.074
[6 empty] | Subtotal: | 1618.5612
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 24 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. G. Pipeline drips (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
operator (crane) |  |  |  | 1 | 10 | 67.2307 | 672.3068
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 10 | 71.3693 | 713.6927
helper |  |  |  | 1 | 10 | 49.9585 | 499.5849
laborer |  |  |  | 2 | 10 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 8 |  | 90 | 720
[6 empty] | Subtotal: | 5403.6994
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 108.074
[6 empty] | Subtotal: | 108.074
|  |  |  | Total Direct Costs (2) = |  |  | 7130.3346
3. Remove gravel and miscellaneous debris, grade disturbed area (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 5 | 44.9682 | 224.8408
dump truck, 8 cy |  |  |  | 1 | 5 | 22.2809 | 111.4044
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 32.4811
[6 empty] | Subtotal: | 414.2939
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 5 |  | 90 | 225
[6 empty] | Subtotal: | 1624.0575
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 32.4811
[6 empty] | Subtotal: | 32.4811
|  |  |  | Total Direct Costs (3) = |  |  | 2070.8326
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 25 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. G. Pipeline drips (continued)
4. Restore site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 26.1824
[6 empty] | Subtotal: | 184.526
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 58.3827 | 291.9133
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 4 |  | 90 | 180
[6 empty] | Subtotal: | 1309.1215
Material | [6 empty] | Total
allow $ 500 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 500
Sales tax @ | 7% | [5 empty] | 35
[6 empty] | Subtotal: | 535
|  |  |  | Total Direct Costs (4) = |  |  | 2028.6476
Summary: Pipeline Drips
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 3480.7055
2. Excavate and remove section of pipeline and drip tank | [6 empty] | 7130.3346
3. Remove gravel and miscellaneous debris | [6 empty] | 2070.8326
4. Restore site | [6 empty] | 2028.6476
|  |  |  | Pipeline contractor direct costs: |  |  | 14710.5202
|  |  |  | 5% Mobilization |  |  | 735.526
[6 empty] | Subtotal: | 15446.0463
|  |  |  | 15% Contractor overhead: |  |  | 2316.9069
[6 empty] | Subtotal: | 17762.9532
|  |  |  | 10% Contractor profit: |  |  | 1776.2953
|  |  |  | Total pipeline contractor costs: |  |  | 19539.2485
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
976.9624
|  |  |  | Total environmental contractor cost: |  |  | 976.9624
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 26 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. G. Pipeline drips (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 2.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 1250
D. Pipeline company management and overhead costs (15% of A + B + C)
3264.9316
|  |  |  | Total management and overhead cost: |  |  | 3264.9316
|  | Total cost to retire a pipeline drip (A + B + C + D): |  |  |  |  | 25031
|  | No. of pipeline drips: |  |  |  |  | 178
|  | Total estimated cost to retire pipeline drips: |  |  |  |  | 4455518

## Cathodic Protection
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 27 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
H. Cathodic protection facilities
Description of Work:
Detailed cost estimate below reflects work required to remove cathodic protection test sites and rectifiers.
Work includes removal of test sites and rectifiers and associated electrical equipment. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove test sites
Equipment |  |  |  | No. | Hours | Rate | Total
1/2 ton pickup with 4wd |  |  |  | 1 | 1 | 9.1135 | 9.1135
small tools, 2% of labor | [6 empty] | 3.8888
[6 empty] | Subtotal: | 13.0024
Labor |  |  |  | No. | Hours | Rate | Total
laborer |  |  |  | 2 | 1 | 49.3919 | 98.7839
foreman |  |  |  | 1 | 1 | 68.6578 | 68.6578
per diem | 0.1 | day | crew size: | 3 |  | 90 | 27
[6 empty] | Subtotal: | 194.4416
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 3.8888
[6 empty] | Subtotal: | 3.8888
|  |  |  | Total Direct Costs (1) = |  |  | 211.3328
Summary: Remove Test Sites
A. Pipeline contractor costs
|  |  |  | Pipeline contractor direct costs: |  |  | 211.3328
|  |  |  | 5% Mobilization |  |  | 10.5666
[6 empty] | Subtotal: | 221.8995
|  |  |  | 15% Contractor overhead: |  |  | 33.2849
[6 empty] | Subtotal: | 255.1844
|  |  |  | 10% Contractor profit: |  |  | 25.5184
|  |  |  | Total pipeline contractor costs: |  |  | 280.7028
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
14.0351
|  |  |  | Total environmental contractor cost: |  |  | 14.0351
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 28 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. H. Cathodic protection facilities (continued)
1. Remove test sites (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 0.1
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 50
D. Pipeline company management and overhead costs (15% of A + B + C)
51.7107
|  |  |  | Total management and overhead cost: |  |  | 51.7107
|  |  | Total cost to remove a C.P. test site (A + B + C + D): |  |  |  | 396
|  |  | No. of cathodic protection test sites: |  |  |  | 8564
|  |  | Total estimated cost to remove test sites: |  |  |  | 3391344
2. Remove rectifiers
Equipment |  |  |  | No. | Hours | Rate | Total
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 20.8203
[6 empty] | Subtotal: | 171.5439
Labor |  |  |  | No. | Hours | Rate | Total
electrician |  |  |  | 1 | 5 | 66.2032 | 331.0158
helper |  |  |  | 1 | 5 | 46.3422 | 231.7111
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 3 |  | 90 | 135
[6 empty] | Subtotal: | 1041.0158
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 20.8203
[6 empty] | Subtotal: | 20.8203
|  |  |  | Total Direct Costs (1) = |  |  | 1233.3801
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 29 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. H. Cathodic protection facilities (continued)
Summary: Remove Rectifiers
A. Pipeline contractor costs
|  |  |  | Pipeline contractor direct costs: |  |  | 1233.3801
|  |  |  | 5% Mobilization |  |  | 61.669
[6 empty] | Subtotal: | 1295.0491
|  |  |  | 15% Contractor overhead: |  |  | 194.2574
[6 empty] | Subtotal: | 1489.3064
|  |  |  | 10% Contractor profit: |  |  | 148.9306
|  |  |  | Total pipeline contractor costs: |  |  | 1638.2371
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
81.9119
|  |  |  | Total environmental contractor cost: |  |  | 81.9119
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 0.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 250
D. Pipeline company management and overhead costs (15% of A + B + C)
295.5223
|  |  |  | Total management and overhead cost: |  |  | 295.5223
|  |  | Total cost to remove a rectifier (A + B + C + D): |  |  |  | 2266
|  |  | No. of rectifiers: |  |  |  | 597
|  |  | Total estimated cost to remove rectifiers: |  |  |  | 1352802

## Pipeline Marker
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 30 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
I. Pipeline markers
Description of Work:
Detailed cost estimate below reflects work required to remove a pipeline marker.
1. Remove pipeline marker
Equipment |  | No. | Hours | Rate | Total
1/2 ton pickup with 4wd |  | 1 | 0.25 | 9.1135 | 2.2784
small tools, 2% of labor |  |  |  |  | 0.83721
|  |  |  | Subtotal: | 3.1156
Labor |  | No. | Hours | Rate | Total
laborer |  | 2 | 0.25 | 49.3919 | 24.696
foreman |  | 1 | 0.25 | 68.6578 | 17.1644
|  |  |  | Subtotal: | 41.8604
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 0.83721
|  |  |  | Subtotal: | 0.83721
|  | Total Direct Costs (1) = |  |  | 45.8132
Summary: Pipeline Markers
A. Pipeline contractor costs
|  | Pipeline contractor direct costs: |  |  | 45.8132
|  |  |  | Subtotal: | 45.8132
|  | 5% Mobilization |  |  | 2.2907
|  |  |  | Subtotal: | 48.1039
|  | 15% Contractor overhead: |  |  | 7.2156
|  |  |  | Subtotal: | 55.3194
|  | 10% Contractor profit: |  |  | 5.5319
|  | Total pipeline contractor costs: |  |  | 60.8514
B. Pipeline company management and overhead costs (15% of A) |  |  |  |  | 9.1277
|  | Total management and overhead cost: |  |  | 9.1277
| Total cost to remove a pipeline marker (A + B): |  |  |  | 70
| No. of pipeline markers: |  |  |  | 34780
| Total estimated cost to remove pipeline markers: |  |  |  | 2434600

## Small M&R
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 31 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
J. M&R stations
1. Small
Description of Work:
Detailed cost estimate below reflects work required to retire a typical small M&R station. Work includes
ROW fence removal, excavation, removal of valves, blowdowns, meter runs and regulators, removal of meter
and control building(s), capping pipelines, excavation of gravel, and restoration of area. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C |  |  |  | 1 | 5 | 36.0375 | 180.1876
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 804.9534
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 2 | 5 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 4 | 5 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3219.5516
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 64.391
[6 empty] | Subtotal: | 64.391
|  |  |  | Total Direct Costs (1) = |  |  | 4088.896
2. Excavate, remove valves, blowdowns and meter runs, cap pipe ends, demolish control bldgs (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C w hammer |  |  |  | 1 | 50 | 43.6067 | 2180.336
hydrocrane, Grove 25 ton |  |  |  | 1 | 50 | 53.3806 | 2669.032
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
3/4 ton pick-up with trailer |  |  |  | 2 | 50 | 21.0312 | 2103.12
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 796.4816
[6 empty] | Subtotal: | 9788.0816
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 32 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 1. Small M&R stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 50 | 58.3827 | 2919.133
operator (hydrocrane) |  |  |  | 1 | 50 | 67.2307 | 3361.5341
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
pipefitter/welder |  |  |  | 2 | 50 | 71.3693 | 7136.9271
helper |  |  |  | 2 | 50 | 49.9585 | 4995.849
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 12 |  | 90 | 5400
[6 empty] | Subtotal: | 39824.0781
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 796.4816
[6 empty] | Subtotal: | 796.4816
|  |  |  | Total Direct Costs (2) = |  |  | 50408.6412
3. Remove gravel and miscellaneous debris (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 10 | 51.6128 | 516.128
dump truck 14 cy |  |  |  | 2 | 10 | 23.3985 | 467.9696
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 100.9165
[6 empty] | Subtotal: | 1267.2845
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 2 | 10 | 53.9872 | 1079.7439
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 8 |  | 90 | 720
[6 empty] | Subtotal: | 5045.8255
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 100.9165
[6 empty] | Subtotal: | 100.9165
|  |  |  | Total Direct Costs (3) = |  |  | 6414.0265
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 33 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 1. Small M&R stations (continued)
4. Restore site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 10 | 51.6128 | 516.128
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 88.3191
[6 empty] | Subtotal: | 1012.2695
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 4415.9536
Material | [6 empty] | Total
allow $ 5000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 5000
Sales tax @ | 7% | [5 empty] | 350
[6 empty] | Subtotal: | 5350
|  |  |  | Total Direct Costs (4) = |  |  | 10778.2231
Summary: Small M&R Stations
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 4088.896
2. Excavate, remove valves, blowdowns and meter runs, cap pipe ends | [6 empty] | 50408.6412
3. Remove gravel and miscellaneous debris | [6 empty] | 6414.0265
4. Restore site | [6 empty] | 10778.2231
|  |  |  | Pipeline contractor direct costs: |  |  | 71689.7868
|  |  |  | 5% Mobilization |  |  | 3584.4893
[6 empty] | Subtotal: | 75274.2762
|  |  |  | 15% Contractor overhead: |  |  | 11291.1414
[6 empty] | Subtotal: | 86565.4176
|  |  |  | 10% Contractor profit: |  |  | 8656.5418
|  |  |  | Total pipeline contractor costs: |  |  | 95221.9593
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
4761.098
|  |  |  | Total environmental contractor cost: |  |  | 4761.098
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 34 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 1. Small M&R stations (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 7.5
2. Company cost per day | [6 empty] | 500
|  | Total company inspection cost per site: |  |  |  |  | 3750
D. Pipeline company management and overhead costs (15% of A + B + C)
15559.9586
|  |  |  | Total management and overhead cost: |  |  | 15559.9586
|  | Total cost to retire a small M&R station (A + B + C + D): |  |  |  |  | 119293
|  | No. of small M&R stations: |  |  |  |  | 296
|  | Total estimated cost to retire remote small M&R stations: |  |  |  |  | 35310728

## Medium M&R
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 35 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
J. M&R stations
2. Medium
Description of Work:
Detailed cost estimate below reflects work required to retire a typical medium M&R station. Work includes
ROW fence removal, excavation, removal of valves, blowdowns, meter runs and regulators, removal of meter
and control building(s), capping pipelines, excavation of gravel, and restoration of area. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
lowboy |  |  |  | 1 | 10 | 50.2615 | 502.6152
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 128.7821
[6 empty] | Subtotal: | 1699.2133
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 2 | 10 | 53.9872 | 1079.7439
pipefitter/welder |  |  |  | 1 | 10 | 71.3693 | 713.6927
helper |  |  |  | 1 | 10 | 49.9585 | 499.5849
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 10 |  | 90 | 900
[6 empty] | Subtotal: | 6439.1031
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 128.7821
[6 empty] | Subtotal: | 128.7821
|  |  |  | Total Direct Costs (1) = |  |  | 8267.0985
2. Excavate, remove valves, blowdowns and meter runs, cap pipe ends, demolish control bldgs (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C w hammer |  |  |  | 1 | 100 | 67.0052 | 6700.52
hydrocrane, Grove 25 ton |  |  |  | 1 | 100 | 53.3806 | 5338.064
flatbed truck |  |  |  | 1 | 100 | 22.5552 | 2255.52
3/4 ton pick-up with trailer |  |  |  | 2 | 100 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 2 | 100 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 1592.9631
[6 empty] | Subtotal: | 21916.0111
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 36 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 2. Medium M&R stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 100 | 58.3827 | 5838.2661
operator (hydrocrane) |  |  |  | 1 | 100 | 67.2307 | 6723.0681
teamster |  |  |  | 1 | 100 | 53.9872 | 5398.7193
pipefitter/welder |  |  |  | 2 | 100 | 71.3693 | 14273.8542
helper |  |  |  | 2 | 100 | 49.9585 | 9991.6979
laborer |  |  |  | 4 | 100 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 12 |  | 90 | 10800
[6 empty] | Subtotal: | 79648.1561
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1592.9631
[6 empty] | Subtotal: | 1592.9631
|  |  |  | Total Direct Costs (2) = |  |  | 103157.1304
3. Remove gravel and miscellaneous debris (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 20 | 51.6128 | 1032.256
dump truck 14 cy |  |  |  | 3 | 20 | 23.3985 | 1403.9088
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 227.0279
[6 empty] | Subtotal: | 3027.7335
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 3 | 20 | 53.9872 | 3239.2316
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 11351.3949
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 227.0279
[6 empty] | Subtotal: | 227.0279
|  |  |  | Total Direct Costs (3) = |  |  | 14606.1563
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 37 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 2. Medium M&R stations (continued)
4. Restore site (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 20 | 51.6128 | 1032.256
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 176.6381
[6 empty] | Subtotal: | 2024.5389
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 1 | 20 | 53.9872 | 1079.7439
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 7 |  | 90 | 1260
[6 empty] | Subtotal: | 8831.9072
Material | [6 empty] | Total
allow $ 10,000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 10000
Sales tax @ | 7% | [5 empty] | 700
[6 empty] | Subtotal: | 10700
|  |  |  | Total Direct Costs (4) = |  |  | 21556.4461
Summary: Medium M&R Stations
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 8267.0985
2. Excavate, remove valves, blowdowns and meter runs, cap pipe ends | [6 empty] | 103157.1304
3. Remove gravel and miscellaneous debris | [6 empty] | 14606.1563
4. Restore site | [6 empty] | 21556.4461
|  |  |  | Pipeline contractor direct costs: |  |  | 147586.8313
|  |  |  | 5% Mobilization |  |  | 7379.3416
[6 empty] | Subtotal: | 154966.1728
|  |  |  | 15% Contractor overhead: |  |  | 23244.9259
[6 empty] | Subtotal: | 178211.0987
|  |  |  | 10% Contractor profit: |  |  | 17821.1099
|  |  |  | Total pipeline contractor costs: |  |  | 196032.2086
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
9801.6104
|  |  |  | Total environmental contractor cost: |  |  | 9801.6104
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 38 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. J. 2. Medium M&R stations (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 15
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 7500
D. Pipeline company management and overhead costs (15% of A + B + C)
32000.0729
|  |  |  | Total management and overhead cost: |  |  | 32000.0729
|  | Total cost to retire a medium M&R station (A + B + C + D): |  |  |  |  | 245334
|  | No. of medium M&R stations: |  |  |  |  | 40
|  | Total estimated cost to retire medium M&R stations: |  |  |  |  | 9813360

## Large Comp
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 39 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
K. Compressor stations
1. Large
Description of Work:
Detailed cost estimate below reflects work required to retire a typical large compressor station. Work includes
removal of fence and miscellaneous material, valves, blowdowns, piping, compressor station equipment,
and buildings; excavation of concrete foundations and gravel; and site restoration. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove fence and miscellaneous material and access work site (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 2 | 20 | 44.9682 | 1798.7264
flatbed truck |  |  |  | 2 | 20 | 22.5552 | 902.208
lowboy |  |  |  | 2 | 20 | 50.2615 | 2010.4608
3/4 ton pick-up with trailer |  |  |  | 2 | 20 | 21.0312 | 841.248
1/2 ton pickup with 4wd |  |  |  | 4 | 20 | 9.1135 | 729.0816
small tools, 2% of labor | [6 empty] | 515.1283
[6 empty] | Subtotal: | 6796.8531
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 2 | 20 | 58.3827 | 2335.3064
teamster |  |  |  | 4 | 20 | 53.9872 | 4318.9754
pipefitter/welder |  |  |  | 2 | 20 | 71.3693 | 2854.7708
helper |  |  |  | 2 | 20 | 49.9585 | 1998.3396
laborer |  |  |  | 8 | 20 | 49.3919 | 7902.709
foreman |  |  |  | 2 | 20 | 68.6578 | 2746.3112
per diem | 2 | days | crew size: | 20 |  | 90 | 3600
[6 empty] | Subtotal: | 25756.4125
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 515.1283
[6 empty] | Subtotal: | 515.1283
|  |  |  | Total Direct Costs (1) = |  |  | 33068.3938
2. Excavate, remove valves, blowdowns, and yard piping (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 4 | 100 | 44.9682 | 17987.264
hydrocrane, Grove 30 ton |  |  |  | 4 | 100 | 60.8178 | 24327.104
flatbed truck |  |  |  | 4 | 100 | 22.5552 | 9022.08
3/4 ton pick-up with trailer |  |  |  | 4 | 100 | 21.0312 | 8412.48
1/2 ton pickup with 4wd |  |  |  | 4 | 100 | 9.1135 | 3645.408
small tools, 2% of labor | [6 empty] | 3857.0128
[6 empty] | Subtotal: | 67251.3488
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 40 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 1. Large compressor stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 4 | 100 | 58.3827 | 23353.0644
operator (hydrocrane) |  |  |  | 4 | 100 | 67.2307 | 26892.2724
teamster |  |  |  | 4 | 100 | 53.9872 | 21594.8772
pipefitter/welder |  |  |  | 4 | 100 | 71.3693 | 28547.7084
helper |  |  |  | 4 | 100 | 49.9585 | 19983.3959
laborer |  |  |  | 8 | 100 | 49.3919 | 39513.5448
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 29 |  | 90 | 26100
[6 empty] | Subtotal: | 192850.6412
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 3857.0128
[6 empty] | Subtotal: | 3857.0128
|  |  |  | Total Direct Costs (2) = |  |  | 263959.0028
3. Remove station equipment (15 days)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 4 | 150 | 60.8178 | 36490.656
flatbed truck |  |  |  | 4 | 150 | 22.5552 | 13533.12
3/4 ton pick-up with trailer |  |  |  | 8 | 150 | 21.0312 | 25237.44
1/2 ton pickup with 4wd |  |  |  | 8 | 150 | 9.1135 | 10936.224
small tools, 2% of labor | [6 empty] | 8050.2668
[6 empty] | Subtotal: | 94247.7068
Labor |  |  |  | No. | Hours | Rate | Total
operator (crane) |  |  |  | 4 | 150 | 67.2307 | 40338.4086
teamster |  |  |  | 4 | 150 | 53.9872 | 32392.3158
pipefitter/welder |  |  |  | 8 | 150 | 71.3693 | 85643.1252
helper |  |  |  | 8 | 150 | 49.9585 | 59950.1876
laborer |  |  |  | 16 | 150 | 49.3919 | 118540.6344
foreman |  |  |  | 1 | 150 | 68.6578 | 10298.6671
per diem | 15 | days | crew size: | 41 |  | 90 | 55350
[6 empty] | Subtotal: | 402513.3388
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 8050.2668
[6 empty] | Subtotal: | 8050.2668
|  |  |  | Total Direct Costs (3) = |  |  | 504811.3123
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 41 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 1. Large compressor stations (continued)
4. Remove station buildings (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320CL w grapple |  |  |  | 2 | 100 | 60.7873 | 12157.456
backhoe, Cat 320CL w shears |  |  |  | 2 | 100 | 79.7763 | 15955.264
backhoe, Cat 320C w hammer |  |  |  | 2 | 100 | 67.0052 | 13401.04
hydrocrane, 30 ton |  |  |  | 4 | 100 | 60.8178 | 24327.104
flatbed truck |  |  |  | 4 | 100 | 22.5552 | 9022.08
lowboy |  |  |  | 2 | 100 | 50.2615 | 10052.304
3/4 ton pick-up with trailer |  |  |  | 8 | 100 | 21.0312 | 16824.96
1/2 ton pickup with 4wd |  |  |  | 8 | 100 | 9.1135 | 7290.816
small tools, 2% of labor | [6 empty] | 6427.3852
[6 empty] | Subtotal: | 115458.4092
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 6 | 100 | 58.3827 | 35029.5966
operator (hydrocrane) |  |  |  | 4 | 100 | 67.2307 | 26892.2724
teamster |  |  |  | 6 | 100 | 53.9872 | 32392.3158
pipefitter/welder |  |  |  | 8 | 100 | 71.3693 | 57095.4168
helper |  |  |  | 8 | 100 | 49.9585 | 39966.7918
laborer |  |  |  | 16 | 100 | 49.3919 | 79027.0896
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 49 |  | 90 | 44100
[6 empty] | Subtotal: | 321369.2611
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 6427.3852
[6 empty] | Subtotal: | 6427.3852
|  |  |  | Total Direct Costs (4) = |  |  | 443255.0555
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (15 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C w hammer |  |  |  | 8 | 150 | 67.0052 | 80406.24
backhoe, Cat 320C |  |  |  | 2 | 150 | 44.9682 | 13490.448
dump truck 14 cy |  |  |  | 4 | 150 | 23.3985 | 14039.088
3/4 ton pick-up with trailer |  |  |  | 8 | 150 | 21.0312 | 25237.44
1/2 ton pickup with 4wd |  |  |  | 4 | 150 | 9.1135 | 5468.112
small tools, 2% of labor | [6 empty] | 7755.5721
[6 empty] | Subtotal: | 146396.9001
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 42 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 1. Large compressor stations (continued)
Line Item 5 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 10 | 150 | 58.3827 | 87573.9915
teamster |  |  |  | 4 | 150 | 53.9872 | 32392.3158
pipefitter/welder |  |  |  | 8 | 150 | 71.3693 | 85643.1252
helper |  |  |  | 8 | 150 | 49.9585 | 59950.1876
laborer |  |  |  | 8 | 150 | 49.3919 | 59270.3172
foreman |  |  |  | 1 | 150 | 68.6578 | 10298.6671
per diem | 15 | days | crew size: | 39 |  | 90 | 52650
[6 empty] | Subtotal: | 387778.6045
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 7755.5721
[6 empty] | Subtotal: | 7755.5721
|  |  |  | Total Direct Costs (5) = |  |  | 541931.0767
6. Restore site (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 2 | 50 | 51.6128 | 5161.28
flatbed truck |  |  |  | 2 | 50 | 22.5552 | 2255.52
1/2 ton pickup with 4wd |  |  |  | 4 | 50 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 805.5329
[6 empty] | Subtotal: | 10045.0369
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 2 | 50 | 58.3827 | 5838.2661
teamster |  |  |  | 2 | 50 | 53.9872 | 5398.7193
laborer |  |  |  | 8 | 50 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 13 |  | 90 | 5850
[6 empty] | Subtotal: | 40276.6468
Material | [6 empty] | Total
allow $ 20000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 20000
Sales tax @ | 7% | [5 empty] | 1400
[6 empty] | Subtotal: | 21400
|  |  |  | Total Direct Costs (6) = |  |  | 71721.6838
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 43 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 1. Large compressor stations (continued)
Summary: Large Compressor Stations
A. Pipeline contractor costs
1. Remove fence and miscellaneous material and access work site | [6 empty] | 33068.3938
2. Excavate, remove valves, blowdowns, and yard piping | [6 empty] | 263959.0028
3. Remove station equipment | [6 empty] | 504811.3123
4. Remove station buildings | [6 empty] | 443255.0555
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface | [6 empty] | 541931.0767
6. Restore site | [6 empty] | 71721.6838
|  |  |  | Pipeline contractor direct costs: |  |  | 1858746.5249
|  |  |  | 5% Mobilization |  |  | 92937.3262
[6 empty] | Subtotal: | 1951683.8512
|  |  |  | 15% Contractor overhead: |  |  | 292752.5777
[6 empty] | Subtotal: | 2244436.4289
|  |  |  | 10% Contractor profit: |  |  | 224443.6429
|  |  |  | Total pipeline contractor costs: |  |  | 2468880.0717
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 123444.0036
|  |  |  | Total environmental contractor costs: |  |  | 123444.0036
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 57
2. Company cost per day | [6 empty] | 1000
|  | Total company inspection cost per site: |  |  |  |  | 57000
D. Pipeline company management and overhead costs (15% of A + B + C)
397398.6113
|  |  |  | Total management and overhead cost: |  |  | 397398.6113
| Total cost to retire typical large compressor station (A + B + C + D): | [5 empty] | 3046722.6866
Transmission Compressor Stations (Large)
Estimated
| Name of | Location by | Station | No. of | Station | Retirement
| Station | State | No. | Units | HP | Cost
1 | Hugoton | Kansas | 518 | 6 | 22100 | 3046722.6866

## Medium Comp
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 44 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
K. Compressor stations
2. Medium
Description of Work:
Detailed cost estimate below reflects work required to retire a typical medium compressor station. Work
includes removal of fence and misc. material, valves, blowdowns, piping, compressor station equipment,
and buildings; excavation of concrete foundations and gravel; and site restoration. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove fence and miscellaneous material and access work site (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
lowboy |  |  |  | 1 | 20 | 50.2615 | 1005.2304
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 3398.4265
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 12878.2063
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 257.5641
|  |  |  | Total Direct Costs (1) = |  |  | 16534.1969
2. Excavate, remove valves, blowdowns, and yard piping (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 2 | 100 | 44.9682 | 8993.632
hydrocrane, Grove 30 ton |  |  |  | 2 | 100 | 60.8178 | 12163.552
flatbed truck |  |  |  | 2 | 100 | 22.5552 | 4511.04
3/4 ton pick-up with trailer |  |  |  | 2 | 100 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 2 | 100 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 2006.1642
[6 empty] | Subtotal: | 33703.3322
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 45 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 2. Medium compressor stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 2 | 100 | 58.3827 | 11676.5322
operator (hydrocrane) |  |  |  | 2 | 100 | 67.2307 | 13446.1362
teamster |  |  |  | 2 | 100 | 53.9872 | 10797.4386
pipefitter/welder |  |  |  | 2 | 100 | 71.3693 | 14273.8542
helper |  |  |  | 2 | 100 | 49.9585 | 9991.6979
laborer |  |  |  | 4 | 100 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 15 |  | 90 | 13500
[6 empty] | Subtotal: | 100308.2096
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 2006.1642
[6 empty] | Subtotal: | 2006.1642
|  |  |  | Total Direct Costs (2) = |  |  | 136017.706
3. Remove station equipment (15 days)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 2 | 150 | 60.8178 | 18245.328
flatbed truck |  |  |  | 2 | 150 | 22.5552 | 6766.56
3/4 ton pick-up with trailer |  |  |  | 4 | 150 | 21.0312 | 12618.72
1/2 ton pickup with 4wd |  |  |  | 4 | 150 | 9.1135 | 5468.112
small tools, 2% of labor | [6 empty] | 4141.6201
[6 empty] | Subtotal: | 47240.3401
Labor |  |  |  | No. | Hours | Rate | Total
operator (crane) |  |  |  | 2 | 150 | 67.2307 | 20169.2043
teamster |  |  |  | 2 | 150 | 53.9872 | 16196.1579
pipefitter/welder |  |  |  | 4 | 150 | 71.3693 | 42821.5626
helper |  |  |  | 4 | 150 | 49.9585 | 29975.0938
laborer |  |  |  | 8 | 150 | 49.3919 | 59270.3172
foreman |  |  |  | 1 | 150 | 68.6578 | 10298.6671
per diem | 15 | days | crew size: | 21 |  | 90 | 28350
[6 empty] | Subtotal: | 207081.003
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 4141.6201
[6 empty] | Subtotal: | 4141.6201
|  |  |  | Total Direct Costs (3) = |  |  | 258462.9631
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 46 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 2. Medium compressor stations (continued)
4. Remove station buildings (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320CL w grapple |  |  |  | 1 | 100 | 60.7873 | 6078.728
backhoe, Cat 320CL w shears |  |  |  | 1 | 100 | 79.7763 | 7977.632
hydrocrane, 30 ton |  |  |  | 1 | 100 | 60.8178 | 6081.776
flatbed truck |  |  |  | 2 | 100 | 22.5552 | 4511.04
lowboy |  |  |  | 1 | 100 | 50.2615 | 5026.152
3/4 ton pick-up with trailer |  |  |  | 4 | 100 | 21.0312 | 8412.48
1/2 ton pickup with 4wd |  |  |  | 4 | 100 | 9.1135 | 3645.408
small tools, 2% of labor | [6 empty] | 3004.1237
[6 empty] | Subtotal: | 44737.3397
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 2 | 100 | 58.3827 | 11676.5322
operator (hydrocrane) |  |  |  | 1 | 100 | 67.2307 | 6723.0681
teamster |  |  |  | 3 | 100 | 53.9872 | 16196.1579
pipefitter/welder |  |  |  | 4 | 100 | 71.3693 | 28547.7084
helper |  |  |  | 4 | 100 | 49.9585 | 19983.3959
laborer |  |  |  | 8 | 100 | 49.3919 | 39513.5448
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 23 |  | 90 | 20700
[6 empty] | Subtotal: | 150206.1854
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 3004.1237
[6 empty] | Subtotal: | 3004.1237
|  |  |  | Total Direct Costs (4) = |  |  | 197947.6488
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (15 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C w hammer |  |  |  | 4 | 150 | 67.0052 | 40203.12
backhoe, Cat 320C |  |  |  | 1 | 150 | 44.9682 | 6745.224
dump truck 14 cy |  |  |  | 2 | 150 | 23.3985 | 7019.544
3/4 ton pick-up with trailer |  |  |  | 4 | 150 | 21.0312 | 12618.72
1/2 ton pickup with 4wd |  |  |  | 2 | 150 | 9.1135 | 2734.056
small tools, 2% of labor | [6 empty] | 3994.2727
[6 empty] | Subtotal: | 73314.9367
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 47 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 2. Medium compressor stations (continued)
Line Item 5 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 5 | 150 | 58.3827 | 43786.9958
teamster |  |  |  | 2 | 150 | 53.9872 | 16196.1579
pipefitter/welder |  |  |  | 4 | 150 | 71.3693 | 42821.5626
helper |  |  |  | 4 | 150 | 49.9585 | 29975.0938
laborer |  |  |  | 4 | 150 | 49.3919 | 29635.1586
foreman |  |  |  | 1 | 150 | 68.6578 | 10298.6671
per diem | 15 | days | crew size: | 20 |  | 90 | 27000
[6 empty] | Subtotal: | 199713.6358
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 3994.2727
[6 empty] | Subtotal: | 3994.2727
|  |  |  | Total Direct Costs (5) = |  |  | 277022.8453
6. Restore site (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 50 | 51.6128 | 2580.64
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 441.5954
[6 empty] | Subtotal: | 5061.3474
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 50 | 58.3827 | 2919.133
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 7 |  | 90 | 3150
[6 empty] | Subtotal: | 22079.768
Material | [6 empty] | Total
allow $ 15000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 15000
Sales tax @ | 7% | [5 empty] | 1050
[6 empty] | Subtotal: | 16050
|  |  |  | Total Direct Costs (6) = |  |  | 43191.1153
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 48 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 2. Medium compressor stations (continued)
Summary: Medium Compressor Stations
A. Pipeline contractor costs
1. Remove fence and miscellaneous material and access work site | [6 empty] | 16534.1969
2. Excavate, remove valves, blowdowns, and yard piping | [6 empty] | 136017.706
3. Remove station equipment | [6 empty] | 258462.9631
4. Remove station buildings | [6 empty] | 197947.6488
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface | [6 empty] | 277022.8453
6. Restore site | [6 empty] | 43191.1153
|  |  |  | Pipeline contractor direct costs: |  |  | 929176.4754
|  |  |  | 5% Mobilization |  |  | 46458.8238
[6 empty] | Subtotal: | 975635.2991
|  |  |  | 15% Contractor overhead: |  |  | 146345.2949
[6 empty] | Subtotal: | 1121980.594
|  |  |  | 10% Contractor profit: |  |  | 112198.0594
|  |  |  | Total pipeline contractor costs: |  |  | 1234178.6534
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 61708.9327
|  |  |  | Total environmental contractor costs: |  |  | 61708.9327
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 57
2. Company cost per day | [6 empty] | 1000
|  | Total company inspection cost per site: |  |  |  |  | 57000
D. Pipeline company management and overhead costs (15% of A + B + C)
202933.1379
|  |  |  | Total management and overhead cost: |  |  | 202933.1379
| Total cost to retire typical medium compressor station (A + B + C + D): | [5 empty] | 1555820.724
Transmission Compressor Stations (Medium)
Estimated
| Name of | Location by | Station | No. of | Station | Retirement
| Station | State | No. | Units | HP | Cost
1 | Grabham | Kansas | 515 | 6 | 14135 | 1555820.724
2 | Hesston | Kansas | 536 | 8 | 10600 | 1555820.724
[5 empty] | Total: | 3111641.448

## Small Comp
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 49 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
K. Compressor stations
3. Small
Description of Work:
Detailed cost estimate below reflects work required to retire a typical small compressor station. Work includes
removal of fence and miscellaneous material, valves, blowdowns, piping, compressor station equipment,
and buildings; excavation of concrete foundations and gravel; and site restoration. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove fence and miscellaneous material and access work site (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 20 | 44.9682 | 899.3632
flatbed truck |  |  |  | 1 | 20 | 22.5552 | 451.104
lowboy |  |  |  | 1 | 20 | 50.2615 | 1005.2304
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 9.1135 | 364.5408
small tools, 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 3398.4265
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 58.3827 | 1167.6532
teamster |  |  |  | 2 | 20 | 53.9872 | 2159.4877
pipefitter/welder |  |  |  | 1 | 20 | 71.3693 | 1427.3854
helper |  |  |  | 1 | 20 | 49.9585 | 999.1698
laborer |  |  |  | 4 | 20 | 49.3919 | 3951.3545
foreman |  |  |  | 1 | 20 | 68.6578 | 1373.1556
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 12878.2063
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 257.5641
[6 empty] | Subtotal: | 257.5641
|  |  |  | Total Direct Costs (1) = |  |  | 16534.1969
2. Excavate, remove valves, blowdowns, and yard piping (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 2 | 50 | 44.9682 | 4496.816
hydrocrane, Grove 30 ton |  |  |  | 2 | 50 | 60.8178 | 6081.776
flatbed truck |  |  |  | 2 | 50 | 22.5552 | 2255.52
3/4 ton pick-up with trailer |  |  |  | 2 | 50 | 21.0312 | 2103.12
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 1003.0821
[6 empty] | Subtotal: | 16851.6661
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 50 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 3. Small compressor stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 2 | 50 | 58.3827 | 5838.2661
operator (hydrocrane) |  |  |  | 2 | 50 | 67.2307 | 6723.0681
teamster |  |  |  | 2 | 50 | 53.9872 | 5398.7193
pipefitter/welder |  |  |  | 2 | 50 | 71.3693 | 7136.9271
helper |  |  |  | 2 | 50 | 49.9585 | 4995.849
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 15 |  | 90 | 6750
[6 empty] | Subtotal: | 50154.1048
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1003.0821
[6 empty] | Subtotal: | 1003.0821
|  |  |  | Total Direct Costs (2) = |  |  | 68008.853
3. Remove station equipment (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 2 | 50 | 60.8178 | 6081.776
flatbed truck |  |  |  | 2 | 50 | 22.5552 | 2255.52
3/4 ton pick-up with trailer |  |  |  | 4 | 50 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 4 | 50 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 1380.54
[6 empty] | Subtotal: | 15746.78
Labor |  |  |  | No. | Hours | Rate | Total
operator (crane) |  |  |  | 2 | 50 | 67.2307 | 6723.0681
teamster |  |  |  | 2 | 50 | 53.9872 | 5398.7193
pipefitter/welder |  |  |  | 4 | 50 | 71.3693 | 14273.8542
helper |  |  |  | 4 | 50 | 49.9585 | 9991.6979
laborer |  |  |  | 8 | 50 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 21 |  | 90 | 9450
[6 empty] | Subtotal: | 69027.001
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1380.54
[6 empty] | Subtotal: | 1380.54
|  |  |  | Total Direct Costs (3) = |  |  | 86154.321
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 51 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 3. Small compressor stations (continued)
4. Remove station buildings (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320CL w grapple |  |  |  | 1 | 50 | 60.7873 | 3039.364
backhoe, Cat 320CL w shears |  |  |  | 1 | 50 | 79.7763 | 3988.816
hydrocrane, 30 ton |  |  |  | 1 | 50 | 60.8178 | 3040.888
flatbed truck |  |  |  | 2 | 50 | 22.5552 | 2255.52
lowboy |  |  |  | 1 | 50 | 50.2615 | 2513.076
3/4 ton pick-up with trailer |  |  |  | 4 | 50 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 4 | 50 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 1502.0619
[6 empty] | Subtotal: | 22368.6699
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 2 | 50 | 58.3827 | 5838.2661
operator (hydrocrane) |  |  |  | 1 | 50 | 67.2307 | 3361.5341
teamster |  |  |  | 3 | 50 | 53.9872 | 8098.079
pipefitter/welder |  |  |  | 4 | 50 | 71.3693 | 14273.8542
helper |  |  |  | 4 | 50 | 49.9585 | 9991.6979
laborer |  |  |  | 8 | 50 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 23 |  | 90 | 10350
[6 empty] | Subtotal: | 75103.0927
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1502.0619
[6 empty] | Subtotal: | 1502.0619
|  |  |  | Total Direct Costs (4) = |  |  | 98973.8244
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C w hammer |  |  |  | 4 | 100 | 67.0052 | 26802.08
backhoe, Cat 320C |  |  |  | 1 | 100 | 44.9682 | 4496.816
dump truck 14 cy |  |  |  | 2 | 100 | 23.3985 | 4679.696
3/4 ton pick-up with trailer |  |  |  | 4 | 100 | 21.0312 | 8412.48
1/2 ton pickup with 4wd |  |  |  | 2 | 100 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 2662.8485
[6 empty] | Subtotal: | 48876.6245
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 52 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 3. Small compressor stations (continued)
Line Item 5 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 5 | 100 | 58.3827 | 29191.3305
teamster |  |  |  | 2 | 100 | 53.9872 | 10797.4386
pipefitter/welder |  |  |  | 4 | 100 | 71.3693 | 28547.7084
helper |  |  |  | 4 | 100 | 49.9585 | 19983.3959
laborer |  |  |  | 4 | 100 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 20 |  | 90 | 18000
[6 empty] | Subtotal: | 133142.4239
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 2662.8485
[6 empty] | Subtotal: | 2662.8485
|  |  |  | Total Direct Costs (5) = |  |  | 184681.8968
6. Restore site (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 50 | 51.6128 | 2580.64
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 441.5954
[6 empty] | Subtotal: | 5061.3474
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 50 | 58.3827 | 2919.133
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 7 |  | 90 | 3150
[6 empty] | Subtotal: | 22079.768
Material | [6 empty] | Total
allow $ 10000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 10000
Sales tax @ | 7% | [5 empty] | 700
[6 empty] | Subtotal: | 10700
|  |  |  | Total Direct Costs (6) = |  |  | 37841.1153
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 53 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 3. Small compressor stations (continued)
Summary: Small Compressor Stations
A. Pipeline contractor costs
1. Remove fence and miscellaneous material and access work site | [6 empty] | 16534.1969
2. Excavate, remove valves, blowdowns, and yard piping | [6 empty] | 68008.853
3. Remove station equipment | [6 empty] | 86154.321
4. Remove station buildings | [6 empty] | 98973.8244
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface | [6 empty] | 184681.8968
6. Restore site | [6 empty] | 37841.1153
|  |  |  | Pipeline contractor direct costs: |  |  | 492194.2075
|  |  |  | 5% Mobilization |  |  | 24609.7104
[6 empty] | Subtotal: | 516803.9179
|  |  |  | 15% Contractor overhead: |  |  | 77520.5877
[6 empty] | Subtotal: | 594324.5055
|  |  |  | 10% Contractor profit: |  |  | 59432.4506
|  |  |  | Total pipeline contractor costs: |  |  | 653756.9561
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 32687.8478
|  |  |  | Total environmental contractor costs: |  |  | 32687.8478
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 32
2. Company cost per day | [6 empty] | 1000
|  | Total company inspection cost per site: |  |  |  |  | 32000
D. Pipeline company management and overhead costs (15% of A + B + C)
107766.7206
|  |  |  | Total management and overhead cost: |  |  | 107766.7206
| Total cost to retire a typical small compressor station (A + B + C + D): | [5 empty] | 826211.5245
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 54 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 3. Small compressor stations (continued)
Transmission Compressor Stations (Small)
Estimated
| Name of | Location by | Station | No. of | Station | Retirement
| Station | State | No. | Units | HP | Cost
1 | Americus | Kansas | 532 | 4 | 8000 | 826211.5245
2 | Humbolt | Kansas | 591 | 1 | 9300 | 826211.5245
3 | Montezuma | Kansas | 538 | 3 | 6000 | 826211.5245
4 | Ottawa | Kansas | 555 | 2 | 8500 | 826211.5245
5 | Stafford | Kansas | 557 | 3 | 6000 | 826211.5245
6 | Tonganoxie | Kansas | 542 | 7 | 8160 | 826211.5245
7 | United | Kansas | 529 | 4 | 7440 | 826211.5245
8 | Peculiar | Missouri | 539 | 3 | 5535 | 826211.5245
9 | Saginaw | Missouri | 507 | 3 | 7600 | 826211.5245
10 | Alva | Oklahoma | 556 | 4 | 6900 | 826211.5245
11 | Blackwell | Oklahoma | 511 | 4 | 8400 | 826211.5245
[5 empty] | Total: | 9088326.7694

## Very Small Comp
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 55 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
K. Compressor stations
4. Very small
Description of Work:
Detailed cost estimate below reflects work required to retire a typical very small compressor station. Work
includes removal of fence and misc. material, valves, blowdowns, piping, compressor station equipment,
and buildings; excavation of concrete foundations and gravel; and site restoration. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove fence and miscellaneous material and access work site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 10 | 44.9682 | 449.6816
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
lowboy |  |  |  | 1 | 10 | 50.2615 | 502.6152
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 9.1135 | 182.2704
small tools, 2% of labor | [6 empty] | 128.7821
[6 empty] | Subtotal: | 1699.2133
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 2 | 10 | 53.9872 | 1079.7439
pipefitter/welder |  |  |  | 1 | 10 | 71.3693 | 713.6927
helper |  |  |  | 1 | 10 | 49.9585 | 499.5849
laborer |  |  |  | 4 | 10 | 49.3919 | 1975.6772
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 10 |  | 90 | 900
[6 empty] | Subtotal: | 6439.1031
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 128.7821
[6 empty] | Subtotal: | 128.7821
|  |  |  | Total Direct Costs (1) = |  |  | 8267.0985
2. Excavate, remove valves, blowdowns, and yard piping (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C |  |  |  | 1 | 50 | 44.9682 | 2248.408
hydrocrane, Grove 30 ton |  |  |  | 1 | 50 | 60.8178 | 3040.888
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
3/4 ton pick-up with trailer |  |  |  | 1 | 50 | 21.0312 | 1051.56
1/2 ton pickup with 4wd |  |  |  | 1 | 50 | 9.1135 | 455.676
small tools, 2% of labor | [6 empty] | 540.3699
[6 empty] | Subtotal: | 8464.6619
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 56 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 4. Very small compressor stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 1 | 50 | 58.3827 | 2919.133
operator (hydrocrane) |  |  |  | 1 | 50 | 67.2307 | 3361.5341
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
pipefitter/welder |  |  |  | 1 | 50 | 71.3693 | 3568.4635
helper |  |  |  | 1 | 50 | 49.9585 | 2497.9245
laborer |  |  |  | 2 | 50 | 49.3919 | 4939.1931
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 8 |  | 90 | 3600
[6 empty] | Subtotal: | 27018.4969
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 540.3699
[6 empty] | Subtotal: | 540.3699
|  |  |  | Total Direct Costs (2) = |  |  | 36023.5288
3. Remove station equipment (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 1 | 50 | 60.8178 | 3040.888
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
3/4 ton pick-up with trailer |  |  |  | 2 | 50 | 21.0312 | 2103.12
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 729.0989
[6 empty] | Subtotal: | 7912.2189
Labor |  |  |  | No. | Hours | Rate | Total
operator (crane) |  |  |  | 1 | 50 | 67.2307 | 3361.5341
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
pipefitter/welder |  |  |  | 2 | 50 | 71.3693 | 7136.9271
helper |  |  |  | 2 | 50 | 49.9585 | 4995.849
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 11 |  | 90 | 4950
[6 empty] | Subtotal: | 36454.945
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 729.0989
[6 empty] | Subtotal: | 729.0989
|  |  |  | Total Direct Costs (3) = |  |  | 45096.2628
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 57 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 4. Very small compressor stations (continued)
4. Remove station buildings (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320CL w grapple |  |  |  | 1 | 50 | 60.7873 | 3039.364
backhoe, Cat 320CL w shears |  |  |  | 1 | 50 | 79.7763 | 3988.816
hydrocrane, 30 ton |  |  |  | 1 | 50 | 60.8178 | 3040.888
flatbed truck |  |  |  | 2 | 50 | 22.5552 | 2255.52
lowboy |  |  |  | 1 | 50 | 50.2615 | 2513.076
3/4 ton pick-up with trailer |  |  |  | 4 | 50 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 4 | 50 | 9.1135 | 1822.704
small tools, 2% of labor | [6 empty] | 1502.0619
[6 empty] | Subtotal: | 22368.6699
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 2 | 50 | 58.3827 | 5838.2661
operator (hydrocrane) |  |  |  | 1 | 50 | 67.2307 | 3361.5341
teamster |  |  |  | 3 | 50 | 53.9872 | 8098.079
pipefitter/welder |  |  |  | 4 | 50 | 71.3693 | 14273.8542
helper |  |  |  | 4 | 50 | 49.9585 | 9991.6979
laborer |  |  |  | 8 | 50 | 49.3919 | 19756.7724
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 23 |  | 90 | 10350
[6 empty] | Subtotal: | 75103.0927
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1502.0619
[6 empty] | Subtotal: | 1502.0619
|  |  |  | Total Direct Costs (4) = |  |  | 98973.8244
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320C w hammer |  |  |  | 2 | 100 | 67.0052 | 13401.04
backhoe, Cat 320C |  |  |  | 1 | 100 | 44.9682 | 4496.816
dump truck 14 cy |  |  |  | 1 | 100 | 23.3985 | 2339.848
3/4 ton pick-up with trailer |  |  |  | 2 | 100 | 21.0312 | 4206.24
1/2 ton pickup with 4wd |  |  |  | 1 | 100 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 1476.4647
[6 empty] | Subtotal: | 26831.7607
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 58 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 4. Very small compressor stations (continued)
Line Item 5 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 3 | 100 | 58.3827 | 17514.7983
teamster |  |  |  | 1 | 100 | 53.9872 | 5398.7193
pipefitter/welder |  |  |  | 2 | 100 | 71.3693 | 14273.8542
helper |  |  |  | 2 | 100 | 49.9585 | 9991.6979
laborer |  |  |  | 2 | 100 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 100 | 68.6578 | 6865.7781
per diem | 10 | days | crew size: | 11 |  | 90 | 9900
[6 empty] | Subtotal: | 73823.234
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 1476.4647
[6 empty] | Subtotal: | 1476.4647
|  |  |  | Total Direct Costs (5) = |  |  | 102131.4594
6. Restore site (5 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953C |  |  |  | 1 | 50 | 51.6128 | 2580.64
flatbed truck |  |  |  | 1 | 50 | 22.5552 | 1127.76
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 9.1135 | 911.352
small tools, 2% of labor | [6 empty] | 441.5954
[6 empty] | Subtotal: | 5061.3474
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 50 | 58.3827 | 2919.133
teamster |  |  |  | 1 | 50 | 53.9872 | 2699.3596
laborer |  |  |  | 4 | 50 | 49.3919 | 9878.3862
foreman |  |  |  | 1 | 50 | 68.6578 | 3432.8891
per diem | 5 | days | crew size: | 7 |  | 90 | 3150
[6 empty] | Subtotal: | 22079.768
Material | [6 empty] | Total
allow $ 5000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 5000
Sales tax @ | 7% | [5 empty] | 350
[6 empty] | Subtotal: | 5350
|  |  |  | Total Direct Costs (6) = |  |  | 32491.1153
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 59 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 4. Very small compressor stations (continued)
Summary: Very Small Compressor Stations
A. Pipeline contractor costs
1. Remove fence and miscellaneous material and access work site | [6 empty] | 8267.0985
2. Excavate, remove valves, blowdowns, and yard piping | [6 empty] | 36023.5288
3. Remove station equipment | [6 empty] | 45096.2628
4. Remove station buildings | [6 empty] | 98973.8244
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface | [6 empty] | 102131.4594
6. Restore site | [6 empty] | 32491.1153
|  |  |  | Pipeline contractor direct costs: |  |  | 322983.2892
|  |  |  | 5% Mobilization |  |  | 16149.1645
[6 empty] | Subtotal: | 339132.4537
|  |  |  | 15% Contractor overhead: |  |  | 50869.868
[6 empty] | Subtotal: | 390002.3217
|  |  |  | 10% Contractor profit: |  |  | 39000.2322
|  |  |  | Total pipeline contractor costs: |  |  | 429002.5539
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 21450.1277
|  |  |  | Total environmental contractor costs: |  |  | 21450.1277
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 31
2. Company cost per day | [6 empty] | 1000
|  | Total company inspection cost per site: |  |  |  |  | 31000
D. Pipeline company management and overhead costs (15% of A + B + C)
72217.9022
|  |  |  | Total management and overhead cost: |  |  | 72217.9022
| Total cost to retire a typical very small compressor station (A + B + C + D): | [5 empty] | 553670.5838
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 60 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. K. 4. Very small compressor stations (continued)
Transmission Compressor Stations (Very Small)
Estimated
| Name of | Location by | Station | No. of | Station | Retirement
| Station | State | No. | Units | HP | Cost
1 | Cheyenne | Colorado | 573 | 1 | 2400 | 553670.5838
2 | Merino | Colorado | 574 | 1 | 3950 | 553670.5838
3 | Yuma | Colorado | 575 | 1 | 2400 | 553670.5838
4 | Atchison | Kansas | 501 | 5 | 1340 | 553670.5838
5 | Hoxie | Kansas | 578 | 1 | 2400 | 553670.5838
6 | Levant | Kansas | 577 | 1 | 2400 | 553670.5838
7 | Ogallah | Kansas | 579 | 1 | 2400 | 553670.5838
8 | Otis | Kansas | 583 | 1 | 2400 | 553670.5838
9 | St . Francis | Kansas | 576 | 1 | 2400 | 553670.5838
10 | Columbia | Missouri | 552 | 1 | 1354 | 553670.5838
11 | Concordia | Missouri | 551 | 2 | 1800 | 553670.5838
12 | Lone Jack | Missouri | 553 | 1 | 1354 | 553670.5838
13 | Cotton Valley | Oklahoma | 523 | 2 | 4000 | 553670.5838
14 | Drumright | Oklahoma | 514 | 3 | 2475 | 553670.5838
15 | Edmond | Oklahoma | 535 | 3 | 3550 | 553670.5838
16 | Mutual | Oklahoma | 548 | 1 | 1100 | 553670.5838
17 | Wakita | Oklahoma | 543 | 2 | 4000 | 553670.5838
18 | Arlington | Wyoming | 572 | 1 | 3950 | 553670.5838
19 | Riner | Wyoming | 569 | 2 | 4800 | 553670.5838
[5 empty] | Total: | 10519741.0922

## Communication Towers
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 61 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. Pipeline Retirement
L. Communication towers
Description of Work:
Detailed cost estimate below reflects work required to retire a typical communication tower. Work includes
removal of fence and miscellaneous material, rigging tower for demolition, demolition of tower, excavation of
concrete footings and gravel, and site restoration. Estimate also includes environmental inspection, pipeline
company inspection, and pipeline company management and overhead.
1. Remove fence and miscellaneous material and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
bobcat |  |  |  | 1 | 5 | 12.1209 | 60.6044
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
lowboy |  |  |  | 1 | 5 | 50.2615 | 251.3076
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 21.0312 | 105.156
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 46.4139
[6 empty] | Subtotal: | 621.8255
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
pipefitter/welder |  |  |  | 1 | 5 | 71.3693 | 356.8464
helper |  |  |  | 1 | 5 | 49.9585 | 249.7924
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 7 |  | 90 | 315
[6 empty] | Subtotal: | 2320.6963
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 46.4139
[6 empty] | Subtotal: | 46.4139
|  |  |  | Total Direct Costs (1) = |  |  | 2988.9357
2. Rig tower for demolition (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 1 | 10 | 60.8178 | 608.1776
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 66.7319
[6 empty] | Subtotal: | 1201.9087
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 62 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. L. Communication towers (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (hydrocrane) |  |  |  | 1 | 10 | 67.2307 | 672.3068
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
laborer |  |  |  | 2 | 10 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 5 |  | 90 | 450
[6 empty] | Subtotal: | 3336.5952
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 66.7319
[6 empty] | Subtotal: | 66.7319
|  |  |  | Total Direct Costs (2) = |  |  | 4605.2358
3. Demolish tower (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  |  | 1 | 10 | 60.8178 | 608.1776
flatbed truck |  |  |  | 1 | 10 | 22.5552 | 225.552
3/4 ton pick-up with trailer |  |  |  | 2 | 10 | 21.0312 | 420.624
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 122.463
[6 empty] | Subtotal: | 1467.9518
Labor |  |  |  | No. | Hours | Rate | Total
operator (crane) |  |  |  | 1 | 10 | 67.2307 | 672.3068
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 2 | 10 | 71.3693 | 1427.3854
helper |  |  |  | 2 | 10 | 49.9585 | 999.1698
laborer |  |  |  | 2 | 10 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 9 |  | 90 | 810
[6 empty] | Subtotal: | 6123.1504
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 122.463
[6 empty] | Subtotal: | 122.463
|  |  |  | Total Direct Costs (3) = |  |  | 7713.5652
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 63 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. L. Communication towers (continued)
4. Demolish concrete footings to 3-ft below ground surface (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C w hammer |  |  |  | 1 | 10 | 43.6067 | 436.0672
dump truck 8 cy |  |  |  | 1 | 10 | 22.2809 | 222.8088
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 21.0312 | 210.312
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 9.1135 | 91.1352
small tools, 2% of labor | [6 empty] | 92.8279
[6 empty] | Subtotal: | 1053.1511
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 58.3827 | 583.8266
teamster |  |  |  | 1 | 10 | 53.9872 | 539.8719
pipefitter/welder |  |  |  | 1 | 10 | 71.3693 | 713.6927
helper |  |  |  | 1 | 10 | 49.9585 | 499.5849
laborer |  |  |  | 2 | 10 | 49.3919 | 987.8386
foreman |  |  |  | 1 | 10 | 68.6578 | 686.5778
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 4641.3926
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 92.8279
[6 empty] | Subtotal: | 92.8279
|  |  |  | Total Direct Costs (4) = |  |  | 5787.3715
5. Restore site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
bobcat |  |  |  | 1 | 5 | 12.1209 | 60.6044
flatbed truck |  |  |  | 1 | 5 | 22.5552 | 112.776
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 9.1135 | 45.5676
small tools, 2% of labor | [6 empty] | 32.4811
[6 empty] | Subtotal: | 251.4291
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 58.3827 | 291.9133
teamster |  |  |  | 1 | 5 | 53.9872 | 269.936
laborer |  |  |  | 2 | 5 | 49.3919 | 493.9193
foreman |  |  |  | 1 | 5 | 68.6578 | 343.2889
per diem | 0.5 | day | crew size: | 5 |  | 90 | 225
[6 empty] | Subtotal: | 1624.0575
Material | [6 empty] | Total
allow $ 500 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 500
Sales tax @ | 7% | [5 empty] | 35
[6 empty] | Subtotal: | 535
|  |  |  | Total Direct Costs (5) = |  |  | 2410.4866
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 64 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
I. L. Communication towers (continued)
Summary: Communication Towers
A. Pipeline contractor costs
1. Remove fence and miscellaneous material and access work site | [6 empty] | 2988.9357
2. Rig tower for demolition | [6 empty] | 4605.2358
3. Demolish tower | [6 empty] | 7713.5652
4. Demolish concrete footings to 3-ft below ground surface | [6 empty] | 5787.3715
5. Restore site | [6 empty] | 2410.4866
|  |  |  | Pipeline contractor direct costs: |  |  | 23505.5948
|  |  |  | 5% Mobilization |  |  | 1175.2797
[6 empty] | Subtotal: | 24680.8746
|  |  |  | 15% Contractor overhead: |  |  | 3702.1312
[6 empty] | Subtotal: | 28383.0058
|  |  |  | 10% Contractor profit: |  |  | 2838.3006
|  |  |  | Total pipeline contractor costs: |  |  | 31221.3063
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 1561.0653
|  |  |  | Total environmental contractor costs: |  |  | 1561.0653
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 4
2. Company cost per day | [6 empty] | 1000
|  | Total company inspection cost per site: |  |  |  |  | 4000
D. Pipeline company management and overhead costs (15% of A + B + C)
5517.3557
|  |  |  | Total management and overhead cost: |  |  | 5517.3557
|  | Total cost to retire a communications tower (A + B + C + D): |  |  |  |  | 42299.7274
|  | No. of communication towers: |  |  |  |  | 61
|  | Total estimated cost to retire communication towers: |  |  |  |  | 2580283.3713

## Salvage Equip
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 65 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
II. Salvage
A. Equipment
Compressor stations
Estimated
|  |  |  | Salvage | Estimated
|  |  | No. of | Per Station | Salvage
No. | Location |  | Stations | (2008$) | (2008$)
1 | Large compressor station |  | 1 | -504811.3123 | -504811.3123
2 | Medium compressor station |  | 2 | -258462.9631 | -516925.9262
3 | Small compressor station |  | 11 | -86154.321 | -947697.5313
4 | Very small compressor station |  | 19 | -45096.2628 | -856828.9936
|  | Total: | 33 |  | -2826263.7634

## Salvage Scrap
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 66 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
II. Salvage
B. Scrap steel
|  |  | Estimated carbon steel scap value: |  |  | 180 | per ton
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Valve | Weight | Value | Salvage
| 1 | Mainline valves |  |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  | a. |  | Avg. valve 16" dia. |  | 487 | 1 | 487 | 180 | -87660
[9 empty] | Subtotal: | -87660
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Station | Weight | Value | Salvage
| 2 | M&R stations |  |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  | a. |  | Small M&R station |  | 296 | 10 | 2960 | 180 | -532800
|  | b. |  | Medium M&R station |  | 40 | 20 | 800 | 180 | -144000
[9 empty] | Subtotal: | -676800
[7 empty] | Weight/ | Total | Scrap | Estimated
| 3 | Compressor stations |  |  |  |  | Bldg | Weight | Value | Salvage
|  | a. | Large |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  |  | 1 | Compressor bldgs |  | 2 | 250 | 500 | 180 | -90000
|  |  | 2 | Control/office bldg |  | 2 | 100 | 200 | 180 | -36000
|  |  | 3 | Storage bldg |  | 1 | 50 | 50 | 180 | -9000
|  |  | 4 | Unit local control bldg |  | 1 | 10 | 10 | 180 | -1800
|  |  | 5 | Minor bldgs |  | 4 | 5 | 20 | 180 | -3600
|  |  | 6 | Piping, valves |  | L.S. | 200 | 200 | 180 | -36000
[9 empty] | Estimated salvage: | -176400
[9 empty] | No. of large stations: | 1
[9 empty] | Total estimated salvage: | -176400
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Bldg | Weight | Value | Salvage
|  | b. | Medium |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  |  | 1 | Compressor bldg |  | 1 | 250 | 250 | 180 | -45000
|  |  | 2 | Control/office bldg |  | 1 | 100 | 100 | 180 | -18000
|  |  | 3 | Storage bldg |  | 1 | 50 | 50 | 180 | -9000
|  |  | 4 | Unit local control bldg |  | 1 | 10 | 10 | 180 | -1800
|  |  | 5 | Minor bldgs |  | 3 | 5 | 15 | 180 | -2700
|  |  | 6 | Piping, valves |  | L.S. | 150 | 150 | 180 | -27000
[9 empty] | Estimated salvage: | -103500
[9 empty] | No. of medium stations: | 2
[9 empty] | Total estimated salvage: | -207000
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 67 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
II. B. Scrap steel (continued)
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Bldg | Weight | Value | Salvage
|  | c. | Small |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  |  | 1 | Compressor bldgs |  | 1 | 150 | 150 | 180 | -27000
|  |  | 2 | Control/office bldg |  | 1 | 75 | 75 | 180 | -13500
|  |  | 3 | Storage bldg |  | 1 | 35 | 35 | 180 | -6300
|  |  | 4 | Unit local control bldg |  | 1 | 10 | 10 | 180 | -1800
|  |  | 5 | Minor bldgs |  | 2 | 5 | 10 | 180 | -1800
|  |  | 6 | Piping, valves, meter runs |  | L.S. | 100 | 100 | 180 | -18000
[9 empty] | Estimated salvage: | -68400
[9 empty] | No. of small stations: | 11
[9 empty] | Total estimated salvage: | -752400
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Bldg | Weight | Value | Salvage
|  | d. | Very small |  |  | No. | (ton) | (ton) | (ton) | (2008$)
|  |  | 1 | Compressor bldg |  | 1 | 50 | 50 | 180 | -9000
|  |  | 2 | Control/office bldg |  | 1 | 25 | 25 | 180 | -4500
|  |  | 3 | Storage bldg |  | 1 | 25 | 25 | 180 | -4500
|  |  | 4 | Unit local control bldg |  | 1 | 10 | 10 | 180 | -1800
|  |  | 5 | Minor bldgs |  | 2 | 5 | 10 | 180 | -1800
|  |  | 6 | Piping, valves |  | L.S. | 50 | 50 | 180 | -9000
[9 empty] | Estimated salvage: | -30600
[9 empty] | No. of very small stations: | 19
[9 empty] | Total estimated salvage: | -581400
[9 empty] | Subtotal compressor stations: | -1717200
[7 empty] | Weight/ | Total | Scrap | Estimated
[7 empty] | Tower | Weight | Value | Salvage
| 4 | Communication towers |  |  |  | No. | (ton) | (ton) | (ton) | (2008$)
[6 empty] | 61 | 20 | 1220 | 180 | -219600
[9 empty] | Subtotal: | -219600
[6 empty] | Length | Wt/ft
[6 empty] | of Pipe | 16-inch | Total | Total | Estimated
[6 empty] | Removed | Pipe | Weight | Weight | Salvage
| 4 | Pipe (misc. removal) |  |  | No. | (ft) | (lbs) | (lbs) | (ton) | (2008$)
|  | a. |  | Uncased crossings | 3690 | 40 | 62.58 | 9236808 | 4618.404 | -831312.72
|  | b. |  | Cased crossings | 1010 | 240 | 62.58 | 15169392 | 7584.696 | -1365245.28
|  | c. |  | Small stream crossings | 1678 | 40 | 62.58 | 4200369.6 | 2100.1848 | -378033.264
|  | d. |  | River crossings | 170 | 40 | 62.58 | 425544 | 212.772 | -38298.96
|  | e. |  | Pipeline drips | 178 | 40 | 62.58 | 445569.6 | 222.7848 | -40101.264
[9 empty] | Subtotal: | -2612890.224
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 68 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
II. B. Scrap steel (continued)
Summary Scrap Steel Salvage
Salvage
Salvage Item | [9 empty] | Amount
1 |  | Valves | [7 empty] | -87660
2 |  | M&R stations | [7 empty] | -676800
3 |  | Compressor stations | [7 empty] | -1717200
4 |  | Communication towers | [7 empty] | -219600
5 |  | Pipe (misc. removal) | [7 empty] | -2612890.224
[9 empty] | Total: | -5314150.224

## Pipeline Labor Rates
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 69 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
Pipeline Contractor Labor Rates and Company Inspection Costs
A | Pipeline contractor labor rates
|  | (Note 1) | (Note 2) |  | (Note 3) |  | (Note 4)
|  | Sept 2007 |  | Jan 2008 |  | Jan 2008 | Labor | Jan 2008
|  | Labor Rate |  | Labor Rate |  | Labor Rate | Overhead | Labor Rate
|  | Including |  | Including |  | Adjusted | 25% of | Pipeline
|  | Fringe | Escalation | Fringe | Overtime | for | Sept 2007 | Demolition
|  | Benefits | Factor | Benefits | Factor | Overtime | Base Rate | Estimate
| Trade | ($/hr) |  | ($/hr) |  | ($/hr) | (%) | ($/hr)
1 | Operating engineers:
2 | Crane operator | 47.11 | 1.005 | 47.3456 | 1.17 | 55.3943 | 11.8364 | 67.2307
3 | Heavy equipment | 40.91 | 1.005 | 41.1146 | 1.17 | 48.104 | 10.2786 | 58.3827
4 | Small equipment | 39.87 | 1.005 | 40.0694 | 1.17 | 46.8811 | 10.0173 | 56.8985
5 | Electrician | 46.39 | 1.005 | 46.6219 | 1.17 | 54.5477 | 11.6555 | 66.2032
6 | Electrician helper | 32.473 | 1.005 | 32.6354 | 1.17 | 38.1834 | 8.1588 | 46.3422
7 | Ironworker (structural) | 44.63 | 1.005 | 44.8531 | 1.17 | 52.4782 | 11.2133 | 63.6915
8 | Laborer | 34.61 | 1.005 | 34.7831 | 1.17 | 40.6962 | 8.6958 | 49.3919
9 | Pipefitter/welder | 50.01 | 1.005 | 50.26 | 1.17 | 58.8043 | 12.565 | 71.3693
10 | Pipefitter/welder helper | 35.007 | 1.005 | 35.182 | 1.17 | 41.163 | 8.7955 | 49.9585
11 | Teamster | 37.83 | 1.005 | 38.0192 | 1.17 | 44.4824 | 9.5048 | 53.9872
12 | Foreman | 48.11 | 1.005 | 48.3505 | 1.17 | 56.5701 | 12.0876 | 68.6578
| Labor overhead factor: | 25%
| Per diem: | 90 | IRS Publication 1542, "Per Diem Rates"
B. | Pipeline company inspection costs
Estimated
Cost/day
1 | Pipeline | [6 empty] | 500
2 | Compressor stations and communication towers | [6 empty] | 1000
Note: Inspection costs include direct labor, per diem, and transportation costs.
Notes
1 | Hourly union pay scales, September 2007, Kansas City, Missouri (ENR September 17, 2007).
2 | Escalation factor based on ENR construction cost indices Sept 2007 of 8050 and Jan 2008 of 8090.
3 | Work 6-day week, 10-hr day. See workpapers for calculation of overtime factor.
4 | FICA, unemployment compensation, and workers compensation insurance that employers must pay.

## Pipeline Equipment Rates
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 70 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
Pipeline Contractor Equipment Rates
|  | (Note 1) | (Note 2)
|  | July 2007 |  | Jan 2008
|  | Equipment | Escalation | Equipment
|  | Rate | Factor | Rate
| Equipment Description | ($/hr) |  | ($/hr)
1 | air compressor 160G, 160 cfm | 12.31 | 1.016 | 12.507
2 | air hose, 1-inch, 100 ft | 1.09 | 1.016 | 1.1074
3 | paving breaker, 80-90 Lb | 0.73 | 1.016 | 0.74168
4 | crane, 25 ton, Grove, hydrocrane 152 hp | 52.54 | 1.016 | 53.3806
5 | crane, 30 ton, Grove, hydrocrane 152 hp | 59.86 | 1.016 | 60.8178
6 | crane, 50 ton, Grove, hydrocrane 400 hp | 108.08 | 1.016 | 109.8093
7 | fork lift | 18.81 | 1.016 | 19.111
8 | motor grader, Cat 135-H, 135 hp | 38.82 | 1.016 | 39.4411
9 | hydraulic excavator, Bobcat, 0.10 cy | 11.93 | 1.016 | 12.1209
10 | hydraulic excavator, Cat 312C, 0.68 cy | 35.47 | 1.016 | 36.0375
11 | hydraulic excavator, Cat 320C, 1.50 cy | 44.26 | 1.016 | 44.9682
12 | hydraulic excavator, Cat 320CL, 0.80 cy | 53.39 | 1.016 | 54.2442
13 | hydraulic hammer, 750 ft-lb | 7.45 | 1.016 | 7.5692
14 | hydraulic hammer, 3000 ft-lb | 21.69 | 1.016 | 22.037
15 | hydraulic grapple, Labounty 120 TR | 6.44 | 1.016 | 6.543
16 | hydraulic shears, 27", Labounty MSD 40-III SV | 25.13 | 1.016 | 25.5321
17 | lights, 6/1000W, 8 KW gen, trailer mtd. | 5.98 | 1.016 | 6.0757
18 | pipelayer, Cat 561M, 18 ft boom, 40,000 lbs capacity | 35.58 | 1.016 | 36.1493
19 | pipelayer, Cat 572R, 20 ft boom, 90,000 lbs capacity | 67.32 | 1.016 | 68.3971
20 | pump, grout, trailer mounted, 810 cf/hr | 11.22 | 1.016 | 11.3995
21 | pump, grout, trailer mounted, 2295 cf/hr | 26.03 | 1.016 | 26.4465
22 | pump, water, skid-mounted, 6" dia, 1165 gpm | 11.87 | 1.016 | 12.0599
23 | pump, hose, 6" dia, 100' length | 3.15 | 1.016 | 3.2004
24 | tractor, Cat D-6R, 165 hp | 79.36 | 1.016 | 80.6298
25 | winch for D-6R dozer | 7.41 | 1.016 | 7.5286
26 | track loader, Cat 953C, 2.25 cy | 50.8 | 1.016 | 51.6128
27 | dump truck, 8 cy | 21.93 | 1.016 | 22.2809
28 | dump truck, 14 cy | 23.03 | 1.016 | 23.3985
29 | flatbed truck | 22.2 | 1.016 | 22.5552
30 | pipe truck | 45.87 | 1.016 | 46.6039
31 | lowboy, 50 ton | 49.47 | 1.016 | 50.2615
32 | 1/2 ton pickup, crew, 4wd | 8.97 | 1.016 | 9.1135
33 | 3/4 ton pickup, crew, 4wd | 10.88 | 1.016 | 11.0541
34 | welder, trailer mounted, 45 hp | 9.82 | 1.016 | 9.9771
Notes
1 | Hourly Equipment Rates from July 2007, US Army Corps of Engineers
Construction Equipment Ownership and Operating Expense Schedule, Region V.
2 | Escalation factor based on ENR construction cost indices July 2007 of 7959 and 8090 of January 2008.
per ENR 3/24/08.

## Trans Workpapers - General
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 71 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
Workpapers - General
A. | Quantities
| 1 | Total SSC pipeline miles |  |  |  | Storage | Transmission | Total
|  | a. | Colorado |  |  |  | 171.4 | 171.4
|  | b. | Kansas |  |  | 170.8 | 3102 | 3272.8
|  | c. | Missouri |  |  |  | 872 | 872
|  | d. | Nebraska |  |  |  | 5.8 | 5.8
|  | e. | Oklahoma |  |  | 19.3 | 1266.2 | 1285.5
|  | f. | Texas |  |  |  | 37.1 | 37.1
|  | g. | Wyoming |  |  |  | 261.2 | 261.2
[6 empty] | 190.1 | 5715.7 | 5905.8
|  |  |  | Total transmission pipeline miles: |  | 96.78% |  | 5715.7
|  |  |  | Total storage pipeline miles: |  | 3.219% |  | 190.1
|  |  |  | Total SSC miles: |  | 100% |  | 5905.8
[7 empty] | Dia. > 12-inch | All diameters
| 2 | Transmission pipeline miles |  |  |  |  | (Miles) | (Miles)
|  | a. | Colorado |  |  |  | 171.3 | 171.4
|  | b. | Kansas |  |  |  | 1826 | 3102
|  | c. | Missouri |  |  |  | 343.7 | 872
|  | d. | Nebraska |  |  |  | 0 | 5.8
|  | e. | Oklahoma |  |  |  | 943.8 | 1266.2
|  | f. | Texas |  |  |  | 36.7 | 37.1
|  | g. | Wyoming |  |  |  | 177.1 | 261.2
[6 empty] | Total: | 3498.6 | 5715.7
|  |  |  | Percentage of transmission pipeline > 12-inch diameter: |  |  |  | 61.21%
| 3 | No. of transmission uncased railroad and highway/road crossings
|  | a. | Highways/roads |  |  |  |  | No.
|  |  | 1 | Per SSC all diameters |  |  |  | 4980
|  |  | 2 | Pipeline diameter > 12-inch |  |  |  | 3048
|  | b. | Railroads
|  |  | 1 | Per SSC all diameters |  |  |  | 642
| 4 | No. of transmission cased railroad and highway/road crossings
|  | a. | Highways/roads |  |  |  |  | No.
|  |  | 1 | Per SSC all diameters |  |  |  | 1084
|  |  | 2 | Pipeline diameter > 12-inch |  |  |  | 664
|  | b. | Railroads
|  |  | 1 | Per SSC all diameters |  |  |  | 346
No.
| 5 | No. of transmission small stream crossings per SSC | [5 empty] | 1678
|  |  |  | Average crossing length per SSC (ft): | 100 | ft
Docket No. RP08-___
Exhibit No. ____ (SSC-4.3)
Statement P
Page 72 of 72
Southern Star Central Gas Pipeline, Inc.
Transmission Final Abandonment Estimate
Workpapers - General (continued)
No.
| 6 | No. of transmission river crossings per SSC | [5 empty] | 170
|  |  |  | Average crossing length per SSC (ft): | 500 | ft
| 7 | No. of transmission mainline valve sites | [5 empty] | No.
|  | a. | Large per SSC |  |  |  |  | 54
|  | b. | Small per SSC |  |  |  |  | 26
|  | c. | Unknown per SSC |  |  |  |  | 407
[7 empty] | Total: | 487
No.
| 8 | No. of transmission pipeline drips per SSC | [5 empty] | 178
| 9 | No. of transmission cathodic protection facilities per SSC | [5 empty] | No.
|  | a. | Test sites |  |  |  |  | 8564
|  | b. | Rectifiers |  |  |  |  | 597
| 10 | No. of pipeline markers |  |  |  | Per SSC | Storage | Transmission
|  | a. | Class 1 |  |  | 26099 | 840 | 25259
|  | b. | Class 2 |  |  | 3166 | 102 | 3064
|  | c. | Class 3 |  |  | 6672 | 215 | 6457
[5 empty] | Total: | 35937 | 1157 | 34780
| 11 | No. of M&R stations
|  | a. | Meter stations |  |  |  |  | No.
|  |  | 1 | Small |  |  | Trans & Storage: | 296
[7 empty] | Storage: | 0
[7 empty] | Transmission: | 296
No.
|  |  | 2 | Medium |  |  | Trans & Storage: | 48
[7 empty] | Storage: | 8
[7 empty] | Transmission: | 40
No.
| 12 | No. of transmission communication towers | [5 empty] | 61
B. | Overtime factor for six 10-hour days worked per week |  |  |  |  | Hours | Overtime
[6 empty] | Worked | Factor | Pay units
|  |  |  | Straight-time 8 hours/day M-F |  | 40 | 1 | 40
|  |  |  | Overtime 2 hours/day M-F |  | 10 | 1.5 | 15
|  |  |  | Overtime Saturday |  | 10 | 1.5 | 15
|  |  |  | Total: |  | 60 |  | 70
|  |  |  | Overtime factor: |  | 1.17
C. | Miscellaneous
| 1 | Sales tax rate | [5 empty] | 7%
| 2 | Grout cost per cy | [5 empty] | 84
| 3 | Backfill material per cy | [5 empty] | 10