## Item 4 SITE SCHEDULE
Chandeleur Pipe Line Co.
System Abandonment
2789.01
| Daily | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | W | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
| Rate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
|  | 1, 2 | [16 empty] | ( 11 )
Labor Crew, 2 | 1046.64 | bar: M 1 to T 2; T 18 to F 19
Equipment, 2 | 485 | bar: M 1 to T 2; T 18 to F 19
|  | Install Compressor ( 1 ) | [9 empty] | Tanks for Flush ( 2 ) | [8 empty] | Rig Down ( 12, 13 )
Labor Crew, 10 | 3915.66 | bar: M 1 to M 15; S 20 to W 24
Equipment, 10 | 1680 | bar: M 1 to M 15; S 20 to W 24
Compressor | bar: M 1 to T 18
Pull Pressure Down ( 10 )
Operators, 4 | #REF! | bar: T 11 to W 17
Pascagoula Station ( 16, 17, 18, 19, 20, 21 )
Labor Crew, 20 | 7308 | bar: M 36 to S 49
Equipment, 20 | 2525 | bar: M 36 to S 49
Isolate Pipelines ( 1, 2, 3, 4, 5, 6, 7, 8 )
Utility Boat: | 1700 | bar: M 1 to T 9
Subsistence | 680 | bar: M 1 to T 9
4 Man Crew | #REF! | bar: M 1 to T 9
[21 empty] | Flush Pipelines ( 12, 13, 14, 15, 16 ) | [16 empty] | Cut P/L & Risers ( 17, 18, 19, 20, . . ..
Jackup : | 6500 | bar: S 20 to M 50
Subsistence | 680 | bar: S 20 to M 50
8 Man Crew | #REF! | bar: S 20 to M 36; F 47 to S 48
4 Dive Teams | #REF! | bar: T 37 to M 50
[9 empty] | TETCO ( 9 ) | [28 empty] | Disconnect SSTI ( 17, 18, 19, 20, 21, 22
Dive Boat, 8 Team | #REF! | bar: M 8 to W 10; T 37 to M 50
Pascagoula Channel ( 17 ) . . . .
Spud Barge | #REF! | bar: T 37 to M 50
Crew Boat: | 2250 | bar: S 21 to M 50
| Daily | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | W | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
| Rate | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 46 | 96 | 97 | 98 | 99 | 100 | days | Total
Labor Crew, 2 | 1046.64 | [51 empty] | 4 | 4186.56
Equipment, 2 | 485 | [51 empty] | 4 | 1940
Labor Crew, 10 | 3915.66 | [51 empty] | 20 | 78313.2
Equipment, 10 | 1680 | [51 empty] | 20 | 33600
Compressor | [52 empty] | 18 | 12812
Operators, 4 | 1612 | [51 empty] | 7 | 11284
|  | . . . 24, ) |  |  | Coden Station ( 25,26,27,28,29 )
Labor Crew, 20 | 7308 | [51 empty] | 24 | 175392 | bar: T 51 to T 60
Equipment, 20 | 2525 | [51 empty] | 24 | 60600 | bar: T 51 to T 60
Utility Boat: | 1700 | [51 empty] | 9 | 15300
Subsistence | 680 | [51 empty] | 9 | 6120
4 Man Crew | 2490 | [51 empty] | 9 | 22410
. . 21 )
Jackup : | 6500 | [51 empty] | 33 | 214500 | bar: T 51 to W 52
Subsistence | 680 | [51 empty] | 33 | 22440 | bar: T 51 to W 52
8 Man Crew | 4170 | [51 empty] | 19 | 79230
4 Dive Teams | 9313 | [51 empty] | 16 | 149008 | bar: T 51 to W 52
. . . 21, 22 Disconnect SSTI )
Dive Boat, 8 Team | 20110 | [51 empty] | 31 | 623410 | bar: T 51 to M 64
|  | . . ( 17 ) Pascagoula Channel | [5 empty] | Miss Gulf Outlet Channel ( 18 )
Spud Barge | 14963 | [51 empty] | 46 | 688298 | bar: T 51 to W 82
Crew Boat: | 2250 | [51 empty] | 62 | 139500 | bar: T 51 to W 82
Notes:
1 x's in bold show criteal path |  | T 51: also marked in yellow
2 Brackets in case a phase of similar tasks. Corresponding task numbers are noted. | [52 empty] | 2338347

## Item 5 Cost Summary
Cost Breakdown
WBSE | Description | Amount
100 | Engineering & Project Management | 59758.5 | 1.991%
720 | Contract Engineering & Drafting | 70905.45 | 2.362%
200 | Purchased Materials | 2400 | 0.07996%
300 | I&E Materials | 0 | 0%
600 | Permitting and Special Categories | 40000 | 1.333%
700 | Contracts | 2424648.89 | 80.78%
Cont. | Contingency | 255771.284 | 8.521%
G&A | G&A | 148069.6319 | 4.933%
| TOTAL | 3001553.7559

## Item 6 Class 3 Estimate
COST ESTIMATE SHEET
CAPITAL/EXPENSE PROJECT
| Project No. |  | Chandeleur Pipe Line Co.
| Title |  | System Abandonment
| Description |  | 2789.01 |  |  |  |  | 10 | % AVE. CONTINGENCY
WBS | DESCRIPTION |  |  | # | UNIT | COST | QTY | TOTAL | % | TOTAL W/
ELEMENT | [5 empty] | $/UNIT |  | $ | CONT. | CONTINGENCY
100 | Company Engineering and Project Mgmt
|  |  | Company Personnel | 1 |  | 59758.5 | 1 | 59758.5 | 10 | 65734.35
|  |  | Subtotal |  |  |  |  | 59758.5 |  | 65734.35
200 | Purchased Materials
|  |  | Materials | 1 | EA | 2400 | 1 | 2400 | 10 | 2640
|  |  | Tax |  |  | 0% |  | 0 |  | 0
|  |  | Subtotal |  |  |  |  | 2400 |  | 2640
300 | I&E Materials
|  |  |  | 1 | EA
|  |  | Tax |  |  | 0% |  | 0 |  | 0
|  |  | Subtotal |  |  |  |  | 0 |  | 0
600 | Land and Special Categories
|  |  | Environmental Specialist | 1 | As Req'd | 20000 | 1 | 20000 |  | 20000
|  |  | ROW | 1 | As Req'd | 20000 | 1 | 20000 |  | 20000
|  |  | Costs Spent to Date | 1 | EA
|  |  | Subtotal |  |  |  |  | 40000 |  | 40000
700 | Contracts
Contractor- Installation
Installation Work - Onshore
|  |  | Compressor, Rental | 1 | EA | 12812 | 1 | 12812 | 10 | 14093.2
|  |  | Compressor Operators | 1 | EA | 1612 | 7 | 11287 | 10 | 12415.7
|  |  | Labor Crew, 2 | 1 | EA | 1046.64 | 4 | 4186.56 | 10 | 4605.216
|  |  | Labor Crew, 10 | 1 | EA | 3915.66 | 20 | 78313.2 | 10 | 86144.52
|  |  | Labor Crew, 20 | 1 | EA | 7308 | 24 | 175392 | 10 | 192931.2
|  |  | Equipment, 2 | 1 | EA | 485 | 4 | 1940 | 10 | 2134
|  |  | Equipment, 10 | 1 | EA | 1680 | 20 | 33600 | 10 | 36960
|  |  | Equipment, 20 | 1 | EA | 2525 | 24 | 60600 | 10 | 66660
|  |  | Welding | 1 | MH | 78.65 | 0
Welder's Qualification Tests (Shop/Site)
|  |  | Hydrotest | 1 | EA | 0 | 1
|  |  | X-ray | 1 | EA | 0 | 1
|  |  | Blast & Paint | 1 | EA | 0 | 1
Labor, Tools & Truck
|  |  | Inspector | 1 | DA | 630 | 0
Installation Work - Offshore
|  |  | Labor Crew, 4 man w/Equipment | 1 | EA | 2490 | 9 | 22410 | 10 | 24651
|  |  | 4 Dive Teams | 1 | EA | 9313 | 16 | 149008 | 10 | 163908.8
|  |  | Dive Boat & 8 Dive Teams | 1 | EA | 20110 | 31 | 623410 | 10 | 685751
|  |  | Weather Downtime Crews | 1 | EA | 31913 | 3 | 95739 | 10 | 105312.9
|  |  | Jackup | 1 | EA | 6500 | 33 | 214500 | 10 | 235950
|  |  | Crewboat | 1 | EA | 2250 | 62 | 139500 | 10 | 153450
|  |  | Utility Boat | 1 | EA | 1700 | 9 | 15300 | 10 | 16830
|  |  | Spud Barge and Crew | 1 | EA | 14963 | 46 | 688298 | 10 | 757127.8
|  |  | Subsistence | 1 | EA | 680 | 42 | 28560 | 10 | 31416
|  |  | Weather Downtime Boats | 1 | EA | 25413 | 3 | 76239 | 10 | 83862.9
|  | Third Party Engineering & Drafting |  | 1083 | MH | 59.5194 | 1 | 64459.5 | 10 | 70905.45
|  |  | Subtotal |  |  |  |  | 2495554.26 |  | 2745109.686
G&A
|  | 5.7% |  | 5.7 | % | 2597712.76 | 1 | 148069.6273 |  | 148069.6273
|  |  | Subtotal |  |  |  |  | 148069.6273 |  | 148069.6273
|  |  | TOTAL |  |  |  |  | 2745782.3873 |  | 3001553.6633
|  |  | CLASS 3 ESTIMATE TOTAL | [6 empty] | 3001553.6633

## Item 6(a) Co. Personnel
Chandeleur Pipe Line Co.
System Abandonment
2789.01
COMPANY PERSONNEL
| Trips Offshore | 3
| Project duration in weeks | 9
|  | days |  | hr/dy |  | $/hr
| Office | 13.5 | x | 8 | x | 67 | = | 7236
| Onshore | 3 | x | 8 | x | 67 | = | 1608
| Offshore trips | 3 | x | 12 | x | 67 | = | 2412
|  | days |  | $/dy
| Subsistence | 3 | x | 25 | x | 1 | = | 75
|  | trips |  | mi/trip |  | $/mi
| mileage | 3 | x | 150 | x | 0.55 | = | 247.5 | 11578.5
|  | days |  | hr/dy |  | $/hr
| Safety Representative | 10 | x | 8 | x | 55 | = | 4400
| SCADA Representative | 0 | x |  | x | 55 | = | 0
| CSC Op. Rep. | 5 | x | 8 | x | 55 | = | 2200
| Construction Rep. | 63 | x | 12 | x | 55 | = | 41580 | 48180
[8 empty] | subtotal | 59758.5

## Item 6(b) Materials
Chandeleur Pipe Line Co.
System Abandonment
2789.01
MATERIAL
|  |  |  | Qty |  | $/Unit
| Ski Buoys |  |  | 6 | x | 25 | = |  | 150
| Plumbers Plugs |  |  | 15 |  | 150 |  |  | 2250
Pipe: | 10" S/80 |  |  |  | x | 23.7 | =
| 8" S/80 |  |  |  | x | 17.6 | =
| 6" S/80 |  |  |  | x | 11.6 | =
| 4" S/80 |  |  |  | x | 6.5 | =
| 3" S/80 |  |  |  | x | 4.45 | =
| 2" S/80 |  |  |  | x | 2.2 | =
Fittings: | Piggable Y | 10x10x10 |  |  | x | 26955.072 | =
|  | 10x10x8 |  |  | x | 26272 | =
|  | 10x10x6 |  |  | x | 25615 | =
|  | 10x10x4 |  |  | x | 24958 | =
|  | 6x6x6 |  |  | x | 18443 | =
| 5R 90 ells | 10" |  |  | x | 762 | =
|  | 8" |  |  | x | 355.6 | =
|  | 6" |  |  | x | 254 | =
|  | 4" |  |  | x | 165.38 | =
| 3R 90 ells | 6" |  |  | x | 254 | =
|  | 4" |  |  | x | 165.38 | =
| 3R 45 ells | 4" |  |  | x | 82.5 | =
| 45 ells | 10" |  |  | x | 76.5 | =
|  | 8" |  |  | x | 42.25 | =
| LR 90 ells | 10" |  |  | x | 171.25 | =
|  | 8" |  |  | x | 92.25 | =
|  | 6" |  |  | x | 55.5 | =
|  | 4" |  |  | x | 21 | =
|  | 3" |  |  | x | 15.75 | =
|  | 2" |  |  | x | 8.25 | =
| Red 90 | 8" x 6" |  |  | x | 237.5 | =
[5 empty] | x |  | =
[5 empty] | x |  | =
| Red Tees | 10" x 4" |  |  | x | 150 | =
|  | 10" x 6" |  |  | x | 191.25 | =
|  | 10" x 8" |  |  | x | 191.25 | =
|  | 8" x 6" |  |  | x | 113.25 | =
|  | 8" x 3" |  |  | x | 113.25 | =
|  | 6" x 3" |  |  | x | 59.25 | =
| Tees | 10" x 10" |  |  | x | 211 | =
|  | 8" x 8" |  |  | x | 134.51 | =
|  | 6" x 6" |  |  | x | 66 | =
|  | 4" x 4" |  |  | x | 42 | =
|  | 3" x 3" |  |  | x | 25.75 | =
|  | 2" x 2" |  |  | x | 15.75 | =
| Conc Red | 16" x 8" |  |  | x | 84 | =
|  | 12" x 10" |  |  | x | 64 | =
|  | 10" x 8" |  |  | x | 27.25 | =
|  | 8" x 6" |  |  | x | 27.25 | =
|  | 6" x 4" |  |  | x | 20.5 | =
|  | 4" x 2" |  |  | x | 10.5 | =
|  | 3" x 2" |  |  | x | 7.75 | =
| Welds Caps | 4" |  |  | x | 13.58 | =
|  | 3" |  |  | x | 8.28 | =
|  | 2" |  |  | x | 3.67 | =
| TOL | 1/2" |  |  | x | 1.91 | =
|  | 3/4" |  |  | x | 2.59 | =
| WOL | 10" x 4" |  |  | x | 22 | =
|  | 8" x 3" |  |  | x | 18.6 | =
|  | 8" x 2" |  |  | x | 25 | =
|  | 8" x 1" |  |  |  | 20 | =
Flanges: | 600# RTJ | 16" WNF |  |  | x | 909.75 | =
|  | Studs w/nuts | 20 - 1 1/2 x 10 1/2 |  | x | 220 | =
|  | R53 Gasket |  |  | x | 11 | =
|  | 10" WNF |  |  | x | 339.5 | =
|  | Studs w/nuts | 16 - 1 1/4 x 9 |  | x | 99.04 | =
|  | R53 Gasket |  |  | x | 9.93 | =
|  | 8" WNF |  |  | x | 240.75 | =
|  | Studs w/nuts |  |  | x | 43.35 | =
|  | R49 Gasket | 12 - 1 1/8 x 8 |  | x | 9.06 | =
|  | 6" WNF |  |  | x | 104.75 | =
|  | Studs w/nuts | 12 - 1 x 7 |  | x | 38.88 | =
|  | R45 Gasket |  |  | x | 6.85 | =
|  | 4" WNF |  |  | x | 53.25 | =
|  | Studs w/nuts | 8 - 7/8 x 6 |  | x | 13.36 | =
|  | R37 Gasket |  |  | x | 4.57 | =
|  | Insul Flg Kit |  |  | x | 11.28 | =
|  | 3" WNF |  |  | x | 29.75 | =
|  | Studs w/nuts | 8 - 3/4 x 5 1/2 |  | x | 11.92 | =
|  | R31 Gasket |  |  | x | 4.75 | =
|  | 2" WNF |  |  | x | 20.75 | =
|  | Studs w/nuts | 8 - 5/8 x 5 |  | x | 5.98 | =
|  | R23 Gasket |  |  | x | 3.88 | =
Blinds: |  | 16" Blind Flange |  |  | x | 912.5 | =
|  | 10" Blind Flange |  |  | x | 431.5 | =
|  | 3" Blind Flange |  |  | x | 27.25 | =
|  | 2" Blind Flange |  |  | x | 19 | =
Plugs | 1/2" |  |  |  | x | 2 | =
| 3/4" |  |  |  | x | 2 | =
| 1" |  |  |  | x | 3 | =
Valves: | Balls | 4" 1500# |  |  | x | 1708 | =
|  | 10" 600# |  |  | x | 8240 | =
|  | 8" 600# |  |  | x | 6925 | =
|  | 6" 600# |  |  | x | 5200 | =
|  | 4" 600# |  |  | x | 4304 | =
|  | 2" 600# |  |  | x | 540 | =
|  | 4" 150# |  |  | x | 1355.24 | =
|  | 3" 150# |  |  | x | 925 | =
|  | 2" 150# |  |  | x | 340 | =
|  | 1" 600# |  |  | x | 230 | =
| Checks | 10" 600# |  |  | x | 7000 | =
|  | 8" 600# |  |  | x | 5300 | =
|  | 6" 600# |  |  | x | 3560 | =
|  | 4" 600# |  |  | x | 2400 | =
|  | 3" 150# |  |  | x | 760 | =
| SDV | 8" 600# |  |  | x | 8425 | =
|  | 6" 600# |  |  | x | 6600 | =
|  | 4" 600# |  |  | x | 5504 | =
Speciality Items | Swivel Ring | 10" 600# |  |  | x | 1200 | =
|  | 8" 600# |  |  | x | 1000 | =
|  | 6" 600# |  |  | x | 800 | =
|  | 4" 600# |  |  | x | 600 | =
| Chokes | 3" 600# |  |  | x | 3250 | =
| Pig Trap Closures | 12" 600# |  |  | x | 4800 | =
|  | 10" 600# |  |  | x | 4200 | =
|  | 8" 600# |  |  | x | 3600 | =
|  | 6" 600# |  |  | x | 2200 | =
| Ball Launcher | 4" 1500# |  |  | x | 6999 | =
| Needle | 1" VN-2 |  |  | x | 69.35 | =
|  | 3/4" VN-2 |  |  | x | 67 | =
|  | 1/2" VN-2 |  |  | x | 72.9 | =
|  | 1/2" VN-6 |  |  | x | 40.54 | =
Insturments: | Thermowells | 3/4" |  |  | x | 59.44 | =
| Thermometer | 3/4" |  |  | x | 81.99 | =
| Pressure Gage | 1/2" |  |  | x | 81.99 | =
| Hi/Low Pilots | 1/2" |  |  | x | 540 | =
SS Tubing & Fittings
Grating | 3' x 10' sheets | 97 sheets |  |  | x | 4
Angle | 2 1/2 x 2 1/2 x 3/8 | 2850 ft x 5.9 lbs/ft |  |  | x | 0.26
SubMar Mats | 8' x 20' x 9" |  |  |  | x | 3000
Misc | Pipe Supports
[8 empty] | sub-total | 2400
[7 empty] | Taxes estimated at | 0% | 0
2400

## Item 6(c) ONSHORE LABOR
Onshore | [7 empty] | Onshore
| 10 Man Labor Crew | [7 empty] | 2 Man Labor Crew
| length of day | 14 | hrs | [5 empty] | length of day | 14 | hrs
|  | Rate/hr | No. | Rate/day | [5 empty] | Rate/hr | No. | Rate/day
| Superintendent | 37.38 | 1 | 523.32 | = | 523.32 |  |  | Superintendent | 37.38 | 2 | 523.32 | = | 1046.64
| Fitter | 31.66 | 3 | 443.24 | = | 1329.72 |  |  | Fitter | 31.66 | 0 | 443.24 | = | 0
| Welder | 31.66 | 3 | 443.24 | = | 1329.72 |  |  | Welder | 31.66 | 0 | 443.24 | = | 0
| Rigger | 17.45 | 3 | 244.3 | = | 732.9 |  |  | Rigger | 17.45 | 0 | 244.3 | = | 0
| Crane Operator |  |  |  | = |  |  |  | Crane Operator |  |  |  | =
| Painter |  |  |  | = |  |  |  | Painter |  |  |  | =
|  |  | 10 |  |  | 3915.66 | $/day |  |  |  | 2 |  |  | 1046.64 | $/day
| Equipment | [7 empty] | Equipment
| length of day | 14 | hrs | [5 empty] | length of day | 14 | hrs
|  | Rate/hr | No. | Rate/day | [5 empty] | Rate/hr | No. | Rate/day
| Tool House |  | 1 | 300 | = | 300 |  |  | Tool House |  | 1 | 300 | = | 300
| 750 CFM Air Compressor |  | 1 | 125 | = | 125 |  |  | 750 CFM Air Compressor |  | 0 | 125 | = | 0
| Welding Machine |  | 1 | 80 | = | 80 |  |  | Welding Machine |  | 0 | 80 | = | 0
| Cutting Rig |  | 3 | 80 | = | 240 |  |  | Cutting Rig |  | 0 | 80 | = | 0
| 4000# Air Tugger |  | 2 | 60 | = | 120 |  |  | 4000# Air Tugger |  | 0 | 60 | = | 0
| Consumables |  | 1 | 100 | = | 100 |  |  | Consumables |  | 1 | 100 | = | 100
| Cherry Picker 20 ton | 45 | 1 | 630 | = | 630 |  |  | Cherry Picker 20 ton | 45 | 0 | 630 | = | 0
| Crew Truck |  | 1 | 85 |  | 85 |  |  | Crew Truck |  | 1 | 85 |  | 85
[6 empty] | 1680 | $/day | [6 empty] | 485 | $/day
20 Man Labor Crew
| length of day | 14 | hrs
|  | Rate/hr | No. | Rate/day
| Superintendent | 37.38 | 1 | 523.32 | = | 523.32
| Fitter | 31.66 | 6 | 443.24 | = | 2659.44
| Welder | 31.66 | 6 | 443.24 | = | 2659.44
| Rigger | 17.45 | 6 | 244.3 | = | 1465.8
| Crane Operator |  |  |  | =
| Painter |  |  |  | =
|  |  | 19 |  |  | 7308 | $/day
Equipment
| length of day | 14 | hrs
|  | Rate/hr | No. | Rate/day
| Tool House |  | 2 | 300 | = | 600
| 750 CFM Air Compressor |  | 2 | 125 | = | 250
| Welding Machine |  | 2 | 80 | = | 160
| Cutting Rig |  | 6 | 80 | = | 480
| 4000# Air Tugger |  | 2 | 60 | = | 120
| Consumables |  | 2 | 100 | = | 200
| Cherry Picker 20 ton | 45 | 1 | 630 | = | 630
| Crew Truck |  | 1 | 85 |  | 85
[6 empty] | 2525 | $/day

## Item 6(d) SHOP LABOR
Shop:
Welding Crew
|  | $/hr | % on job |  | $/hr
| Foreman | 26.5 | 10% | = | 2.65
| Fitter | 26 | 100% | = | 26
| Welder | 26 | 100% | = | 26
| Rigger | 15 | 100% | = | 15
| Picker w/Oper | 60 | 15% | = | 9
[5 empty] | 78.65 | $/hr
Paint Crew
|  | $/hr | % on job |  | $/hr
| Foreman | 26.5 | 20% | = | 5.3
| Blaster | 21 | 40% | = | 8.4
| Painter | 21 | 60% | = | 12.6
| Rigger | 15 | 100% | = | 15
| Picker w/Oper | 60 | 10% | = | 6
[5 empty] | 47.3 | $/hr
Hydrotest Crew
|  | $/hr | % on job |  | $/hr
| Foremen | 26.5 | 50% | = | 13.25
| Rigger | 21 | 100% | = | 21
| Picker w/Oper | 21 | 15% | = | 3.15
[5 empty] | 37.4 | $/hr
X-Ray
|  |  | hrs/dy |  | shots/dy
|  |  | 8 | = | 64
|  |  | 10 | = | 80
|  |  | 12 | = | 96
|  | No. | Shots |  | shots/dy |  | crews
|  |  | 0 | / | 96 | / | 1 | = | 0
|  |  | days | = | 0

## Item 6(e) OFFSHORE LABOR
Offshore: | [6 empty] | Offshore: | Based on Quote From Stolt Offshore Inc. Tender No. 50762-AFE | [6 empty] | Offshore: | Based on Quote From Stolt Offshore Inc. Tender No. 50762-AFE | [6 empty] | Offshore:
| Construction Crew | [6 empty] | Dive Boat & 8 Dive Teams | [7 empty] | Four Dive Teams | [7 empty] | Pipeline Crossing Removal
| ( Four Man Crew ) | No. | Rate/day |  |  |  | 1.1 | (Eight Crews) |  | No. | Rate/day |  |  |  | 1.1 | (Four Crews) |  | No. | Rate/day |  |  |  | taken from MEGGA Industries quote 12/27/96 |  |  | No. | Rate/day
| Foreman | 1 | 450 | = | 450 |  |  | Supervisor |  | 2 | 640 | = | 1280 |  |  | Supervisor |  | 1 | 640 | = | 640 |  |  | Spud Barge, Oper. & 4100 Manitowac |  | 1 | 1900 | = | 1900
| Fitter w/equip | 2 | 420 | = | 840 |  |  | Diver |  | 8 | 410 | = | 3280 |  |  | Diver |  | 4 | 410 | = | 1640 |  |  | Tug Boat |  | 1 | 720 | = | 720
| Welder w/equip | 1 | 420 | = | 420 |  |  | Tender |  | 8 | 230 | = | 1840 |  |  | Tender |  | 4 | 230 | = | 920 |  |  | Supervisor |  | 1 | 420 | = | 420
| Rigger | 0 | 300 | = | 0 |  |  | Overtime: | No. | Hrs | Rate/Hr |  |  |  |  | Overtime: | No. | Hrs | Rate/Hr |  |  |  |  | Foreman |  | 1 | 360 | = | 360
| Crane Operator | 1 | 400 | = | 400 |  |  | Supervisor | 2 | 2 | 74 | = | 296 |  |  | Supervisor | 1 | 2 | 74 | = | 148 |  |  | Welder w/equipment |  | 1 | 360 | = | 360
| Painter | 0 | 330 | = | 0 |  |  | Diver | 8 | 2 | 47 | = | 752 |  |  | Diver | 4 | 2 | 47 | = | 376 |  |  | Welders Helper |  | 1 | 210 | = | 210
| Tool Box | 1 | 150 | = | 150 |  |  | Tender | 8 | 2 | 27 | = | 432 |  |  | Tender | 4 | 2 | 27 | = | 216 |  |  | Riggers |  | 5 | 210 | = | 1050
| 175 CFM Air Compressor | 1 | 110 | = | 110 | [7 empty] | 0 | [7 empty] | 0 |  |  | Deck Barge |  | 1 | 150 | = | 150
| 4000# Air Tugger | 2 | 60 | = | 120 |  |  |  |  | 24 |  |  | 7880 | $/day |  |  |  | 15 |  |  | 3940 | $/day |  | Crew Boat |  | 1 | 600 | = | 600
|  | 5 |  |  | 2490 | $/day | 1.2 | (Equipment) | [6 empty] | 1.2 | (Equipment) | [7 empty] | Hand Tools |  | 1 | 100 | = | 100
[8 empty] | Deep Air Diving Package ( 50' to 190' ) |  | 1 | 500 | = | 500 |  |  | Deep Air Diving Package ( 50' to 190' ) |  | 1 | 500 | = | 500 |  | taken from Stolt Tender No. 50762-AFE
| ( Eight Man Crew ) | No. | Rate/day |  |  |  |  | Pollution Dome Package w/accessories |  | 1 | 150 | = | 150 |  |  | Pollution Dome Package w/accessories |  | 1 | 150 | = | 150 |  |  | Diver |  | 3 | 410 | = | 1230
| Foreman | 1 | 450 | = | 450 |  |  | Jetting Pump Package ( Complete ) |  | 1 | 380 | = | 380 |  |  | Jetting Pump Package ( Complete ) |  | 1 | 380 | = | 380 |  |  | Tender |  | 3 | 230 | = | 690
| Fitter w/equip | 5 | 420 | = | 2100 |  |  | Underwater Burning Package |  | 1 | 275 | = | 275 |  |  | Underwater Burning Package |  | 1 | 275 | = | 275 |  |  | (Equipment)
| Welder w/equip | 2 | 420 | = | 840 |  |  | Topside Burning Packaage |  | 1 | 40 | = | 40 |  |  | Topside Burning Package |  | 1 | 40 | = | 40 |  |  | Deep Air Diving Package ( 50' to 190' ) |  | 0 | 500 | = | 0
| Rigger | 0 | 300 | = | 0 |  |  | Offshore Construction Toolbox |  | 1 | 125 | = | 125 |  |  | Offshore Construction Toolbox |  | 1 | 125 | = | 125 |  |  |  | Pollution Dome Package w/accessories | 1 | 150 | = | 150
| Crane Operator | 1 | 400 | = | 400 |  |  | Air Compressor Roto Screw ( 425 cfm ) |  | 1 | 175 | = | 175 |  |  | Air Compressor Roto Screw ( 425 cfm ) |  | 1 | 175 | = | 175 |  |  |  | Jetting Pump Package ( Complete ) | 1 | 380 | = | 380
| Painter | 0 | 330 | = | 0 |  |  | Air Lift |  | 1 | 45 | = | 45 |  |  | Air Lift |  | 1 | 45 | = | 45 |  |  |  | Underwater Burning Package | 1 | 275 | = | 275
| Tool Box | 1 | 150 | = | 150 |  |  | Hydraulic Power Unit w/300' reel |  | 1 | 205 | = | 205 |  |  | Hydraulic Power Unit w/300' reel |  | 1 | 205 | = | 205 |  |  |  | Topside Burning Package | 1 | 40 | = | 40
| 175 CFM Air Compressor | 1 | 110 | = | 110 |  |  | Hydraulic Impact Wrench |  | 2 | 75 | = | 150 |  |  | Hydraulic Impact Wrench |  | 2 | 75 | = | 150 |  |  |  | Offshore Construction Toolbox | 1 | 125 | = | 125
| 4000# Air Tugger | 2 | 60 | = | 120 |  |  | Dive Video Equip. w/500' Cable |  | 1 | 200 | = | 200 |  |  | Dive Video Equip. w/500' Cable |  | 0 | 200 | = | 0 |  |  |  | Air Compressor Roto Screw ( 425 cfm ) | 1 | 175 | = | 175
|  | 9 |  |  | 4170 | $/day |  | Dive Ladder |  | 1 | 20 | = | 20 |  |  | Dive Ladder |  | 1 | 20 | = | 20 |  |  |  | Air Lift | 1 | 45 | = | 45
[8 empty] | 15 BBL Tanks @ $50.00 Each |  | 2 | 50 | = | 100 |  |  | Dive Stage |  | 1 | 40 | = | 40 |  |  |  | Hydraulic Power Unit w/300' reel | 1 | 205 | = | 205
[12 empty] | = | 0 |  |  | 50' Sections of 1" Air Hose |  | 8 | 6 | = | 48 |  |  |  | Hydraulic Impact Wrench | 2 | 75 | = | 150
[13 empty] | 2365 | $/day |  | Hydraulic Grinders |  | 2 | 70 | = | 140 |  |  |  | Dive Video Equip. w/500' Cable | 0 | 200 | = | 0
[7 empty] | 1.4 | ( Dive Vessel ) | [7 empty] | Hydraulic Chippers |  | 2 | 60 | = | 120 |  |  |  | Dive Ladder | 1 | 20 | = | 20
[7 empty] | 1.41 | 4-Point Vessel |  | 1 | 6875 | = | 6875 |  |  | Wachs Model D Saws |  | 2 | 245 | = | 490 |  |  |  | Dive Stage | 0 | 40 | = | 0
[7 empty] | 1.42 | Subsistence |  | 19 | 60 | = | 1140 |  |  | 1000# Lift Bags |  | 2 | 65 | = | 130 |  |  |  | 50' Sections of 1" Air Hose | 8 | 6 | = | 48
[12 empty] | = | 0 |  |  | Davit and Stage |  | 1 | 85 | = | 85 |  |  |  | Hydraulic Grinders | 2 | 70 | = | 140
[13 empty] | 8015 | $/day |  | Man-Rated Air Tugger |  | 1 | 225 | = | 225 |  |  |  | Hydraulic Chippers | 2 | 60 | = | 120
[7 empty] | 1.5 | ( Third Party ) | [7 empty] | Dive Control Van |  | 1 | 80 | = | 80 |  |  |  | Wachs Model D Saws | 2 | 245 | = | 490
[8 empty] | Cochrane DGPS w/Oper |  | 1 | 1850 | = | 1850 |  |  | 15 BBL Tanks @ $50.00 Each |  | 2 | 50 | = | 100 |  |  |  | 1000# Lift Bags | 0 | 65 | = | 0
[12 empty] | = | 0 | [6 empty] | = | 0 |  |  |  | Davit and Stage | 1 | 85 | = | 85
[12 empty] | = | 0 | [7 empty] | 3523 | $/day |  |  | Man-Rated Air Tugger | 1 | 225 | = | 225
[13 empty] | 1850 | $/day | 1.4 | ( Third Party ) | [8 empty] | Dive Control Van | 1 | 80 | = | 80
[16 empty] | Cochrane DGPS w/Oper |  | 1 | 1850 | = | 1850 |  |  |  | 15 BBL Tanks @ $50.00 Each | 2 | 50 | = | 100
[12 empty] | Total | 20110 | $/day | [5 empty] | = | 0
[20 empty] | = | 0
[21 empty] | 1850 | $/day
[25 empty] | No. of Personnel | 9 |  |  | 10643 | $/day
[20 empty] | Total | 9313 | $/day
[24 empty] | 900 hp Tug |  | 1 | 4320 | = | 4320
[29 empty] | 14963 | $/day

## Item 6(f) COMPRESSOR LABOR COST
Compressor | quote from Universal Compression
Rental and Operators
rental/month
| Compressor | 1 | 12812 | = | 12812
| Mechanical Supervision | 1 | 1612.44 | = | 1612.44

## Item 6(g) Engrg & Drftg
Chandeleur Pipe Line Co.
System Abandonment
2789.01
ENGINEERING & DRAFTING DESIGN
|  | hrs. |  | $/hr.
Structural
| Engr. | 80 | x | 67 | 5360
| Drft | 40 | x | 49 | 1960
[5 empty] | 7320 |  |  |  | 7320
Pipeline
| Engr. | 250 | x | 67 | 16750
| Drft | 325 | x | 49 | 15925
[5 empty] | 32675 |  |  |  | 32675
| Field Trips | 4
| Personnel | 2
|  | days |  | hr/dy |  | $/hr
| Trips | 4 | x | 12 | x | 67 | = | 3216
|  | 4 | x | 12 | x | 49 | = | 2352
|  | days |  | $/dy
| Subsistence | 4 | x | 25 | x | 2 | = | 200
|  | trips |  | mi/trip |  | $/mi
| mileage | 4 | x | 190 | x | 0.55 | = | 418 | 6186
Bid Preparation & Evaluation
| Engr. | 100 | x | 67 | 6700 |  |  |  | 6700
ENGINEERING MANAGEMENT
| Trips Offshore | 3
| Project duration in weeks | 9
|  | days |  | hr/dy |  | $/hr
| Office | 13.5 | x | 8 | x | 67 | = | 7236
| Onshore | 3 | x | 8 | x | 67 | = | 1608
| Offshore trips | 3 | x | 12 | x | 67 | = | 2412
|  | days |  | $/dy
| Subsistence | 3 | x | 25 | x | 1 | = | 75
|  | trips |  | mi/trip |  | $/mi
| mileage | 3 | x | 150 | x | 0.55 | = | 247.5 | 11578.5
|  | 1083 |  | 59.5194 |  |  |  | subtotal | 64459.5

## Item 6(h) Offshore Fab
Chandeleur Pipe Line Co.
System Abandonment
2789.01
OFFSHORE WELDING
| Weld | No. |  | Hrs/
Welding | Size | Welds |  | Weld
| 10 |  | x | 7 | = | 0
| 8 |  | x | 5.75 | = | 0
| 6 |  | x | 4.25 | = | 0
| 4 |  | x | 3 | = | 0
| 3 |  | x | 2.25 | = | 0
| 2 |  | x | 1.5 | = | 0
| WOL |  | x | 2.25 | = | 0
Structural |  |  | / | 96 | = | 0
[6 empty] | 0 | total hrs | x | 78.65 | $/hr | = |  | 0
crews | 2
hrs/dy | 12 |  |  |  | 0 | hrs |  | = | 0 | dys
|  |  | 12 | hrs/dy | x | 2 | crews
| Weld | No. |  | Shots/ |  | $/
X-Ray | Size | Welds |  | Weld |  | Weld | [5 empty] | Total
| 10 | 0 | x | 3 | x | 3 | = | 0 |  |  |  | No. Shots
| 8 | 0 | x | 3 | x | 2.5 | = | 0 |  |  |  | 0
| 6 | 0 | x | 2 | x | 2.5 | = | 0
| 4 | 0 | x | 2 | x | 2.5 | = | 0
| 3 | 0 | x | 2 | x | 2.5 | = | 0
| 2 | 0 | x | 2 | x | 2.5 | = | 0
| WOL | 0 | x | 3 | x | 2.5 | = | 0
|  |  | x | 3 | x | 2.5 | = | 0
[8 empty] | 0 |  |  |  | 0
crews | 1
hrs/dy | 12
days
|  | days |  | hrs/dy |  | $/hr |  | crews
|  | 0 | x | 12 | x | 45 | x | 1 |  |  | = | 0
travel |  | days |  | hrs |  | $/hr |  | crews
|  | 0 | x | 4 | x | 30 | x | 1 |  |  | = | 0
mileage |  | days |  | miles |  | $/mi |  | crews
|  | 0 | x | 90 | x | 0.55 | x | 1 |  |  | = | 0 | 0
[12 empty] | sub-total | 0

## Item 6(i) Transportation
Jack-up |  | dys |  | $/dy
| mob/demob |  | x | 6500 |  |  |  |  | = | 0
| on job |  | x | 6500 |  |  |  |  | = | 0
Moves in
Fuel |  | gal/hr |  | hrs |  | $/gal |  | Field
| underway | 45 | x | 10 | x | 1.6 | x | 4 | = | 2880
|  | gal/dy |  | dys |  | $/gal
| on location | 100 | x | 33 | x | 1.6 |  |  | = | 5280
# trips
Shorebase |  | $/Use | [5 empty] | to Dock
|  | 200 | [5 empty] | 2 | = | 400
8560
Crewboat |  | dys |  | $/dy
| mob/demob |  | x | 2250 |  |  |  |  | = | 0
| on job |  | x | 2250 |  |  |  |  | = | 0
# trips
Fuel |  | gal/hr |  | hrs |  | $/gal |  | to Dock
| underway | 80 | x | 2 | x | 1.6 | x | 62 | = | 15872
|  | gal/dy |  | dys |  | $/gal
| on location | 100 | x | 62 | x | 1.6 |  |  | = | 9920
Shorebase |  | $/Use | [5 empty] | # trips
|  | 200 | [5 empty] | 62 | = | 12400
38192
Utility Boat |  | dys |  | $/dy |  |  |  |  | =
| mob/demob |  | x | 0 |  |  |  |  | = | 0
| on job |  | x | 0 |  |  |  |  | = | 0
# trips
Fuel |  | gal/hr |  | hrs |  | $/gal |  | to Dock
| underway | 60 | x | 4 | x | 1.6 | x | 4 | = | 1536
|  | gal/dy |  | dys |  | $/gal
| on location | 100 | x | 9 | x | 1.6 |  |  | = | 1440
Shorebase |  | $/Use | [5 empty] | # trips
|  | 200 | [5 empty] | 4 | = | 800
3776
[10 empty] | sub-total | 50528

## Item 6(j) Item Costs
| Offshore |  | Onshore
| personnel | personnel | travel | mileage |  | base cost | 1
Inspector | $/dy | $/hr | $/hr | $/mi |  | % inflation | 3.5%
| 456 | 35 | 35 | 0.55 |  | years | 10
[6 empty] | new cost | 1.4106
|  | fuel | fuel |  |  |  | fuel | fuel
|  | underway | on location |  | Barge |  | underway | on location
Jack-up | $/dy | gal/hr | gal/dy |  | w/Tug | $/dy | gal/hr | gal/dy
| 6500 | 45 | 100 |  |  |  | 45 | 100
quote from Superior Energy Svcs. email attached
|  | fuel | fuel |  |  |  | fuel | fuel
|  | underway | standby |  |  |  | underway | on location
Crewboat | $/dy | gal/hr | gal/dy |  | Tug | $/dy | gal/hr | gal/dy
| 2250 | 80 | 100 |  |  |  | 45 | 100
quote from Spirit Marine Serv. quote attached
Fuel | $/gal | Shorebase | $/Use |  |  |  | fuel | fuel
| 1.6 |  | 200 |  |  |  | underway | standby
[5 empty] | Utility Boat | $/dy | gal/hr | gal/dy
[5 empty] | 1700 |  | 60 | 100
| Offshore | Day Trip | Site Work
Subsistence | $/dy | $/dy | $/dy
| 68 | 25 | 84
X-Ray |  | Offshore |  |  | Onshore
| personnel | travel | mileage | personnel | travel | mileage
| $/hr | $/hr | $/mi | $/hr | $/hr | $/mi
| 45 | 30 | 0.55 | 42 | 30 | 0.55
Instrumentation |  | Offshore
| personnel | travel | mileage
| $/hr | $/hr | $/mi
| 40 | 0 | 0.55
Project Manager
| personnel | mileage
| $/hr | $/mi
| 67 | 0.55
Engineering |  |  |  |  | Drafting
| personnel | mileage |  |  |  | personnel | mileage
| $/hr | $/mi |  |  |  | $/hr | $/mi
| 67 | 0.55 |  |  |  | 49 | 0.55

## Item 6(k) Shop Fab
Chandeleur Pipe Line Co.
System Abandonment
2789.01
SHOP FABRICATION
| Weld | No. |  | Hrs/
Welding | Size | Welds |  | Weld
| 10 |  | x | 7 | = | 0
| 8 |  | x | 5.75 | = | 0
| 6 |  | x | 4.25 | = | 0
| 4 |  | x | 3 | = | 0
| 3 |  | x | 2.25 | = | 0
| 2 |  | x | 1.5 | = | 0
| WOL |  | x | 2.25 | = | 0
Structural |  |  | / | 96 | = | 0
[6 empty] | 0 | total hrs | x | 78.65 | $/hr | = |  | 0
crews | 1
hrs/dy | 10 |  |  |  | 0 | hrs |  | = | 0 | dys
|  |  | 10 | hrs/dy | x | 1 | crews
Hydrotest |  |  | 0 | days | x | 10 | hrs/dy | x | 37.4 | $/hr | = | 0
| Pump | [9 empty] | =
| Deadweights | [9 empty] | =
| Chart Recorder | [9 empty] | =
0
Blast & Paint |  |  | 0 | days | x | 10 | hrs/dy | x | 47.3 | $/hr | = |  | 0
| Weld | No. |  | Shots/ |  | $/
X-Ray | Size | Welds |  | Weld |  | Weld | [5 empty] | Total
| 10 | 0 | x | 3 | x | 3 | = | 0 |  |  |  | No. Shots
| 8 | 0 | x | 3 | x | 2.5 | = | 0 |  |  |  | 0
| 6 | 0 | x | 2 | x | 2.5 | = | 0
| 4 | 0 | x | 2 | x | 2.5 | = | 0
| 3 | 0 | x | 2 | x | 2.5 | = | 0
| 2 | 0 | x | 2 | x | 2.5 | = | 0
| WOL | 0 | x | 3 | x | 2.5 | = | 0
|  |  | x | 3 | x | 2.5 | = | 0
[8 empty] | 0 |  |  |  | 0
crews | 1
hrs/dy | 12
days | 0
|  | days |  | hrs/dy |  | $/hr |  | crews
|  | 0 | x | 12 | x | 42 | x | 1 |  |  | = | 0
travel |  | days |  | hrs |  | $/hr |  | crews
|  | 0 | x | 4 | x | 30 | x | 1 |  |  | = | 0
mileage |  | days |  | miles |  | $/mi |  | crews
|  | 0 | x | 90 | x | 0.55 | x | 1 |  |  | = | 0 | 0
Freight
Inspector |  | days |  | hrs/dy |  | $/hr
|  | 0 | x | 10 | x | 63 |  |  |  |  | = |  | 0
Total Days in Shop |  | 0 | [9 empty] | sub-total | 0