## Item (3)(a) Assumptions
Assumptions:
All Producers on the system are assumed shutin. Wells are not flowing. Utilities at each location are no longer active.
Producers are responsible to abandon producer owned pipelines and measurement equipment.
Producer will remove meter skid with assciated piping, risers, and riser tie-in pipe and valves at time of platform removal.
No salvage or resale value has been considered for pipe or equipment.
No allowances have been made for named tropical strom downtime.
All work will be performed during the summer work season.
All pipelines are abandoned in place except where specifically noted otherwise. Tube Turns and 100' of pipeline are removed at each end of pipelines.
Pipelines are buried a minimum of 3 feet at each end.
All pipeline ends are sealed using a mechanical type plug.
In field travel time for boats between locations is included in costs for work at each location.
All operations are daylight work only unless otherwise noted.

## Item 3(b)
Chandeleur Pipeline
System Abandonment |  | Comment | Equipment | Personnel | Event | Time to | Cumm. | Proj
[5 empty] | Timing | do Task | /Equip. | Run
[6 empty] | days | days | days
Isolate Pipelines at Production Platforms
LOTO at meters on each location
Remove section of pipe & blind pipe ends upstream of meters
| Mob to Location |  | Utility Boat | 4 Man Crew | 1 | 2 | 2 | 2
| MP 41 'L' |  | Utility Boat | 4 Man Crew | 2 | 1 | 3 | 3
| MP 41 'B' |  | Utility Boat | 4 Man Crew | 3 | 1 | 4 | 4
| CS 35 |  | Utility Boat | 4 Man Crew | 4 | 1 | 5 | 5
| CS 32 |  | Utility Boat | 4 Man Crew | 5 | 1 | 6 | 6
| MO 904 |  | Utility Boat | 4 Man Crew | 6 | 1 | 7 | 7
| MO 990 'A' |  | Utility Boat | 4 Man Crew | 7 | 1 | 8 | 8
| MO 908 |  | Utility Boat | 4 Man Crew | 8 | 1 | 9 | 9
| Dive at BS 42 and close TETCO Pipeline valve on SSTI tie-in. ( Mob & DeMob for this operation ) |  | Dive Boat | 8 Dive Teams | 9 | 3 | 3 | 10
Reduce Pressure on Pipeline
| Rig up rental compressor at Pascagoula Metering Station. | 7 to 10 days | Labor Crew | 10 Man Crew | 1 | 10 | 10 | 10
Prepare site to tie down compressor
Concrete slab with anchor bolts
Leveled and packed ground to pin compressor down on
Install rental fuel gas filter
Install gas turbine meter run for gas sales measurement
Install rental compressor with cooler
Tie in compressor suction to manifold and discharge into Destin Meter Skid
Sit up portable lights for night operations
| Route 12" and 16" Chandeleur Pipelines at Manifold into Refinery |  |  | 2 Man Crew | 1 | 1 | 1 | 1
| Draw down pressure on pipelines to 600 psig by pulling gas into the Pascagoula Refinery. |  |  | 2 Man Crew | 2 | 1 | 2 | 2
| Pull down pressure on pipeline to 50 psig. Discharge into Destin Pipeline at 900 psig. | 7 to 10 days | Rental Compressor | Operators | 10 | 7 | 7 | 17
| Blowdown pipeline to atmosphere. |  |  | 2 Man Crew | 11 | 2 | 4 | 19
Blowdown offshore at MP 41 'B'?
Flush Pipeline System with Water
| Tie-In 500 bbl frac tank to pig trap kickout line at Pascagoula |  | Labor Crew | 10 Man Crew | 2 | 5 | 15 | 15
Rig up 1000 gpm pump at platform ( 1 day travel, 1 day rig up each location )
Push pig with seawater from platform
| Mob to Location |  | Jack Up | 8 Man Crew | 12 | 2 | 2 | 21
| MO 908 'A' into 12" Chandeleur Pipeline ( 1/2 day to flush line ) |  | Jack Up | 8 Man Crew | 13 | 3 | 5 | 24
| MO 990 'A' into 16" Chandeleur Pipeline ( 1/2 day to flush line ) |  | Jack Up | 8 Man Crew | 14 | 3 | 8 | 27
| MP 41 'B' to Pascagoula ( 1-1/2 day to flush line ) |  | Jack Up | 8 Man Crew | 15 | 4 | 12 | 31
| MP 41 'L' to Pascagoula ( 2-1/2 days to flush line ) |  | Jack Up | 8 Man Crew | 16 | 5 | 17 | 36
Pascagoula Metering Station
| Rig down and move Rental Compressor and equipment out |  | Labor Crew | 10 Man Crew | 12 | 4 | 19 | 23
| Remove 500 bbl frac tank ( Ship out any liquids ) |  | Labor Crew | 10 Man Crew | 13 | 1 | 20 | 24
- 20 man crew divided into red and blue teams
| Set Up on Site |  |  | 20 Man Crew | 16 | 1 | 1 | 36
| Remove 16" & 12" Pig Receivers |  | Labor Crew | 20 Man Crew | 20 | 1 | 2 | 37
| Remove Manifold and piping between Manifold, Pig Receivers, and Destin Meter Skid |  | Labor Crew | 20 Man Crew | 20 | 3 | 5 | 39
| Cut incoming 16" & 12" pipelines below ground level, seal ends, and bury |  | Labor Crew | 20 Man Crew | 20 | 2 | 7 | 39
| Remove 250 ft of 12" pipeline from Destin Meter Skid to Destin Pipeline Tie-In. Back fill trench. |  | Labor Crew | 20 Man Crew | 21 | 2 | 10 | 41
| Remove Destin Meter Skid ( Hold for Salvage ) |  | Labor Crew | 20 Man Crew | 21 | 1 | 8 | 40
| Remove buried dual 12" pipe runs between Manifold and Refinery and GulfSouth meters. Back fill trench. |  | Labor Crew | 20 Man Crew | 21 | 2 | 12 | 42
| Remove Refinery Meter Skid ( Hold for Salvage ) |  | Labor Crew | 20 Man Crew | 21 | 1 | 13 | 42
| Remove concrete block retaining wall around former oil tank storage area |  | Labor Crew | 20 Man Crew | 22 | 1 | 14 | 43
| Remove tie back piping from Refinery Meter Skid to 16" & 12" buried piping into Refinery. Blind flange connections at buried 16" & 12" flanges. |  | Labor Crew | 20 Man Crew | 22 | 3 | 17 | 45
| Remove GulfSouth pressure control station and Instrument Bldg. ( Computer Bldg. and Microwave Tower belong to GulfSouth ) |  | Labor Crew | 20 Man Crew | 22 | 1 | 19 | 44
| Remove buried Bad Oil Storage Tank and fill hole. |  | Labor Crew | 20 Man Crew | 22 | 1 | 18 | 45
| Remove three 10" meter runs along with buried 20" suction and dischagre headers. |  | Labor Crew | 20 Man Crew | 23 | 3 | 22 | 48
| Remove departing 12" pipeline upto GulfSouth ownership. Seal and bury end of pipeline. |  | Labor Crew | 20 Man Crew | 23 | 3 | 25 | 48
| Remove Chandeleur Pipeline Instrument/Computer Bldg. ( Hold for Salvage ) |  | Labor Crew | 20 Man Crew | 24 | 1 | 26 | 49
| Clean up and level site |  | Labor Crew | 20 Man Crew | 24 | 1 | 27 | 49

## Item 3(c)
MP41 'L'
| Travel |  | Jack Up | 4 Dive Teams | 17 | 0 | 0 | 36
| Cut & remove tube turns on incoming & departing 16" risers. |  | Jack Up | 4 Dive Teams | 17 | 2 | 2 | 38
Cut, seal, and bury ends of pipelines 100 feet off structure
| Decommission and remove TETCO meter skid. Remove pipeline shutdown valve and associated piping. Remove incoming & departing 16" risers. ( Include with platform removal. ) | Negotiate w/Producer to remove at salvage of Platform
MP41 'B'
| Travel |  | Jack Up | 4 Dive Teams | 18 | 1 | 3 | 39
| Cut & remove tube turns on the 16" & 12" risers. |  | Jack Up | 4 Dive Teams | 18 | 3 | 6 | 42
Cut, seal, and bury ends of pipelines 100 feet off structure
| Decommission and remove meter skid. Remove shutdown valves and associated piping. Remove 16" & 12" pipeline pig launchers. Remove 16" & 12" risers. ( Included with platform removal. ) | Negotiate w/Producer to remove at salvage of Platform
MO 861 'A'
| Travel |  | Jack Up | 4 Dive Teams | 19 | 1 | 7 | 43
| Remove departing 12" riser and tube turn. |  | Jack Up | 4 Dive Teams | 19 | 3 | 10 | 46
Cut, seal, and bury end of departing pipeline 100 feet off structure
861 'A' is a jacket only, not a producing platform. The incoming riser & pipe crossing structure is part of the CNGPL system.
TETCO
| Travel to Location ( Remob Dive Boat to start this phase ) |  | Dive Boat | 8 Dive Teams | 17 | 2 | 2 | 38
| Setup on Location |  |  |  |  | 1 | 3 | 39
| Jet to uncover SSTI assembly |  |  |  |  | 1 | 4 | 40
| Disassemble SSTI and 10" Jumper |  |  |  |  | 1 | 5 | 41
| Bury connections on pipelines |  |  |  |  | 1 | 6 | 42
CS 35 SSTI
| Travel to Location |  | Dive Boat | 8 Dive Teams | 18 | 1 | 7 | 43
| Setup on Location |  |  |  |  | 1 | 8 | 44
| Jet to uncover SSTI assembly |  |  |  |  | 1 | 9 | 45
| Disconnect 6" pipeline/SSTI tie-in to Carrier pipeline |  |  |  |  | 1 | 10 | 46
| Bury SSTI assemly |  |  |  |  | 0 | 10 | 46
CS 32 SSTI
| Travel to Location |  | Dive Boat | 8 Dive Teams | 19 | 0 | 10 | 46
| Setup on Location |  |  |  |  | 0 | 10 | 46
| Jet to uncover SSTI assembly |  |  |  |  | 0 | 10 | 46
| Disconnect 6" pipeline/SSTI tie-in to Carrier pipeline |  |  |  |  | 1 | 11 | 47
| Bury SSTI assemly |  |  |  |  | 1 | 12 | 48
MO 904 SSTI ( UNOCAL Tie-in )
| Travel to Location |  | Dive Boat | 8 Dive Teams | 20 | 1 | 13 | 49
| Setup on Location |  |  |  |  | 1 | 14 | 50
| Jet to uncover SSTI assembly |  |  |  |  | 1 | 15 | 51
| Disconnect 10" pipeline/SSTI tie-in to Carrier pipeline |  |  |  |  | 1 | 16 | 52
| Bury SSTI assemly |  |  |  |  | 1 | 17 | 53
MO 902 SSTI ( 12" Lateral to 16" Chandeleur )
| Travel to Location |  | Dive Boat | 8 Dive Teams | 21 | 1 | 18 | 54
| Setup on Location |  |  |  |  | 1 | 19 | 55
| Jet to uncover SSTI assembly |  |  |  |  | 1 | 20 | 56
| Disconnect 12" pipeline/SSTI tie-in to Carrier pipeline |  |  |  |  | 1 | 21 | 57
| Retrieve SSTI assembly and bury pipeline ends |  |  |  |  | 1 | 22 | 58
MO 990 SSTI
| Travel to Location |  | Dive Boat | 8 Dive Teams | 22 | 1 | 23 | 59
| Setup on Location |  |  |  |  | 1 | 24 | 60
| Jet to uncover SSTI assembly |  |  |  |  | 1 | 25 | 61
| Disconnect 12" pipeline/SSTI tie-in to Carrier pipeline |  |  |  |  | 1 | 26 | 62
| Retrieve pipeline braces and SSTI assembly |  |  |  |  | 1 | 27 | 63
| Blind connection on dual 8" pipelines and SSTI and bury ends |  |  |  |  | 1 | 28 | 64
Pascagoula Channel
| Mob to Location |  | Spud Barge | 9 Man Crew | 17 | 2 | 2 | 38
| Remove 12" & 16" pipeline crossings and 12" spare |  |  |  |  | 18 | 20 | 56
Buried 10 ft. under channel, 6 days per line
Miss Gulf Outlet Channel
| Mob to Location |  | Spud Barge | 9 Man Crew | 18 | 2 | 22 | 58
| Remove 12" & 16" pipeline crossings and 12" spare |  |  |  |  | 24 | 46 | 82
Buried 35 ft. under channel 8 days per line

## Item 3(d)(1) SSTI TETCO
Chandeleur Pipe Line Co. |  |  |  | SSTI Disassembly
System Abandoment
2789.01
Assume 14 hour daylight operation
SSTI Assembly
TETCO ( Breton Sound 42 )
Pipeline Brace in Vertical
16" Chandeleur Pipeline
200 ft of 10" Jumper
24" TETCO Pipeline
Pipeline Brace in Vertical
Plan View
Day 1
Set buoy markers on TETCO & Chandeleur Pipelines |  |  |  |  | 5 @ 2 hrs each | 10 hrs
Set anchors | [5 empty] | 4 hrs
Day 2
Jet to uncover SSTI assembly
( Pipeline brace and manifold piping will be covered by 3:1 sand/concrete bags )
Day 3
Close Chandeleur Pipeline valve #1 and TETCO Pipeline valve #3
Remove SSTI assembly at Chandeleur Pipeline, disconnect from 10" Jumper, and remove brace
Disconnect 10" Jumper at TETCO Pipeline valve #3 and blind
Remove SSTI assembly and 10" Jumper to surface
Day 4
Retrieve SSTI assembly
Blind Chandeleur Pipeline valve #1
Insure Chaneleur Pipeline valve #1 and TETCO Pipeline valve #3 are covered to 3 feet
1
2
3

## Item 3(d)(2) SSTI MO 902
Chandeleur Pipe Line Co. |  |  | SSTI Disassembly
System Abandoment
2789.01
Assume 14 hour daylight operation
Typical SSTI Assembly
Mobile-902 ( 12" Lateral Pipeline )
12" Chandeleur Pipeline
Mechanical Tap
Pipeline Brace
Carrier Pipeline
12" Lateral Pipeline
Plan View
Day 1
Set buoy markers on pipelines and manifold |  |  |  | 3 @ 2 hrs each |  | 6 hrs
Set anchors | [5 empty] | 4 hrs
Day 2
Jet to uncover SSTI assembly
( Pipeline brace and manifold piping will be covered by 3:1 sand/concrete bags )
Day 3
Close Chandeleur Pipeline valve #1
Close manifold valve #2 and Lateral Pipeline valve #3
Disconnect flange at valve #1
Disconnect pipeline brace from Carrier pipeline and Lateral pipeline
Retrieve pipeline brace
Day 4
Retrieve SSTI assembly
Blind Chandeleur Pipeline valve #1 and Lateral pipeline end
Insure Carrier pipeline valve #1 and Lateral Pipeline end are covered to 3 feet
1
2
3

## Item 3(d)(3) SSTI MO 990
Chandeleur Pipe Line Co. |  |  | SSTI Disassembly
System Abandoment
2789.01
Assume 14 hour daylight operation
Typical SSTI Assembly
Mobile-990 ( Looped Lines to MO 990 'A' )
|  | Mechanical Tap |  |  | 16" Chandeleur Pipeline
| Carrier Pipeline |  | Pipeline Brace
8" Looped Pipeline
Plan View
Day 1
Set buoy markers on pipelines and manifold |  |  |  | 4 @ 2 hrs each | 8 hrs
Set anchors |  |  |  |  | 4 hrs
Day 2
Jet to uncover SSTI assembly
( Pipeline brace and manifold piping will be covered by 3:1 sand/concrete bags )
Day 3
Close Chandeleur Pipeline valve #1
Close manifold valve #2 and pipeline valves #3
Disconnect flange at valve #1
Disconnect pipeline braces, two, from Carrier pipeline and Lateral pipeline
Day 4
Retrieve braces and SSTI assembly
Day 5
Blind Chandeleur Pipeline valve #1 and two Lateral pipeline ends
Insure Carrier pipeline valve #1 and Lateral Pipeline ends are covered to 3 feet
1
2
3

## Item 3(d)(4) SSTI Costs
Chandeleur Pipe Line Co. |  |  | SSTI Disassembly
System Abandoment
2789.01
Assume 14 hour daylight operation
Typical SSTI Assembly
Chandeleur Sound-35 & 32, Mobile-904
|  | Mechanical Tap |  |  |  | 16" Chandeleur Pipeline
Pipeline Brace
Carrier Pipeline
Dual 6" Pipelines
From CS 35
Plan View
From CS 32
Day 1
Set buoy markers on pipelines and manifold |  |  |  | 3 @ 2 hrs each |  | 6 hrs
Set anchors | [5 empty] | 4 hrs
Day 2
Jet to uncover SSTI assembly
( Pipeline brace and manifold piping will be covered by 3:1 sand/concrete bags )
Day 3
Close Carrier pipeline valve #1
Close manifold valve #2 and pipeline valves #3 and #4
Disconnect flange at Carrier valve #1
Disconnect pipeline brace from Carrier pipeline
Tie unto SSTI assembly and move away from Carrier pipeline
Blind Carrier pipeline valve #1 and mating flange on SSTI assembly
Day 4
Bury manifold assembly and Lateral pipeline ends to 3 feet of cover
Insure Carrier pipeline valve #1 is covered to 3 feet
1
2
3
4