## Summary Sheet
Exhibit No. DCP-29
Page 3 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
Summary
Estimated
Cost
(March 2006$)
I. | Project Management
| A. | Pre-abandonment |  |  |  |  | 280000
| B. | Abandonment |  |  |  |  | 936000
[6 empty] | Total I. | 1216000
II. | Contract Expense
| A. | Engineering |  |  |  |  | 257000
| B. | Environmental |  |  |  |  | 1142050
| C. | ROW |  |  |  |  | 744200
[6 empty] | Total II. | 2143250
III. | Property Tax | [5 empty] | 472651
[6 empty] | Total III. | 472651
IV. | Pipeline Retirement
| A. | Clean and purge pipeline |  |  |  |  | 135200
| B. | Uncased highway crossings |  |  |  |  | 3589238.7675
| C. | Cased highway crossings |  |  |  |  | 1457979.0265
| D. | Cased railroad crossings |  |  |  |  | 166626.1745
| E. | Small stream crossings |  |  |  |  | 847053.0486
| F. | River crossings
|  | 1 | Hunting Creek |  |  |  | 66478.6629
|  | 2 | St. Leonards Creek |  |  |  | 91111.2015
|  | 3 | Patuxent River |  |  |  | 201174.7658
|  | 4 | Potomac River |  |  |  | 722761.7486
| G. | Remote mainline valves |  |  |  |  | 232391.2499
| H. | Pipeline drips |  |  |  |  | 54038.5226
| I. | Cathodic protection facilities |  |  |  |  | 25005.5491
| J. | Pipeline markers |  |  |  |  | 89461.4683
| K. | M&R stations
|  | 1 | Loudon M&R station |  |  |  | 298913.7093
|  | 2 | Pleasant Valley M&R station |  |  |  | 163279.9267
|  | 3 | Ox M&R station |  |  |  | 67411.0717
| L. | Compressor stations
|  | 1 | Loudon compressor station |  |  |  | 859632.9794
|  | 2 | Pleasant Valley compressor station |  |  |  | 584724.7775
[6 empty] | Total IV. | 9517282.6503
Exhibit No. DCP-29
Page 4 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
Summary
Estimated
Cost
(March 2006$)
V. | Salvage
| A. | Equipment |  |  |  |  | -231280.586
| B. | Scrap steel |  |  |  |  | -227397
| C. | Line pack |  |  |  |  | -1577679.0052
[6 empty] | Total V. | -2036356.5912
VI. | Contingency |  |  | (10% of I, II, and IV above) |  |  | 1287653.265
[6 empty] | Total VI. | 1287653.265
[5 empty] | Grand Total: |  | 12600480.3241

## Project Management
Exhibit No. DCP-29
Page 5 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
I. Project Management
It is estimated that Cove Point will begin planning its transmission pipeline retirement two years prior to commencement
of retirement activities. Further it is estimated that the retirement project will take one year. Costs have been included
in the estimate to provide an allowance for company personnel that will be used to assist the general contractor and
subcontractors with dismantling compressor stations and M&R stations to assure project safety and security.
[5 empty] | Unit | No. | Days | Rate | Total
A. Pre-Abandonment
|  | 1 | Construction manager |  | person | 1 | 130 | 800 | 104000
|  | 2 | Environmental coordinator (office) |  | person | 1 | 130 | 800 | 104000
|  | 3 | Office support |  | person | 1 | 130 | 400 | 52000
|  | 4 | FERC 7(b) abandonment application |  | person | 1 | 10 | 800 | 8000
|  | 5 | ROW lease holder notification (legal) |  | person | 1 | 10 | 1200 | 12000
[6 empty] | Subtotal pre-abandonment: |  |  | 280000
B. Abandonment
|  | 1 | Construction manager |  | person | 1 | 260 | 800 | 208000
|  | 2 | Environmental coordinator (office) |  | person | 1 | 130 | 800 | 104000
|  | 3 | Office support |  | person | 1 | 260 | 400 | 104000
|  | 4 | Transmission personnel |  | person | 5 | 130 | 800 | 520000
[6 empty] | Subtotal abandonment: |  |  | 936000
|  |  |  | Total project management: |  |  |  |  | 1216000

## Contract Expense
Exhibit No. DCP-29
Page 6 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
II. Contract Expense
[7 empty] | Unit | No. | Days | Rate | Total
A. Engineering
|  | 1 | Inspection of pipeline facilities |  |  |  | person | 2 | 15 | 800 | 24000
|  | 2 | Plans, specifications and estimate |  |  |  | person | 2 | 60 | 800 | 96000
|  | 3 | Prepare bid documents and attend meetings |  |  |  | person | 2 | 75 | 800 | 120000
|  | 4 | Travel expenses |  |  |  | trip | 8 |  | 1500 | 12000
|  | 5 | Misc. office expense |  |  |  | lump sum |  |  |  | 5000
[6 empty] | Total engineering expense: |  |  |  |  | 257000
B. Environmental
|  | 1 | Environmental assessment of transmission pipeline facilities
|  |  | a. | Inspection and assessment of pipeline facilities |  |  | person | 2 | 15 | 800 | 24000
|  |  | b. | Create sampling plan |  |  | person | 2 | 15 | 800 | 24000
|  |  | c. | Lab analysis of pre-abandonment field samples
|  |  |  | 1 | Remote site field samples |  | each | 54 |  | 150 | 8100
|  |  |  | 2 | M&R station field samples |  | each | 25 |  | 150 | 3750
|  |  |  | 3 | Compressor station field samples |  | each | 100 |  | 150 | 15000
|  |  | d. | Evaluation and reports |  |  | person | 2 | 15 | 800 | 24000
[10 empty] | Subtotal: | 98850
|  | 2 | Environmental monitoring during abandonment work
|  |  | a. | Environmental consultant (on-site)
|  |  |  | 1 | Remote sites |  | person | 1 | 1049 | 800 | 839200
|  |  |  | 2 | M&R stations |  | person | 1 | 52 | 800 | 41600
|  |  |  | 3 | Compressor stations |  | person | 1 | 114 | 800 | 91200
|  |  | b. | Lab analysis of abandonment field samples
|  |  |  | 1 | Remote site field samples |  | each | 211 |  | 150 | 31650
|  |  |  | 2 | M&R station field samples |  | each | 25 |  | 150 | 3750
|  |  |  | 3 | Compressor station field samples |  | each | 100 |  | 150 | 15000
|  |  | c. | Evaluation and reports |  |  | person | 1 | 26 | 800 | 20800
[10 empty] | Subtotal: | 1043200
[6 empty] | Total environmental expense: |  |  |  |  | 1142050
C. ROW
|  | 1 | ROW agent |  |  |  | person | 1 | 448 | 600 | 268800
|  | 2 | Damage payments to leaseholders for land use loss |  |  |  | leaseholder | 448 |  | 1000 | 448000
|  | 3 | Travel expenses (auto) |  |  |  | trip | 896 |  | 25 | 22400
|  | 4 | Misc. office expense |  |  |  | lump sum |  |  |  | 5000
[6 empty] | Total ROW expense: |  |  |  |  | 744200

## Property Tax
Exhibit No. DCP-29
Page 7 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
III. Property Tax
It is estimated that it will take one year to retire the pipeline and restore the premises to a natural
setting. Cove Point must pay property tax related to its pipeline assets for this one-year period.
Property Tax
Paid in
|  | State | Yr. 2005
|  | Maryland | 256334
|  | Virginia | 216317
|  | Total: | 472651

## Clean and Purge
Exhibit No. DCP-29
Page 8 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
A. Clean and purge pipeline
Description of Work:
Prior to its last delivery, Cove Point conducts a series of pigging operations to ensure that its line is clean and free
of liquids. After the last delivery to its customers, Cove Point operating staff isolates the pipeline system from gas
supply inputs and delivery points. Abandonment pressure is assumed to be 200 psig. Line pack is evacuated to
atmospheric pressure by flaring or venting. At this point pipeline is filled with natural gas at atmospheric pressure.
Cove Point staff evacuates sections of pipe using pipeline evacuation equipment. At this point pipeline is filled with
air at atmospheric pressure. Pipeline is ready for demolition work.
|  |  |  | Unit | No. | Days | Rate | Total
1 | Pigging operation prior to final shutdown. |  |  | each | 2 |  | 10000 | 20000
2 | Isolate pipeline from input and delivery points |  |  | person | 3 | 5 | 800 | 12000
3 | Blowdown system (14 sites) |  |  | person | 3 | 14 | 800 | 33600
4 | Pipeline evacuation
| a. | Evacuate TL-522 pipeline at M/L valves (10 sites) |  | person | 3 | 20 | 800 | 48000
| b. | Evacuate TL-523 pipeline (1 site) |  | person | 3 | 1 | 800 | 2400
| c. | Evacuate TL-530 pipeline (1 site) |  | person | 3 | 1 | 800 | 2400
| d. | Evacuate TL-531 pipeline (1 site) |  | person | 3 | 1 | 800 | 2400
| e. | Evacuate TL-538 pipeline (1 site) |  | person | 3 | 1 | 800 | 2400
[7 empty] | Subtotal: | 57600
4 | Compressor station and M&R station evacuation
| a. | Evacuate compressor stations (2 sites) |  | person | 3 | 2 | 800 | 4800
| b. | M&R station evacuation (3 sites) |  | person | 3 | 3 | 800 | 7200
[7 empty] | Subtotal: | 12000
|  |  | Total estimated cost to clean and purge pipeline: |  |  |  |  | 135200

## Uncased HWY Crossing
Exhibit No. DCP-29
Page 9 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
B. Uncased Highway Crossings
Description of Work:
Detailed cost estimate below reflects work required to retire an uncased highway crossing (100 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with concrete
or grout, backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (1 day)
Equipment |  |  | No. | Hours | Rate | Total
dozer, cat D-6 |  |  | 1 | 8 | 76.8792 | 615.0336
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
3/4 ton pick-up with trailer |  |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 49.7381
[5 empty] | Subtotal: | 1127.2005
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster |  |  | 1 | 8 | 37.23 | 297.84
pipefitter/welder |  |  | 1 | 8 | 52.0455 | 416.364
helper |  |  | 1 | 8 | 36.4318 | 291.4548
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 2486.9028
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 49.7381
[5 empty] | Subtotal: | 49.7381
|  |  | Total Direct Costs (1) = |  |  | 3663.8413
2. Excavate and cap pipe ends (2 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor | [5 empty] | 111.3897
[5 empty] | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 10 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. B. Uncased highway crossings (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 16 | 37.23 | 595.68
teamster |  |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  |  | 1 | 16 | 52.0455 | 832.728
helper |  |  | 1 | 16 | 36.4318 | 582.9096
laborer |  |  | 4 | 16 | 23.6513 | 1513.68
foreman |  |  | 1 | 16 | 53.3205 | 853.128
[5 empty] | Subtotal: | 5569.4856
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 111.3897
[5 empty] | Subtotal: | 111.3897
|  |  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
dump truck 8 cy |  |  | 1 | 8 | 21.6815 | 173.452
concrete pump, trailer mounted |  |  | 1 | 8 | 13.2355 | 105.884
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 35.5817
[5 empty] | Subtotal: | 977.6609
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1779.084
Material | [5 empty] | Total
Concrete @ $88/cy (estimate 30 cy) | [5 empty] | 2640
Sales tax (5%) | [5 empty] | 132
Miscellaneous (2% of labor) | [5 empty] | 35.5817
[5 empty] | Subtotal: | 2807.5817
|  |  | Total Direct Costs (3) = |  |  | 5564.3266
Exhibit No. DCP-29
Page 11 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. B. Uncased highway crossings (continued)
4. Restore Site (1 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 29.6249
[5 empty] | Subtotal: | 339.0369
Labor |  |  | No. | Hours | Rate | Total
teamster (flatbed) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1481.244
Material | [5 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 1000
[5 empty] | Subtotal: | 1000
|  |  | Total Direct Costs (4) = |  |  | 2820.2809
Summary: Uncased Highway Crossings
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites | [5 empty] | 3663.8413
2. Excavate and cap pipe ends | [5 empty] | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area | [5 empty] | 5564.3266
4. Restore Site | [5 empty] | 2820.2809
|  |  | Pipeline contractor direct costs: |  |  | 20641.6546
|  |  | 5% Mobilization |  |  | 1032.0827
[5 empty] | Subtotal: | 21673.7373
|  |  | 15% Contractor overhead: |  |  | 3251.0606
[5 empty] | Subtotal: | 24924.7979
|  |  | 10% Contractor profit: |  |  | 2492.4798
|  |  | Total pipeline contractor costs: |  |  | 27417.2777
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 5
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 3000
| Total pipeline contractor and company inspection cost per uncased highway crossing: |  |  |  |  | 30417.2777
|  | No. of uncased highway crossings: |  |  |  | 118
|  | Total estimated cost to retire uncased highway crossings: |  |  |  | 3589238.7675

## Cased Road Crossing
Exhibit No. DCP-29
Page 12 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
C. Cased highway crossings
D. Cased railroad crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a cased highway/railroad crossing (100 feet).
Work includes R.O.W. fence removal, excavation, removal of pipe from casing, filling casing
with concrete or grout, removal of vent pipes, and restoration of area.
1. Remove R.O.W. Fence and access work sites (1 day)
Equipment |  |  | No. | Hours | Rate | Total
dozer, cat D-6 w winch |  |  | 1 | 8 | 84.0068 | 672.0544
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
3/4 ton pick-up with trailer |  |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 49.7381
[5 empty] | Subtotal: | 1184.2213
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster |  |  | 1 | 8 | 37.23 | 297.84
pipefitter/welder |  |  | 1 | 8 | 52.0455 | 416.364
helper |  |  | 1 | 8 | 36.4318 | 291.4548
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 2486.9028
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 49.7381
[5 empty] | Subtotal: | 49.7381
|  |  | Total Direct Costs (1) = |  |  | 3720.8621
2. Excavate and remove pipe from casing (2 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 16 | 66.0951 | 1057.5216
dozer, Cat D-6 w winch |  |  | 1 | 16 | 84.0068 | 1344.1088
hydrocrane, Grove, 30 ton |  |  | 1 | 16 | 55.3522 | 885.6352
lowboy |  |  | 1 | 16 | 51.1601 | 818.5616
pipe truck (1/2 time) |  |  | 1 | 8 | 45.6805 | 365.444
flatbed truck |  |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor | [5 empty] | 142.8098
[5 empty] | Subtotal: | 5538.9386
Exhibit No. DCP-29
Page 13 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. C./D. Cased highway/railroad crossings (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator (dozer, backhoe) |  |  | 2 | 16 | 37.23 | 1191.36
operator (hydrocrane) |  |  | 1 | 16 | 42.3428 | 677.484
teamster (pipe truck) |  |  | 1 | 8 | 37.23 | 297.84
teamster (lowboy) |  |  | 1 | 16 | 37.23 | 595.68
teamster (flatbed truck) |  |  | 1 | 16 | 37.23 | 595.68
pipefitter/welder |  |  | 1 | 16 | 52.0455 | 832.728
helper |  |  | 1 | 16 | 36.4318 | 582.9096
laborer |  |  | 4 | 16 | 23.6513 | 1513.68
foreman |  |  | 1 | 16 | 53.3205 | 853.128
[5 empty] | Subtotal: | 7140.4896
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 142.8098
[5 empty] | Subtotal: | 142.8098
|  |  | Total Direct Costs (2) = |  |  | 12822.238
3. Fill casing with concrete or grout, backfill trench, grade disturbed area (2 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 8 cy |  |  | 1 | 16 | 21.6815 | 346.904
concrete pump, trailer mounted |  |  | 1 | 16 | 8.961 | 143.376
1/2 ton pickup with 4wd |  |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor | [5 empty] | 71.1634
[5 empty] | Subtotal: | 1886.9298
Labor |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  | 1 | 16 | 37.23 | 595.68
teamster (dump truck) |  |  | 1 | 16 | 37.23 | 595.68
laborer |  |  | 4 | 16 | 23.6513 | 1513.68
foreman |  |  | 1 | 16 | 53.3205 | 853.128
[5 empty] | Subtotal: | 3558.168
Material | [5 empty] | Total
Concrete @ $88/cy (estimate 30 cy) | [5 empty] | 2640
Sales tax (5%) | [5 empty] | 132
Miscellaneous 2% of labor | [5 empty] | 71.1634
[5 empty] | Subtotal: | 2843.1634
|  |  | Total Direct Costs (3) = |  |  | 8288.2611
Exhibit No. DCP-29
Page 14 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. C./D. Cased highway/railroad crossings (continued)
4. Restore Site (1 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 29.6249
[5 empty] | Subtotal: | 339.0369
Labor |  |  | No. | Hours | Rate | Total
teamster (flatbed) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1481.244
Material | [5 empty] | Total
allow $2000 for topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 2000
[5 empty] | Subtotal: | 2000
|  |  | Total Direct Costs (4) = |  |  | 3820.2809
Summary: Cased Highway/Railroad Crossings
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites | [5 empty] | 3720.8621
2. Excavate and remove pipe from casing | [5 empty] | 12822.238
3. Fill casing with concrete or grout, backfill trench, grade disturbed area | [5 empty] | 8288.2611
4. Restore Site | [5 empty] | 3820.2809
|  |  | Pipeline contractor direct costs: |  |  | 28651.6421
|  |  | 5% Mobilization |  |  | 1432.5821
[5 empty] | Subtotal: | 30084.2242
|  |  | 15% Contractor overhead: |  |  | 4512.6336
[5 empty] | Subtotal: | 34596.8578
|  |  | 10% Contractor profit: |  |  | 3459.6858
|  |  | Total pipeline contractor costs: |  |  | 38056.5436
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 6
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 3600
| Total pipeline contractor and company inspection cost per cased road crossing: |  |  |  |  | 41656.5436
|  | No. of cased highway crossings: |  |  |  | 35
| Item C. | Total estimated cost to retire cased highway crossings: |  |  |  | 1457979.0265
|  | No. of cased railroad crossings: |  |  |  | 4
| Item D. | Total estimated cost to retire cased railroad crossings: |  |  |  | 166626.1745

## Small Stream Crossing
Exhibit No. DCP-29
Page 15 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
E. Small stream crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a small stream crossing (100 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with concrete
or grout, backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (1 day)
Equipment |  |  | No. | Hours | Rate | Total
dozer, cat D-6 |  |  | 1 | 8 | 76.8792 | 615.0336
lowboy |  |  | 1 | 8 | 51.1601 | 409.2808
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
3/4 ton pick-up with trailer |  |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 55.6949
[5 empty] | Subtotal: | 1542.4381
Labor |  |  | No. | Hours | Rate | Total
operator (dozer) |  |  | 1 | 8 | 37.23 | 297.84
teamster |  |  | 2 | 8 | 37.23 | 595.68
pipefitter/welder |  |  | 1 | 8 | 52.0455 | 416.364
helper |  |  | 1 | 8 | 36.4318 | 291.4548
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 2784.7428
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 55.6949
[5 empty] | Subtotal: | 55.6949
|  |  | Total Direct Costs (1) = |  |  | 4382.8757
2. Excavate and cap pipe ends (2 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor | [5 empty] | 111.3897
[5 empty] | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 16 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. E. Small stream crossings (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 16 | 37.23 | 595.68
teamster |  |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  |  | 1 | 16 | 52.0455 | 832.728
helper |  |  | 1 | 16 | 36.4318 | 582.9096
laborer |  |  | 4 | 16 | 23.6513 | 1513.68
foreman |  |  | 1 | 16 | 53.3205 | 853.128
[5 empty] | Subtotal: | 5569.4856
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 111.3897
[5 empty] | Subtotal: | 111.3897
|  |  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
dump truck 8 cy |  |  | 1 | 8 | 21.6815 | 173.452
concrete pump, trailer mounted |  |  | 1 | 8 | 13.2355 | 105.884
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 35.5817
[5 empty] | Subtotal: | 977.6609
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1779.084
Material | [5 empty] | Total
Concrete @ $88/cy (estimate 30 cy) | [5 empty] | 2640
Sales tax (5%) | [5 empty] | 132
Miscellaneous (2% of labor) | [5 empty] | 35.5817
[5 empty] | Subtotal: | 2807.5817
|  |  | Total Direct Costs (3) = |  |  | 5564.3266
Exhibit No. DCP-29
Page 17 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. E. Small stream crossings (continued)
4. Restore Site (1 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 29.6249
[5 empty] | Subtotal: | 339.0369
Labor |  |  | No. | Hours | Rate | Total
teamster (flatbed) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1481.244
Material | [5 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 1000
[5 empty] | Subtotal: | 1000
|  |  | Total Direct Costs (4) = |  |  | 2820.2809
Summary: Small Stream Crossings
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites | [5 empty] | 4382.8757
2. Excavate and cap pipe ends | [5 empty] | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area | [5 empty] | 5564.3266
4. Restore Site | [5 empty] | 2820.2809
|  |  | Pipeline contractor direct costs: |  |  | 21360.689
|  |  | 5% Mobilization |  |  | 1068.0344
[5 empty] | Subtotal: | 22428.7234
|  |  | 15% Contractor overhead: |  |  | 3364.3085
[5 empty] | Subtotal: | 25793.0319
|  |  | 10% Contractor profit: |  |  | 2579.3032
|  |  | Total pipeline contractor costs: |  |  | 28372.3351
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 5
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 3000
| Total pipeline contractor and company inspection cost per small stream: |  |  |  |  | 31372.3351
|  | No. of small stream crossings: |  |  |  | 27
|  | Total estimated cost to retire small stream crossings: |  |  |  | 847053.0486

## Hunting Creek
Exhibit No. DCP-29
Page 18 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
F. River crossings
1. Hunting Creek
Description of Work:
Detailed cost estimate below reflects work required to retire Hunting Creek river crossing (711 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with grout,
backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (2 days)
Equipment |  | No. | Hours | Rate | Total
dozer, cat D-6 |  | 1 | 16 | 76.8792 | 1230.0672
lowboy |  | 1 | 16 | 51.1601 | 818.5616
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 3084.8761
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (1) = |  |  | 8765.7514
2. Excavate and cap pipe ends (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 19 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 1. Hunting Creek (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 8 cy |  | 1 | 16 | 21.6815 | 346.904
concrete pump, trailer mounted |  | 1 | 16 | 54.8269 | 877.2304
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 71.1634
|  |  |  | Subtotal: | 2620.7842
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster (dump) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 3558.168
Material |  |  |  |  | Total
Concrete @ $88/cy (186 cy) |  |  |  |  | 16368
Sales tax @ 5% |  |  |  |  | 818.4
Miscellaneous (2% of labor) |  |  |  |  | 71.1634
|  |  |  | Subtotal: | 17257.5634
|  | Total Direct Costs (3) = |  |  | 23436.5155
Exhibit No. DCP-29
Page 20 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 1. Hunting Creek (continued)
4. Restore Site (2 days)
Equipment |  | No. | Hours | Rate | Total
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 59.2498
|  |  |  | Subtotal: | 678.0738
Labor |  | No. | Hours | Rate | Total
teamster (flatbed) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 2962.488
Material |  |  |  |  | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 2000
|  |  |  | Subtotal: | 2000
|  | Total Direct Costs (4) = |  |  | 5640.5618
Summary: Hunting Creek River Crossing
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites |  |  |  |  | 8765.7514
2. Excavate and cap pipe ends |  |  |  |  | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area |  |  |  |  | 23436.5155
4. Restore Site |  |  |  |  | 5640.5618
|  | Pipeline contractor direct costs: |  |  | 46436.0345
|  | 5% Mobilization |  |  | 2321.8017
|  |  |  | Subtotal: | 48757.8363
|  | 15% Contractor overhead: |  |  | 7313.6754
|  |  |  | Subtotal: | 56071.5117
|  | 10% Contractor profit: |  |  | 5607.1512
|  | Total pipeline contractor costs: |  |  | 61678.6629
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 8
2. Company cost per day |  |  |  |  | 600
|  | Total company inspection cost per site: |  |  | 4800
| Total pipeline contractor and company inspection cost Hunting Creek river crossing: |  |  |  | 66478.6629

## St. Leonards Creek
Exhibit No. DCP-29
Page 21 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
F. River crossings
2. St. Leonards Creek
Description of Work:
Detailed cost estimate below reflects work required to retire St. Leonards Creek river crossing (1450 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with concrete or grout,
backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (2 days)
Equipment |  | No. | Hours | Rate | Total
dozer, cat D-6 |  | 1 | 16 | 76.8792 | 1230.0672
lowboy |  | 1 | 16 | 51.1601 | 818.5616
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 3084.8761
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (1) = |  |  | 8765.7514
2. Excavate and cap pipe ends (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 22 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 2. St. Leonards Creek (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 8 cy |  | 1 | 16 | 21.6815 | 346.904
concrete pump, trailer mounted |  | 1 | 16 | 54.8269 | 877.2304
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 83.077
|  |  |  | Subtotal: | 2632.6978
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
operator (concrete pump) |  | 1 | 16 | 37.23 | 595.68
teamster (dump) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 4153.848
Material |  |  |  |  | Total
Concrete @ $88/cy (380 cy) |  |  |  |  | 33440
Sales tax @ 5% |  |  |  |  | 1672
Miscellaneous (2% of labor) |  |  |  |  | 83.077
|  |  |  | Subtotal: | 35195.077
|  | Total Direct Costs (3) = |  |  | 41981.6227
Exhibit No. DCP-29
Page 23 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 2. St. Leonards Creek (continued)
4. Restore Site (2 days)
Equipment |  | No. | Hours | Rate | Total
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 59.2498
|  |  |  | Subtotal: | 678.0738
Labor |  | No. | Hours | Rate | Total
teamster (flatbed) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 2962.488
Material |  |  |  |  | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 2000
|  |  |  | Subtotal: | 2000
|  | Total Direct Costs (4) = |  |  | 5640.5618
Summary: St. Leonards Creek River Crossing
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites |  |  |  |  | 8765.7514
2. Excavate and cap pipe ends |  |  |  |  | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area |  |  |  |  | 41981.6227
4. Restore Site |  |  |  |  | 5640.5618
|  | Pipeline contractor direct costs: |  |  | 64981.1417
|  | 5% Mobilization |  |  | 3249.0571
|  |  |  | Subtotal: | 68230.1988
|  | 15% Contractor overhead: |  |  | 10234.5298
|  |  |  | Subtotal: | 78464.7286
|  | 10% Contractor profit: |  |  | 7846.4729
|  | Total pipeline contractor costs: |  |  | 86311.2015
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 8
2. Company cost per day |  |  |  |  | 600
|  | Total company inspection cost per site: |  |  | 4800
| Total pipeline contractor and company inspection cost St. Leonards Creek river crossing: |  |  |  | 91111.2015

## Patuxent River
Exhibit No. DCP-29
Page 24 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
F. River crossings
3. Patuxent River
Description of Work:
Detailed cost estimate below reflects work required to retire Patuxent River crossing (4658 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with concrete or
grout, backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (2 days)
Equipment |  | No. | Hours | Rate | Total
dozer, cat D-6 |  | 1 | 16 | 76.8792 | 1230.0672
lowboy |  | 1 | 16 | 51.1601 | 818.5616
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 3084.8761
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (1) = |  |  | 8765.7514
2. Excavate and cap pipe ends (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 25 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 3. Patuxent River (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (3 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 8 cy |  | 1 | 16 | 21.6815 | 346.904
concrete pump, trailer mounted |  | 1 | 24 | 54.8269 | 1315.8456
lights, trailer mounted |  | 1 | 8 | 5.7165 | 45.732
1/2 ton pickup with 4wd |  | 2 | 40 | 8.3739 | 669.912
small tools, 2% of labor |  |  |  |  | 160.038
|  |  |  | Subtotal: | 3595.9532
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
operator (grout pump, 3 shifts for 1 day) |  | 3 | 8 | 37.23 | 893.52
teamster (dump) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
laborer (grouting operation, 3 shifts for 1 day) |  | 12 | 8 | 23.6513 | 2270.52
foreman |  | 1 | 16 | 53.3205 | 853.128
foreman (grouting operation, 3 shifts for 1 day) |  | 3 | 8 | 53.3205 | 1279.692
|  |  |  | Subtotal: | 8001.9
Material |  |  |  |  | Total
Concrete @ $88/cy (1219 cy) |  |  |  |  | 107272
Sales tax @ 5% |  |  |  |  | 5363.6
Miscellaneous (2% of labor) |  |  |  |  | 160.038
|  |  |  | Subtotal: | 112795.638
|  | Total Direct Costs (3) = |  |  | 124393.4912
Exhibit No. DCP-29
Page 26 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 3. Patuxent River (continued)
4. Restore Site (2 days)
Equipment |  | No. | Hours | Rate | Total
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 59.2498
|  |  |  | Subtotal: | 678.0738
Labor |  | No. | Hours | Rate | Total
teamster (flatbed) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 2962.488
Material |  |  |  |  | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 2000
|  |  |  | Subtotal: | 2000
|  | Total Direct Costs (4) = |  |  | 5640.5618
Summary: Patuxent River Crossing
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites |  |  |  |  | 8765.7514
2. Excavate and cap pipe ends |  |  |  |  | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area |  |  |  |  | 124393.4912
4. Restore Site |  |  |  |  | 5640.5618
|  | Pipeline contractor direct costs: |  |  | 147393.0102
|  | 5% Mobilization |  |  | 7369.6505
|  |  |  | Subtotal: | 154762.6607
|  | 15% Contractor overhead: |  |  | 23214.3991
|  |  |  | Subtotal: | 177977.0598
|  | 10% Contractor profit: |  |  | 17797.706
|  | Total pipeline contractor costs: |  |  | 195774.7658
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 9
2. Company cost per day |  |  |  |  | 600
|  | Total company inspection cost per site: |  |  | 5400
| Total pipeline contractor and company inspection cost Patuxent River crossing: |  |  |  | 201174.7658

## Potomac River
Exhibit No. DCP-29
Page 27 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
F. River Crossings
4. Potomac River
Description of Work:
Detailed cost estimate below reflects work required to retire Potomac River crossing (20125 feet).
Work includes R.O.W. fence removal, excavation, capping pipe ends, filling pipe with concrete or
grout, backfilling, and restoration of area.
1. Remove R.O.W. Fence and access work sites (2 days)
Equipment |  | No. | Hours | Rate | Total
dozer, cat D-6 |  | 1 | 16 | 76.8792 | 1230.0672
lowboy |  | 1 | 16 | 51.1601 | 818.5616
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 3084.8761
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (1) = |  |  | 8765.7514
2. Excavate and cap pipe ends (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
lowboy |  | 1 | 16 | 51.1601 | 818.5616
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 2912.3305
Exhibit No. DCP-29
Page 28 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 4. Potomac River (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 2 | 16 | 37.23 | 1191.36
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 5569.4856
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 111.3897
|  |  |  | Subtotal: | 111.3897
|  | Total Direct Costs (2) = |  |  | 8593.2058
3. Fill pipe with concrete or grout, backfill trench, grade disturbed area (5 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 8 cy |  | 1 | 16 | 21.6815 | 346.904
concrete pump, trailer mounted |  | 1 | 96 | 54.8269 | 5263.3824
lights, trailer mounted |  | 1 | 32 | 5.7165 | 182.928
1/2 ton pickup with 4wd |  | 2 | 96 | 8.3739 | 1607.7888
small tools, 2% of labor |  |  |  |  | 402.9938
|  |  |  | Subtotal: | 8861.5186
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
operator (grouting operation, 3 shifts for 4 days) |  | 3 | 32 | 37.23 | 3574.08
teamster (dump) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 8 | 23.6513 | 756.84
laborer (grouting operation, 3 shifts for 4 days) |  | 12 | 32 | 23.6513 | 9082.08
foreman |  | 1 | 8 | 53.3205 | 426.564
foreman (grouting operation, 3 shifts for 4 days) |  | 3 | 32 | 53.3205 | 5118.768
|  |  |  | Subtotal: | 20149.692
Material |  |  |  |  | Total
Concrete @ $88/cy (5268 cy) |  |  |  |  | 463584
Sales tax @ 5% |  |  |  |  | 23179.2
Miscellaneous (2% of labor) |  |  |  |  | 402.9938
|  |  |  | Subtotal: | 487166.1938
|  | Total Direct Costs (3) = |  |  | 516177.4045
Exhibit No. DCP-29
Page 29 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. F. 4. Potomac River (continued)
4. Restore Site (2 days)
Equipment |  | No. | Hours | Rate | Total
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 59.2498
|  |  |  | Subtotal: | 678.0738
Labor |  | No. | Hours | Rate | Total
teamster (flatbed) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 2962.488
Material |  |  |  |  | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 2000
|  |  |  | Subtotal: | 2000
|  | Total Direct Costs (4) = |  |  | 5640.5618
Summary: Potomac River Crossing
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work sites |  |  |  |  | 8765.7514
2. Excavate and cap pipe ends |  |  |  |  | 8593.2058
3. Fill casing with concrete or grout, backfill trench, grade disturbed area |  |  |  |  | 516177.4045
4. Restore Site |  |  |  |  | 5640.5618
|  | Pipeline contractor direct costs: |  |  | 539176.9235
|  | 5% Mobilization |  |  | 26958.8462
|  |  |  | Subtotal: | 566135.7697
|  | 15% Contractor overhead: |  |  | 84920.3654
|  |  |  | Subtotal: | 651056.1351
|  | 10% Contractor profit: |  |  | 65105.6135
|  | Total pipeline contractor costs: |  |  | 716161.7486
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 11
2. Company cost per day |  |  |  |  | 600
|  | Total company inspection cost per site: |  |  | 6600
| Total pipeline contractor and company inspection cost Potomac River crossing: |  |  |  | 722761.7486

## Remote Mainline Valve
Exhibit No. DCP-29
Page 30 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline retirement
G. Remote mainline valves
Description of Work:
Detailed cost estimate below reflects work required to retire a remote 36" mainline valve.
Work includes R.O.W. fence removal, excavation, removal of valves and blowdowns,
capping pipelines, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 4 | 66.0951 | 264.3804
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
3/4 ton pick-up with trailer |  |  | 1 | 4 | 19.1271 | 76.5084
1/2 ton pickup with 4wd |  |  | 2 | 4 | 8.3739 | 66.9912
small tools, 2% of labor | [5 empty] | 24.869
[5 empty] | Subtotal: | 520.4638
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 4 | 37.23 | 148.92
teamster |  |  | 1 | 4 | 37.23 | 148.92
pipefitter/welder |  |  | 1 | 4 | 52.0455 | 208.182
helper |  |  | 1 | 4 | 36.4318 | 145.7274
laborer |  |  | 4 | 4 | 23.6513 | 378.42
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 1243.4514
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 24.869
[5 empty] | Subtotal: | 24.869
|  |  | Total Direct Costs (1) = |  |  | 1788.7843
2. Excavate, remove valves and blowdowns, cap pipe ends (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
crane, Grove 25 ton |  |  | 1 | 8 | 49.234 | 393.872
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
pipe truck |  |  | 1 | 8 | 45.6805 | 365.444
lowboy |  |  | 1 | 8 | 51.1601 | 409.2808
3/4 ton pick-up with trailer |  |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 68.4265
[5 empty] | Subtotal: | 2228.2129
Exhibit No. DCP-29
Page 31 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. G. Remote mainline valves (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
operator (crane) |  |  | 1 | 8 | 42.3428 | 338.742
teamster |  |  | 3 | 8 | 37.23 | 893.52
pipefitter/welder |  |  | 1 | 8 | 52.0455 | 416.364
helper |  |  | 1 | 8 | 36.4318 | 291.4548
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 3421.3248
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 68.4265
[5 empty] | Subtotal: | 68.4265
|  |  | Total Direct Costs (2) = |  |  | 5717.9642
3. Remove gravel and miscellaneous debris, grade disturbed area (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
dump truck 8 cy |  |  | 1 | 8 | 21.6815 | 173.452
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 35.5817
[5 empty] | Subtotal: | 871.7769
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1779.084
Material | [5 empty] | Total
Miscellaneous (2% of labor) | [5 empty] | 35.5817
[5 empty] | Subtotal: | 35.5817
|  |  | Total Direct Costs (3) = |  |  | 2686.4426
Exhibit No. DCP-29
Page 32 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. G. Remote mainline valves (continued)
4. Restore Site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
1/2 ton pickup with 4wd |  |  | 2 | 4 | 8.3739 | 66.9912
small tools, 2% of labor | [5 empty] | 14.8124
[5 empty] | Subtotal: | 169.5184
Labor |  |  | No. | Hours | Rate | Total
teamster (flatbed) |  |  | 1 | 4 | 37.23 | 148.92
laborer |  |  | 4 | 4 | 23.6513 | 378.42
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 740.622
Material | [5 empty] | Total
allow $ 1000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 1000
[5 empty] | Subtotal: | 1000
|  |  | Total Direct Costs (4) = |  |  | 1910.1404
Summary: Remote Mainline Valves
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site | [5 empty] | 1788.7843
2. Excavate, remove valves and blowdowns, cap pipe ends | [5 empty] | 5717.9642
3. Remove gravel and miscellaneous debris | [5 empty] | 2686.4426
4. Restore Site | [5 empty] | 1910.1404
|  |  | Pipeline contractor direct costs: |  |  | 12103.3314
|  |  | 5% Mobilization |  |  | 605.1666
[5 empty] | Subtotal: | 12708.498
|  |  | 15% Contractor overhead: |  |  | 1906.2747
[5 empty] | Subtotal: | 14614.7727
|  |  | 10% Contractor profit: |  |  | 1461.4773
|  |  | Total pipeline contractor costs: |  |  | 16076.25
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 3
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 1800
| Total pipeline contractor and company inspection cost mainline valve: |  |  |  |  | 17876.25
|  | No. of remote mainline valves: |  |  |  | 13
|  | Total estimated cost to retire mainline valves: |  |  |  | 232391.2499

## Pipeline Drip
Exhibit No. DCP-29
Page 33 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
H. Pipeline drips
Description of Work:
Detailed cost estimate below reflects work required to retire a pipeline drip.
Work includes R.O.W. fence removal, excavation, removal of section of pipeline and drip tank,
capping pipelines, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 4 | 66.0951 | 264.3804
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
3/4 ton pick-up with trailer |  |  | 1 | 4 | 19.1271 | 76.5084
1/2 ton pickup with 4wd |  |  | 2 | 4 | 8.3739 | 66.9912
small tools, 2% of labor | [5 empty] | 24.869
[5 empty] | Subtotal: | 520.4638
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 4 | 37.23 | 148.92
teamster |  |  | 1 | 4 | 37.23 | 148.92
pipefitter/welder |  |  | 1 | 4 | 52.0455 | 208.182
helper |  |  | 1 | 4 | 36.4318 | 145.7274
laborer |  |  | 4 | 4 | 23.6513 | 378.42
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 1243.4514
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 24.869
[5 empty] | Subtotal: | 24.869
|  |  | Total Direct Costs (1) = |  |  | 1788.7843
2. Excavate, remove section of pipeline and drip tank, cap pipe ends (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
hydrocrane, Grove 25 ton |  |  | 1 | 8 | 49.234 | 393.872
pipe truck |  |  | 1 | 8 | 45.6805 | 365.444
flatbed truck |  |  | 1 | 8 | 21.9287 | 175.4296
lowboy |  |  | 1 | 8 | 51.1601 | 409.2808
3/4 ton pick-up with trailer |  |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 68.4265
[5 empty] | Subtotal: | 2228.2129
Exhibit No. DCP-29
Page 34 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. H. Pipeline drips (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
operator (hydrocrane) |  |  | 1 | 8 | 42.3428 | 338.742
teamster |  |  | 3 | 8 | 37.23 | 893.52
pipefitter/welder |  |  | 1 | 8 | 52.0455 | 416.364
helper |  |  | 1 | 8 | 36.4318 | 291.4548
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 3421.3248
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 68.4265
[5 empty] | Subtotal: | 68.4265
|  |  | Total Direct Costs (2) = |  |  | 5717.9642
3. Remove gravel and miscellaneous debris, grade disturbed area (1 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 8 | 66.0951 | 528.7608
dump truck 12 cy |  |  | 1 | 8 | 34.5359 | 276.2872
1/2 ton pickup with 4wd |  |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor | [5 empty] | 35.5817
[5 empty] | Subtotal: | 974.6121
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  |  | 1 | 8 | 37.23 | 297.84
laborer |  |  | 4 | 8 | 23.6513 | 756.84
foreman |  |  | 1 | 8 | 53.3205 | 426.564
[5 empty] | Subtotal: | 1779.084
Material | [5 empty] | Total
Miscellaneous (2% of labor) | [5 empty] | 35.5817
[5 empty] | Subtotal: | 35.5817
|  |  | Total Direct Costs (3) = |  |  | 2789.2778
Exhibit No. DCP-29
Page 35 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. H. Pipeline drips (continued)
4. Restore Site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
1/2 ton pickup with 4wd |  |  | 2 | 4 | 8.3739 | 66.9912
small tools, 2% of labor | [5 empty] | 14.8124
[5 empty] | Subtotal: | 169.5184
Labor |  |  | No. | Hours | Rate | Total
teamster (flatbed) |  |  | 1 | 4 | 37.23 | 148.92
laborer |  |  | 4 | 4 | 23.6513 | 378.42
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 740.622
Material | [5 empty] | Total
allow $ 1000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 1000
[5 empty] | Subtotal: | 1000
|  |  | Total Direct Costs (4) = |  |  | 1910.1404
Summary: Pipeline Drips
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site | [5 empty] | 1788.7843
2. Excavate, remove section of pipeline and drip tank, cap pipe ends | [5 empty] | 5717.9642
3. Remove gravel and miscellaneous debris | [5 empty] | 2789.2778
4. Restore Site | [5 empty] | 1910.1404
|  |  | Pipeline contractor direct costs: |  |  | 12206.1666
|  |  | 5% Mobilization |  |  | 610.3083
[5 empty] | Subtotal: | 12816.475
|  |  | 15% Contractor overhead: |  |  | 1922.4712
[5 empty] | Subtotal: | 14738.9462
|  |  | 10% Contractor profit: |  |  | 1473.8946
|  |  | Total pipeline contractor costs: |  |  | 16212.8409
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 3
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 1800
| Total pipeline contractor and company inspection cost pipeline drip: |  |  |  |  | 18012.8409
|  | No. of pipeline drips: |  |  |  | 3
|  | Total estimated cost to retire pipeline drips: |  |  |  | 54038.5226

## Cathodic Protection
Exhibit No. DCP-29
Page 36 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
I. Cathodic protection facilities
Description of Work:
Detailed cost estimate below reflects work required to remove cathodic protection
surface facilities and ground bed facilities. Work includes fence removal, removal of
electrical equipment, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
1/2 ton pickup with 4wd |  |  | 1 | 4 | 8.3739 | 33.4956
small tools, 2% of labor | [5 empty] | 11.0282
[5 empty] | Subtotal: | 132.2386
Labor |  |  | No. | Hours | Rate | Total
teamster |  |  | 1 | 4 | 37.23 | 148.92
laborer |  |  | 2 | 4 | 23.6513 | 189.21
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 551.412
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 11.0282
[5 empty] | Subtotal: | 11.0282
|  |  | Total Direct Costs (1) = |  |  | 694.6789
2. Remove electrical equipment, and ground bed facility (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C |  |  | 1 | 4 | 30.179 | 120.716
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
lowboy |  |  | 1 | 4 | 51.1601 | 204.6404
3/4 ton pick-up with trailer |  |  | 1 | 4 | 19.1271 | 76.5084
1/2 ton pickup with 4wd |  |  | 1 | 4 | 8.3739 | 33.4956
small tools, 2% of labor | [5 empty] | 23.6263
[5 empty] | Subtotal: | 546.7015
Exhibit No. DCP-29
Page 37 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. I. Cathodic protection facilities (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 4 | 37.23 | 148.92
teamster |  |  | 2 | 4 | 37.23 | 297.84
electrician |  |  | 1 | 4 | 48.8325 | 195.33
helper |  |  | 1 | 4 | 34.1827 | 136.731
laborer |  |  | 2 | 4 | 23.6513 | 189.21
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 1181.313
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 23.6263
[5 empty] | Subtotal: | 23.6263
|  |  | Total Direct Costs (2) = |  |  | 1751.6407
3. Remove gravel and miscellaneous debris (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C |  |  | 1 | 4 | 30.179 | 120.716
dump truck 8 cy |  |  | 1 | 4 | 21.6815 | 86.726
1/2 ton pickup with 4wd |  |  | 1 | 4 | 8.3739 | 33.4956
small tools, 2% of labor | [5 empty] | 14.0066
[5 empty] | Subtotal: | 254.9442
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 4 | 37.23 | 148.92
teamster (dump) |  |  | 1 | 4 | 37.23 | 148.92
laborer |  |  | 2 | 4 | 23.6513 | 189.21
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 700.332
Material | [5 empty] | Total
Miscellaneous (2% of labor) | [5 empty] | 14.0066
[5 empty] | Subtotal: | 14.0066
|  |  | Total Direct Costs (3) = |  |  | 969.2829
Exhibit No. DCP-29
Page 38 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. I. Cathodic protection facilities (continued)
4. Restore Site (1/2 day)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 312C |  |  | 1 | 4 | 30.179 | 120.716
flatbed truck |  |  | 1 | 4 | 21.9287 | 87.7148
1/2 ton pickup with 4wd |  |  | 1 | 4 | 8.3739 | 33.4956
small tools, 2% of labor | [5 empty] | 14.0066
[5 empty] | Subtotal: | 255.933
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 4 | 37.23 | 148.92
teamster (flatbed) |  |  | 1 | 4 | 37.23 | 148.92
laborer |  |  | 2 | 4 | 23.6513 | 189.21
foreman |  |  | 1 | 4 | 53.3205 | 213.282
[5 empty] | Subtotal: | 700.332
Material | [5 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 1000
[5 empty] | Subtotal: | 1000
|  |  | Total Direct Costs (4) = |  |  | 1956.265
Summary: Cathodic Protection Facilities
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site | [5 empty] | 694.6789
2. Remove electrical equipment and ground bed facility | [5 empty] | 1751.6407
3. Remove gravel and miscellaneous debris | [5 empty] | 969.2829
4. Restore Site | [5 empty] | 1956.265
|  |  | Pipeline contractor direct costs: |  |  | 5371.8675
|  |  | 5% Mobilization |  |  | 268.5934
[5 empty] | Subtotal: | 5640.4609
|  |  | 15% Contractor overhead: |  |  | 846.0691
[5 empty] | Subtotal: | 6486.53
|  |  | 10% Contractor profit: |  |  | 648.653
|  |  | Total pipeline contractor costs: |  |  | 7135.183
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 2
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost per site: |  |  | 1200
| Total pipeline contractor and company inspection cost cathodic protection: |  |  |  |  | 8335.183
|  | No. of cathodic protection sites: |  |  |  | 3
|  | Total estimated cost to retire cathodic protection sites: |  |  |  | 25005.5491

## Pipeline Marker
Exhibit No. DCP-29
Page 39 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
J. Pipeline markers
Description of Work:
Detailed cost estimate below reflects work required to remove a pipeline marker.
1. Remove pipeline marker
Equipment |  |  | No. | Hours | Rate | Total
1/2 ton pickup with 4wd |  |  | 1 | 0.25 | 8.3739 | 2.0935
small tools, 2% of labor | [5 empty] | 0.50311
[5 empty] | Subtotal: | 2.5966
Labor |  |  | No. | Hours | Rate | Total
laborer |  |  | 2 | 0.25 | 23.6513 | 11.8256
foreman |  |  | 1 | 0.25 | 53.3205 | 13.3301
[5 empty] | Subtotal: | 25.1558
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 0.50311
[5 empty] | Subtotal: | 0.50311
|  |  | Total Direct Costs (1) = |  |  | 28.2555
Summary: Pipeline Markers
1. Remove pipeline marker | [5 empty] | 28.2555
|  |  | Pipeline Contractor Direct Costs: |  |  | 28.2555
|  |  | 5% Mobilization |  |  | 1.4128
[5 empty] | Subtotal: | 29.6682
|  |  | 15% Contractor Overhead: |  |  | 4.4502
[5 empty] | Subtotal: | 34.1185
|  |  | 10% Contractor Profit: |  |  | 3.4118
|  |  | Total Pipeline Contractor Costs: |  |  | 37.5303
Estimate number of pipeline markers based on one marker per 200 feet of pipeline.
Total
[5 empty] | Pipeline | Calculated
[5 empty] | Length | No. of
[5 empty] | (ft) | Markers
[5 empty] | 476742.52 | 2383.7126
|  | Total estimated cost to remove pipeline markers: |  |  |  | 89461.4683

## Loudon M&R
Exhibit No. DCP-29
Page 40 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
K. M&R stations
1. Loudon M&R station
Description of Work:
Detailed cost estimate below reflects work required to retire the Loudon M&R station.
Work includes R.O.W. fence removal, excavation, removal of valves, blowdowns and meter runs,
removal of control buildings, capping pipelines, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 99.4761
|  |  |  | Subtotal: | 2081.8553
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 1 | 16 | 37.23 | 595.68
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 4973.8056
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 99.4761
|  |  |  | Subtotal: | 99.4761
|  | Total Direct Costs (1) = |  |  | 7155.137
2. Excavate, remove valves, blowdowns, cap pipe ends, demolish control bldgs and meter runs (20 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 160 | 66.0951 | 10575.216
bobcat |  | 1 | 160 | 11.4227 | 1827.632
hydrocrane, Grove 30 ton |  | 1 | 160 | 54.8269 | 8772.304
flatbed truck |  | 2 | 160 | 21.9287 | 7017.184
lowboy (part time) |  | 1 | 80 | 51.1601 | 4092.808
3/4 ton pick-up with trailer |  | 4 | 160 | 19.1271 | 12241.344
1/2 ton pickup with 4wd |  | 4 | 160 | 8.3739 | 5359.296
small tools, 2% of labor |  |  |  |  | 2580.2165
|  |  |  | Subtotal: | 52466.0005
Exhibit No. DCP-29
Page 41 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 1. Loudon M&R station (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 2 | 160 | 37.23 | 11913.6
operator (hydrocrane) |  | 1 | 160 | 42.3428 | 6774.84
teamster (flatbed truck) |  | 2 | 160 | 37.23 | 11913.6
teamster (lowboy) |  | 1 | 80 | 37.23 | 2978.4
pipefitter/welder |  | 4 | 160 | 52.0455 | 33309.12
helper |  | 4 | 160 | 36.4318 | 23316.384
laborer |  | 8 | 160 | 23.6513 | 30273.6
foreman |  | 1 | 160 | 53.3205 | 8531.28
|  |  |  | Subtotal: | 129010.824
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 2580.2165
|  |  |  | Subtotal: | 2580.2165
|  | Total Direct Costs (2) = |  |  | 184057.041
3. Remove gravel and miscellaneous debris (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
dump truck 12 cy |  | 2 | 16 | 34.5359 | 1105.1488
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 83.077
|  |  |  | Subtotal: | 2513.7122
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster (dump) |  | 2 | 16 | 37.23 | 1191.36
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 4153.848
Material |  |  |  |  | Total
Miscellaneous (2% of labor) |  |  |  |  | 83.077
|  |  |  | Subtotal: | 83.077
|  | Total Direct Costs (3) = |  |  | 6750.6371
Exhibit No. DCP-29
Page 42 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 1. Loudon M&R station (continued)
4. Restore Site (2 days)
Equipment |  | No. | Hours | Rate | Total
motor grader, Cat 135H |  | 1 | 16 | 36.7195 | 587.512
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 71.1634
|  |  |  | Subtotal: | 1277.4994
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster (flatbed) |  | 1 | 16 | 37.23 | 595.68
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 3558.168
Material |  |  |  |  | Total
allow $ 10,000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 10000
Sales tax @ 5% |  |  |  |  | 500
|  |  |  | Subtotal: | 10500
|  | Total Direct Costs (4) = |  |  | 15335.6674
Summary: Retire Loudon M&R Station
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site |  |  |  |  | 7155.137
2. Excavate, remove valves and blowdowns, cap pipe ends |  |  |  |  | 184057.041
3. Remove gravel and miscellaneous debris |  |  |  |  | 6750.6371
4. Restore Site |  |  |  |  | 15335.6674
|  | Pipeline contractor direct costs: |  |  | 213298.4825
|  | 5% Mobilization |  |  | 10664.9241
|  |  |  | Subtotal: | 223963.4066
|  | 15% Contractor overhead: |  |  | 33594.511
|  |  |  | Subtotal: | 257557.9176
|  | 10% Contractor profit: |  |  | 25755.7918
|  | Total pipeline contractor costs: |  |  | 283313.7093
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 26
2. Company cost per day |  |  |  |  | 600
|  | Total company inspection cost per site: |  |  | 15600
| Total pipeline contractor and company inspection Loudon M&R station: |  |  |  | 298913.7093

## Pleasant Valley M&R
Exhibit No. DCP-29
Page 43 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
K. M&R stations
2. Pleasant Valley M&R station
Description of Work:
Detailed cost estimate below reflects work required to retire the Pleasant Valley M&R station.
Work includes R.O.W. fence removal, excavation, removal of valves, heaters, blowdowns and meter runs,
removal of control building, capping pipelines, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (1 day)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 8 | 66.0951 | 528.7608
flatbed truck |  | 1 | 8 | 21.9287 | 175.4296
3/4 ton pick-up with trailer |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 49.7381
|  |  |  | Subtotal: | 1040.9277
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster |  | 1 | 8 | 37.23 | 297.84
pipefitter/welder |  | 1 | 8 | 52.0455 | 416.364
helper |  | 1 | 8 | 36.4318 | 291.4548
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 2486.9028
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 49.7381
|  |  |  | Subtotal: | 49.7381
|  | Total Direct Costs (1) = |  |  | 3577.5685
2. Excavate, remove valves and blowdowns, cap pipe ends, demolish control bldg, remove small tanks
and meter runs (15 days).
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 120 | 66.0951 | 7931.412
bobcat |  | 1 | 120 | 11.4227 | 1370.724
hydrocrane, Grove 30 ton |  | 1 | 120 | 54.8269 | 6579.228
flatbed truck |  | 2 | 120 | 21.9287 | 5262.888
lowboy (part time) |  | 1 | 60 | 51.1601 | 3069.606
3/4 ton pick-up with trailer |  | 2 | 120 | 19.1271 | 4590.504
1/2 ton pickup with 4wd |  | 2 | 120 | 8.3739 | 2009.736
small tools, 2% of labor |  |  |  |  | 1283.4191
|  |  |  | Subtotal: | 32097.5171
Exhibit No. DCP-29
Page 44 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 2. Pleasant Valley M&R station (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 2 | 120 | 37.23 | 8935.2
operator (hydrocrane) |  | 1 | 120 | 42.3428 | 5081.13
teamster (flatbed truck) |  | 2 | 120 | 37.23 | 8935.2
teamster (lowboy) |  | 1 | 60 | 37.23 | 2233.8
pipefitter/welder |  | 2 | 120 | 52.0455 | 12490.92
helper |  | 2 | 120 | 36.4318 | 8743.644
laborer |  | 4 | 120 | 23.6513 | 11352.6
foreman |  | 1 | 120 | 53.3205 | 6398.46
|  |  |  | Subtotal: | 64170.954
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 1283.4191
|  |  |  | Subtotal: | 1283.4191
|  | Total Direct Costs (2) = |  |  | 97551.8902
3. Remove gravel and miscellaneous debris (1 day)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 8 | 66.0951 | 528.7608
dump truck 12 cy |  | 2 | 8 | 34.5359 | 552.5744
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 41.5385
|  |  |  | Subtotal: | 1256.8561
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  | 2 | 8 | 37.23 | 595.68
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 2076.924
Material |  |  |  |  | Total
Miscellaneous (2% of labor) |  |  |  |  | 41.5385
|  |  |  | Subtotal: | 41.5385
|  | Total Direct Costs (3) = |  |  | 3375.3186
Exhibit No. DCP-29
Page 45 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 2. Pleasant Valley M&R station (continued)
4. Restore Site (1 day)
Equipment |  | No. | Hours | Rate | Total
motor grader, Cat 135H |  | 1 | 8 | 36.7195 | 293.756
flatbed truck |  | 1 | 8 | 21.9287 | 175.4296
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 35.5817
|  |  |  | Subtotal: | 638.7497
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster (flatbed) |  | 1 | 8 | 37.23 | 297.84
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 1779.084
Material |  |  |  |  | Total
allow $ 5000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 7500
Sales tax @ 5% |  |  |  |  | 375
|  |  |  | Subtotal: | 7875
|  | Total Direct Costs (4) = |  |  | 10292.8337
Summary: Pleasant Valley M&R station
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site |  |  |  |  | 3577.5685
2. Excavate, remove valves and blowdowns, cap pipe ends |  |  |  |  | 97551.8902
3. Remove gravel and miscellaneous debris |  |  |  |  | 3375.3186
4. Restore Site |  |  |  |  | 10292.8337
|  | Pipeline contractor direct costs: |  |  | 114797.6109
|  | 5% Mobilization |  |  | 5739.8805
|  |  |  | Subtotal: | 120537.4915
|  | 15% Contractor overhead: |  |  | 18080.6237
|  |  |  | Subtotal: | 138618.1152
|  | 10% Contractor profit: |  |  | 13861.8115
|  | Total pipeline contractor costs: |  |  | 152479.9267
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 18
2. Company cost per day |  |  |  |  | 600
| Total company inspection cost per site: |  |  |  | 10800
Total pipeline contractor and company inspection Pleasant Valley M&R station: |  |  |  |  | 163279.9267

## Ox M&R
Exhibit No. DCP-29
Page 46 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
K. M&R stations
3. Ox M&R station
Description of Work:
Detailed cost estimate below reflects work required to retire the Ox M&R station.
Work includes R.O.W. fence removal, excavation, removal of valves, blowdowns and meter runs,
removal of control building, capping pipelines, excavation of gravel, and restoration of area.
1. Remove R.O.W. Fence and access work site (1 day)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 8 | 66.0951 | 528.7608
flatbed truck |  | 1 | 8 | 21.9287 | 175.4296
3/4 ton pick-up with trailer |  | 1 | 8 | 19.1271 | 153.0168
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 49.7381
|  |  |  | Subtotal: | 1040.9277
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster |  | 1 | 8 | 37.23 | 297.84
pipefitter/welder |  | 1 | 8 | 52.0455 | 416.364
helper |  | 1 | 8 | 36.4318 | 291.4548
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 2486.9028
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 49.7381
|  |  |  | Subtotal: | 49.7381
|  | Total Direct Costs (1) = |  |  | 3577.5685
2. Excavate, remove valves and blowdowns, cap pipe ends, demolish control bldg, remove small tanks
and meter runs (5 days).
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 40 | 66.0951 | 2643.804
bobcat |  | 1 | 40 | 11.4227 | 456.908
hydrocrane, Grove 30 ton |  | 1 | 40 | 54.8269 | 2193.076
flatbed truck |  | 2 | 40 | 21.9287 | 1754.296
lowboy (part time) |  | 1 | 20 | 51.1601 | 1023.202
3/4 ton pick-up with trailer |  | 2 | 40 | 19.1271 | 1530.168
1/2 ton pickup with 4wd |  | 2 | 40 | 8.3739 | 669.912
small tools, 2% of labor |  |  |  |  | 427.8064
|  |  |  | Subtotal: | 10699.1724
Exhibit No. DCP-29
Page 47 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 3. Ox M&R station (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 2 | 40 | 37.23 | 2978.4
operator (hydrocrane) |  | 1 | 40 | 42.3428 | 1693.71
teamster (flatbed truck) |  | 2 | 40 | 37.23 | 2978.4
teamster (lowboy) |  | 1 | 20 | 37.23 | 744.6
pipefitter/welder |  | 2 | 40 | 52.0455 | 4163.64
helper |  | 2 | 40 | 36.4318 | 2914.548
laborer |  | 4 | 40 | 23.6513 | 3784.2
foreman |  | 1 | 40 | 53.3205 | 2132.82
|  |  |  | Subtotal: | 21390.318
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 427.8064
|  |  |  | Subtotal: | 427.8064
|  | Total Direct Costs (2) = |  |  | 32517.2967
3. Remove gravel and miscellaneous debris (1 day)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 8 | 66.0951 | 528.7608
dump truck 12 cy |  | 2 | 8 | 34.5359 | 552.5744
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 41.5385
|  |  |  | Subtotal: | 1256.8561
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster (dump) |  | 2 | 8 | 37.23 | 595.68
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 2076.924
Material |  |  |  |  | Total
Miscellaneous (2% of labor) |  |  |  |  | 41.5385
|  |  |  | Subtotal: | 41.5385
|  | Total Direct Costs (3) = |  |  | 3375.3186
Exhibit No. DCP-29
Page 48 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. K. 3. Ox M&R station (continued)
4. Restore Site (1 day)
Equipment |  | No. | Hours | Rate | Total
motor grader, Cat 135H |  | 1 | 8 | 36.7195 | 293.756
flatbed truck |  | 1 | 8 | 21.9287 | 175.4296
1/2 ton pickup with 4wd |  | 2 | 8 | 8.3739 | 133.9824
small tools, 2% of labor |  |  |  |  | 35.5817
|  |  |  | Subtotal: | 638.7497
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 8 | 37.23 | 297.84
teamster (flatbed) |  | 1 | 8 | 37.23 | 297.84
laborer |  | 4 | 8 | 23.6513 | 756.84
foreman |  | 1 | 8 | 53.3205 | 426.564
|  |  |  | Subtotal: | 1779.084
Material |  |  |  |  | Total
allow $ 5000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 5000
Sales tax @ 5% |  |  |  |  | 250
|  |  |  | Subtotal: | 5250
|  | Total Direct Costs (4) = |  |  | 7667.8337
Summary: Ox M&R station
A. Pipeline contractor costs
1. Remove R.O.W. fence and access work site |  |  |  |  | 3577.5685
2. Excavate, remove valves and blowdowns, cap pipe ends |  |  |  |  | 32517.2967
3. Remove gravel and miscellaneous debris |  |  |  |  | 3375.3186
4. Restore Site |  |  |  |  | 7667.8337
|  | Pipeline contractor direct costs: |  |  | 47138.0175
|  | 5% Mobilization |  |  | 2356.9009
|  |  |  | Subtotal: | 49494.9183
|  | 15% Contractor overhead: |  |  | 7424.2378
|  |  |  | Subtotal: | 56919.1561
|  | 10% Contractor profit: |  |  | 5691.9156
|  | Total pipeline contractor costs: |  |  | 62611.0717
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 8
2. Company cost per day |  |  |  |  | 600
| Total company inspection cost per site: |  |  |  | 4800
Total pipeline contractor and company inspection Ox M&R station: |  |  |  |  | 67411.0717

## Loudon Comp
Exhibit No. DCP-29
Page 49 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
L. Compressor stations
1. Loudon compressor station
Description of Work:
Detailed cost estimate below reflects work required to retire the Loudon compressor station.
Work includes R.O.W. fence removal, excavation, removal of valves, blowdowns, piping and equipment,
removal of compressor building, maintenance building and control building, capping pipelines, excavation of
concrete foundations, excavation of gravel and asphalt roadway, and restoration of site.
1. Remove R.O.W. Fence and access work site (2 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor | [5 empty] | 99.4761
[5 empty] | Subtotal: | 2081.8553
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 1 | 16 | 37.23 | 595.68
teamster |  |  | 1 | 16 | 37.23 | 595.68
pipefitter/welder |  |  | 1 | 16 | 52.0455 | 832.728
helper |  |  | 1 | 16 | 36.4318 | 582.9096
laborer |  |  | 4 | 16 | 23.6513 | 1513.68
foreman |  |  | 1 | 16 | 53.3205 | 853.128
[5 empty] | Subtotal: | 4973.8056
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 99.4761
[5 empty] | Subtotal: | 99.4761
|  |  | Total Direct Costs (1) = |  |  | 7155.137
2. Excavate, remove valves and blowdowns, remove above ground pipe, cap below ground pipe (15 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  |  | 2 | 120 | 66.0951 | 15862.824
bobcat |  |  | 1 | 120 | 11.4227 | 1370.724
hydrocrane, Grove 30 ton |  |  | 2 | 120 | 54.8269 | 13158.456
flatbed truck |  |  | 2 | 120 | 21.9287 | 5262.888
lowboy (part time) |  |  | 1 | 60 | 51.1601 | 3069.606
3/4 ton pick-up with trailer |  |  | 4 | 120 | 19.1271 | 9181.008
1/2 ton pickup with 4wd |  |  | 4 | 120 | 8.3739 | 4019.472
small tools, 2% of labor | [5 empty] | 2126.137
[5 empty] | Subtotal: | 54051.115
Exhibit No. DCP-29
Page 50 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 1. Loudon compressor station (continued)
Line Item 2 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator (backhoe, bobcat) |  |  | 3 | 120 | 37.23 | 13402.8
operator (hydrocrane) |  |  | 2 | 120 | 42.3428 | 10162.26
teamster (flatbed truck) |  |  | 2 | 120 | 37.23 | 8935.2
teamster (lowboy) |  |  | 1 | 60 | 37.23 | 2233.8
pipefitter/welder |  |  | 4 | 120 | 52.0455 | 24981.84
helper |  |  | 4 | 120 | 36.4318 | 17487.288
laborer |  |  | 8 | 120 | 23.6513 | 22705.2
foreman |  |  | 1 | 120 | 53.3205 | 6398.46
[5 empty] | Subtotal: | 106306.848
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 2126.137
[5 empty] | Subtotal: | 2126.137
|  |  | Total Direct Costs (2) = |  |  | 162484.0999
3. Remove station equipment (15 days)
Equipment |  |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  |  | 1 | 120 | 55.3522 | 6642.264
crane, Grove 50 ton |  |  | 1 | 120 | 105.3999 | 12647.988
flatbed truck |  |  | 1 | 120 | 21.9287 | 2631.444
lowboy (part time) |  |  | 1 | 60 | 51.1601 | 3069.606
3/4 ton pick-up with trailer |  |  | 4 | 120 | 19.1271 | 9181.008
1/2 ton pickup with 4wd |  |  | 4 | 120 | 8.3739 | 4019.472
small tools, 2% of labor | [5 empty] | 1934.1648
[5 empty] | Subtotal: | 40125.9468
Labor |  |  | No. | Hours | Rate | Total
operator (crane) |  |  | 2 | 120 | 42.3428 | 10162.26
teamster (flatbed truck) |  |  | 1 | 120 | 37.23 | 4467.6
teamster (lowboy) |  |  | 1 | 60 | 37.23 | 2233.8
pipefitter/welder |  |  | 4 | 120 | 52.0455 | 24981.84
helper |  |  | 4 | 120 | 32.6018 | 15648.84
laborer |  |  | 8 | 120 | 34.1827 | 32815.44
foreman |  |  | 1 | 120 | 53.3205 | 6398.46
[5 empty] | Subtotal: | 96708.24
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 1934.1648
[5 empty] | Subtotal: | 1934.1648
|  |  | Total Direct Costs (3) = |  |  | 138768.3516
Exhibit No. DCP-29
Page 51 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 1. Loudon compressor station (continued)
4. Remove station buildings (15 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B w grapple |  |  | 2 | 120 | 73.1918 | 17566.032
hydrocrane, 30 ton |  |  | 2 | 120 | 55.3522 | 13284.528
flatbed truck |  |  | 2 | 120 | 21.9287 | 5262.888
lowboy (part time) |  |  | 1 | 40 | 51.1601 | 2046.404
3/4 ton pick-up with trailer |  |  | 4 | 120 | 19.1271 | 9181.008
1/2 ton pickup with 4wd |  |  | 4 | 120 | 8.3739 | 4019.472
small tools, 2% of labor | [5 empty] | 2021.893
[5 empty] | Subtotal: | 53382.225
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 2 | 120 | 37.23 | 8935.2
operator (hydrocrane) |  |  | 2 | 120 | 42.3428 | 10162.26
teamster (flatbed truck) |  |  | 2 | 120 | 37.23 | 8935.2
teamster (lowboy) |  |  | 1 | 40 | 37.23 | 1489.2
pipefitter/welder |  |  | 4 | 120 | 52.0455 | 24981.84
helper |  |  | 4 | 120 | 36.4318 | 17487.288
laborer |  |  | 8 | 120 | 23.6513 | 22705.2
foreman |  |  | 1 | 120 | 53.3205 | 6398.46
[5 empty] | Subtotal: | 101094.648
Material | [5 empty] | Total
allow 2% of labor | [5 empty] | 2021.893
[5 empty] | Subtotal: | 2021.893
|  |  | Total Direct Costs (4) = |  |  | 156498.7659
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (15 days)
Equipment |  |  | No. | Hours | Rate | Total
backhoe, Cat 325B w hammer |  |  | 3 | 120 | 78.7332 | 28343.952
backhoe, Cat 325B |  |  | 1 | 120 | 66.0951 | 7931.412
dump truck 12 cy |  |  | 2 | 120 | 34.5359 | 8288.616
3/4 ton pick-up with trailer |  |  | 2 | 120 | 19.1271 | 4590.504
1/2 ton pickup with 4wd |  |  | 2 | 120 | 8.3739 | 2009.736
small tools, 2% of labor | [5 empty] | 1315.8245
[5 empty] | Subtotal: | 52480.0445
Exhibit No. DCP-29
Page 52 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 1. Loudon compressor station (continued)
Line Item 5 (continued)
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 4 | 120 | 37.23 | 17870.4
teamster (dump) |  |  | 2 | 120 | 37.23 | 8935.2
pipefitter/welder |  |  | 2 | 120 | 52.0455 | 12490.92
helper |  |  | 2 | 120 | 36.4318 | 8743.644
laborer |  |  | 4 | 120 | 23.6513 | 11352.6
foreman |  |  | 1 | 120 | 53.3205 | 6398.46
[5 empty] | Subtotal: | 65791.224
Material | [5 empty] | Total
Miscellaneous (2% of labor) | [5 empty] | 1315.8245
[5 empty] | Subtotal: | 1315.8245
|  |  | Total Direct Costs (5) = |  |  | 119587.093
6. Restore Site (5 days)
Equipment |  |  | No. | Hours | Rate | Total
dozer, Cat D-6 |  | ` | 1 | 40 | 76.8792 | 3075.168
motor grader, Cat 135H |  |  | 1 | 40 | 36.7195 | 1468.78
flatbed truck |  |  | 1 | 40 | 21.9287 | 877.148
1/2 ton pickup with 4wd |  |  | 2 | 40 | 8.3739 | 669.912
small tools, 2% of labor | [5 empty] | 207.6924
[5 empty] | Subtotal: | 6298.7004
Labor |  |  | No. | Hours | Rate | Total
operator |  |  | 2 | 40 | 37.23 | 2978.4
teamster (flatbed) |  |  | 1 | 40 | 37.23 | 1489.2
laborer |  |  | 4 | 40 | 23.6513 | 3784.2
foreman |  |  | 1 | 40 | 53.3205 | 2132.82
[5 empty] | Subtotal: | 10384.62
Material | [5 empty] | Total
allow $ 15000 for topsoil, seed, fertilizer, straw bales, etc. | [5 empty] | 15000
Sales tax @ 5% | [5 empty] | 750
[5 empty] | Subtotal: | 15750
|  |  | Total Direct Costs (6) = |  |  | 32433.3204
Exhibit No. DCP-29
Page 53 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 1. Loudon compressor station (continued)
Summary: Loudon Compressor Station
A. Pipeline contractor costs
1. Remove R.O.W. Fence and access work site | [5 empty] | 7155.137
2. Excavate, remove valves and blowdowns, remove above ground pipe, cap below ground pipe | [5 empty] | 162484.0999
3. Remove station equipment | [5 empty] | 138768.3516
4. Remove station buildings | [5 empty] | 156498.7659
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface | [5 empty] | 119587.093
6. Restore Site | [5 empty] | 32433.3204
|  |  | Pipeline contractor direct costs: |  |  | 616926.7678
|  |  | 5% Mobilization |  |  | 30846.3384
[5 empty] | Subtotal: | 647773.1062
|  |  | 15% Contractor overhead: |  |  | 97165.9659
[5 empty] | Subtotal: | 744939.0721
|  |  | 10% Contractor profit: |  |  | 74493.9072
|  |  | Total pipeline contractor costs: |  |  | 819432.9794
B. Pipeline company inspection costs
1. Number of days per site | [5 empty] | 67
2. Company cost per day | [5 empty] | 600
|  |  | Total company inspection cost: |  |  | 40200
| Total pipeline contractor and company inspection Loudon compressor station: |  |  |  |  | 859632.9794

## Pleasant Valley Comp
Exhibit No. DCP-29
Page 54 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. Pipeline Retirement
L. Compressor stations
2. Pleasant Valley Compressor Station
Description of Work:
Detailed cost estimate below reflects work required to retire the Pleasant Valley compressor station.
Work includes R.O.W. fence removal, excavation, removal of valves, blowdowns, piping and equipment,
removal of compressor building, maintenance building and control building, capping pipelines, excavation of
concrete foundations, excavation of gravel and asphalt roadway, and restoration of site.
1. Remove R.O.W. Fence and access work site (2 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 1 | 16 | 66.0951 | 1057.5216
flatbed truck |  | 1 | 16 | 21.9287 | 350.8592
3/4 ton pick-up with trailer |  | 1 | 16 | 19.1271 | 306.0336
1/2 ton pickup with 4wd |  | 2 | 16 | 8.3739 | 267.9648
small tools, 2% of labor |  |  |  |  | 99.4761
|  |  |  | Subtotal: | 2081.8553
Labor |  | No. | Hours | Rate | Total
operator |  | 1 | 16 | 37.23 | 595.68
teamster |  | 1 | 16 | 37.23 | 595.68
pipefitter/welder |  | 1 | 16 | 52.0455 | 832.728
helper |  | 1 | 16 | 36.4318 | 582.9096
laborer |  | 4 | 16 | 23.6513 | 1513.68
foreman |  | 1 | 16 | 53.3205 | 853.128
|  |  |  | Subtotal: | 4973.8056
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 99.4761
|  |  |  | Subtotal: | 99.4761
|  | Total Direct Costs (1) = |  |  | 7155.137
2. Excavate, remove valves and blowdowns, remove above ground pipe, cap below ground pipe (10 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B |  | 2 | 80 | 66.0951 | 10575.216
bobcat |  | 1 | 80 | 11.4227 | 913.816
hydrocrane, Grove 30 ton |  | 2 | 80 | 54.8269 | 8772.304
flatbed truck |  | 2 | 80 | 21.9287 | 3508.592
lowboy (part time) |  | 1 | 40 | 51.1601 | 2046.404
3/4 ton pick-up with trailer |  | 4 | 80 | 19.1271 | 6120.672
1/2 ton pickup with 4wd |  | 4 | 80 | 8.3739 | 2679.648
small tools, 2% of labor |  |  |  |  | 1417.4246
|  |  |  | Subtotal: | 36034.0766
Exhibit No. DCP-29
Page 55 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 2. Pleasant Valley compressor station (continued)
Line Item 2 (continued)
Labor |  | No. | Hours | Rate | Total
operator (backhoe, bobcat) |  | 3 | 80 | 37.23 | 8935.2
operator (hydrocrane) |  | 2 | 80 | 42.3428 | 6774.84
teamster (flatbed truck) |  | 2 | 80 | 37.23 | 5956.8
teamster (lowboy) |  | 1 | 40 | 37.23 | 1489.2
pipefitter/welder |  | 4 | 80 | 52.0455 | 16654.56
helper |  | 4 | 80 | 36.4318 | 11658.192
laborer |  | 8 | 80 | 23.6513 | 15136.8
foreman |  | 1 | 80 | 53.3205 | 4265.64
|  |  |  | Subtotal: | 70871.232
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 1417.4246
|  |  |  | Subtotal: | 1417.4246
|  | Total Direct Costs (2) = |  |  | 108322.7333
3. Remove station equipment (10 days)
Equipment |  | No. | Hours | Rate | Total
hydrocrane, Grove 30 ton |  | 1 | 80 | 55.3522 | 4428.176
crane, Grove 50 ton |  | 1 | 80 | 105.3999 | 8431.992
flatbed truck |  | 1 | 80 | 21.9287 | 1754.296
lowboy (part time) |  | 1 | 40 | 51.1601 | 2046.404
3/4 ton pick-up with trailer |  | 4 | 80 | 19.1271 | 6120.672
1/2 ton pickup with 4wd |  | 4 | 80 | 8.3739 | 2679.648
small tools, 2% of labor |  |  |  |  | 1289.4432
|  |  |  | Subtotal: | 26750.6312
Labor |  | No. | Hours | Rate | Total
operator (crane) |  | 2 | 80 | 42.3428 | 6774.84
teamster (flatbed truck) |  | 1 | 80 | 37.23 | 2978.4
teamster (lowboy) |  | 1 | 40 | 37.23 | 1489.2
pipefitter/welder |  | 4 | 80 | 52.0455 | 16654.56
helper |  | 4 | 80 | 32.6018 | 10432.56
laborer |  | 8 | 80 | 34.1827 | 21876.96
foreman |  | 1 | 80 | 53.3205 | 4265.64
|  |  |  | Subtotal: | 64472.16
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 1289.4432
|  |  |  | Subtotal: | 1289.4432
|  | Total Direct Costs (3) = |  |  | 92512.2344
Exhibit No. DCP-29
Page 56 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 2. Pleasant Valley compressor station (continued)
4. Remove station buildings (10 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B w grapple |  | 2 | 80 | 73.1918 | 11710.688
hydrocrane, 30 ton |  | 2 | 80 | 55.3522 | 8856.352
flatbed truck |  | 2 | 80 | 21.9287 | 3508.592
lowboy (part time) |  | 1 | 24 | 51.1601 | 1227.8424
3/4 ton pick-up with trailer |  | 4 | 80 | 19.1271 | 6120.672
1/2 ton pickup with 4wd |  | 4 | 80 | 8.3739 | 2679.648
small tools, 2% of labor |  |  |  |  | 1345.943
|  |  |  | Subtotal: | 35449.7374
Labor |  | No. | Hours | Rate | Total
operator |  | 2 | 80 | 37.23 | 5956.8
operator (hydrocrane) |  | 2 | 80 | 42.3428 | 6774.84
teamster (flatbed truck) |  | 2 | 80 | 37.23 | 5956.8
teamster (lowboy) |  | 1 | 24 | 37.23 | 893.52
pipefitter/welder |  | 4 | 80 | 52.0455 | 16654.56
helper |  | 4 | 80 | 36.4318 | 11658.192
laborer |  | 8 | 80 | 23.6513 | 15136.8
foreman |  | 1 | 80 | 53.3205 | 4265.64
|  |  |  | Subtotal: | 67297.152
Material |  |  |  |  | Total
allow 2% of labor |  |  |  |  | 1345.943
|  |  |  | Subtotal: | 1345.943
|  | Total Direct Costs (4) = |  |  | 104092.8325
5. Demolish concrete foundations and compressor blocks to 3-ft below ground surface (10 days)
Equipment |  | No. | Hours | Rate | Total
backhoe, Cat 325B w hammer |  | 3 | 80 | 78.7332 | 18895.968
backhoe, Cat 325B |  | 1 | 80 | 66.0951 | 5287.608
dump truck 12 cy |  | 2 | 80 | 34.5359 | 5525.744
3/4 ton pick-up with trailer |  | 2 | 80 | 19.1271 | 3060.336
1/2 ton pickup with 4wd |  | 2 | 80 | 8.3739 | 1339.824
small tools, 2% of labor |  |  |  |  | 877.2163
|  |  |  | Subtotal: | 34986.6963
Exhibit No. DCP-29
Page 57 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 2. Pleasant Valley compressor station (continued)
Line Item 5 (continued)
Labor |  | No. | Hours | Rate | Total
operator |  | 4 | 80 | 37.23 | 11913.6
teamster (dump) |  | 2 | 80 | 37.23 | 5956.8
pipefitter/welder |  | 2 | 80 | 52.0455 | 8327.28
helper |  | 2 | 80 | 36.4318 | 5829.096
laborer |  | 4 | 80 | 23.6513 | 7568.4
foreman |  | 1 | 80 | 53.3205 | 4265.64
|  |  |  | Subtotal: | 43860.816
Material |  |  |  |  | Total
Miscellaneous (2% of labor) |  |  |  |  | 877.2163
|  |  |  | Subtotal: | 877.2163
|  | Total Direct Costs (5) = |  |  | 79724.7286
6. Restore Site (5 days)
Equipment |  | No. | Hours | Rate | Total
dozer, Cat D-6 |  | 1 | 40 | 76.8792 | 3075.168
motor grader, Cat 135H |  | 1 | 40 | 36.7195 | 1468.78
flatbed truck |  | 1 | 40 | 21.9287 | 877.148
1/2 ton pickup with 4wd |  | 2 | 40 | 8.3739 | 669.912
small tools, 2% of labor |  |  |  |  | 207.6924
|  |  |  | Subtotal: | 6298.7004
Labor |  | No. | Hours | Rate | Total
operator |  | 2 | 40 | 37.23 | 2978.4
teamster (flatbed) |  | 1 | 40 | 37.23 | 1489.2
laborer |  | 4 | 40 | 23.6513 | 3784.2
foreman |  | 1 | 40 | 53.3205 | 2132.82
|  |  |  | Subtotal: | 10384.62
Material |  |  |  |  | Total
allow $ 10000 for topsoil, seed, fertilizer, straw bales, etc. |  |  |  |  | 10000
Sales tax @ 5% |  |  |  |  | 500
|  |  |  | Subtotal: | 10500
|  | Total Direct Costs (6) = |  |  | 27183.3204
Exhibit No. DCP-29
Page 58 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
IV. L. 2. Pleasant Valley compressor station (continued)
Summary: Retire Pleasant Valley Compressor Station
A. Pipeline contractor costs
1. Remove R.O.W. Fence and access work site |  |  |  |  | 7155.137
2. Excavate, remove valves and blowdowns, remove above ground pipe, cap below ground pipe |  |  |  |  | 108322.7333
3. Remove station equipment |  |  |  |  | 92512.2344
4. Remove station buildings |  |  |  |  | 104092.8325
5. Demolish concrete foundation and compressor blocks to 3-ft below ground surface |  |  |  |  | 79724.7286
6. Restore Site |  |  |  |  | 27183.3204
|  | Pipeline contractor direct costs: |  |  | 418990.9862
|  | 5% Mobilization |  |  | 20949.5493
|  |  |  | Subtotal: | 439940.5355
|  | 15% Contractor overhead: |  |  | 65991.0803
|  |  |  | Subtotal: | 505931.6159
|  | 10% Contractor profit: |  |  | 50593.1616
|  | Total pipeline contractor costs: |  |  | 556524.7775
B. Pipeline company inspection costs
1. Number of days per site |  |  |  |  | 47
2. Company cost per day |  |  |  |  | 600
| Total company inspection cost per site: |  |  |  | 28200
Total pipeline contractor and company inspection Pleasant Valley compressor station: |  |  |  |  | 584724.7775

## Salvage
Exhibit No. DCP-29
Page 59 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
V. Salvage | [9 empty] | Estimated
Salvage
(2006$)
A. Equipment
|  | 1 | Loudon compressor station | [6 empty] | -138768.3516
|  | 2 | Pleasant Valley compressor station | [6 empty] | -92512.2344
[8 empty] | Total equipment: |  | -231280.586
[7 empty] | Weight | Total | Scrap | Estimated
| B. Scrap Steel | [5 empty] | Per Valve | Weight | Value | Salvage
|  | 1 | Remote valves |  |  | No. | (ton) | (ton) | (ton) | (2006$)
|  |  | a. 36-inch |  |  | 9 | 5 | 45 | 120 | -5400
|  |  | b. 20-inch |  |  | 2 | 1.5 | 3 | 120 | -360
|  |  | c. 12-inch |  |  | 2 | 0.5 | 1 | 120 | -120
[9 empty] | Subtotal: | -5880
|  | 2 | M&R stations
|  |  | a. Loudon M&R station (valves, pipe) |  |  |  |  | 500 | 120 | -60000
|  |  | b. Pleasant Valley M&R station (valves, pipe) |  |  |  |  | 250 | 120 | -30000
|  |  | c. Ox M&R station (valves, pipe) |  |  |  |  | 50 | 120 | -6000
[9 empty] | Subtotal: | -96000
[5 empty] | Pipe | Wt/ft
[5 empty] | Length | 36-inch | Total | Total | Scrap | Estimated
[5 empty] | Removed | Pipe | Weight | Weight | Value | Salvage
|  | 3 | Pipe | No. | (ft) | (lbs) | (lbs) | (ton) | (ton) | (2006$)
|  |  | a. Cased crossings | 39 | 170 | 215 | 1425450 | 712.725 | 120 | -85527
|  |  | b. Uncased crossings | 118 | 20 | 215 | 507400 | 253.7 | 120 | -30444
|  |  | c. Small stream crossings | 27 | 20 | 215 | 116100 | 58.05 | 120 | -6966
|  |  | d. River crossings | 4 | 20 | 215 | 17200 | 8.6 | 120 | -1032
|  |  | e. Drips | 3 | 40 | 215 | 25800 | 12.9 | 120 | -1548
[9 empty] | Subtotal: | -125517
[8 empty] | Total scrap steel: |  | -227397
| C. Line pack | [8 empty] | -1577679.0052
[8 empty] | Total line pack: |  | -1577679.0052
[7 empty] | Total Salvage |  |  | -2036356.5912

## Pipeline Labor Rates
Exhibit No. DCP-29
Page 60 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
Pipeline Contractor Labor Rates and Pipeline Company Inspection Cost
A | Pipeline contractor labor rates
|  | (Note 1) | (Note 2) |  | (Note 3)
|  | Sept 2005 |  | March 2006 |  | March 2006
|  | Labor Rate |  | Labor Rate |  | Labor Rate
|  | Including |  | Including |  | Pipeline
|  | Fringe | Escalation | Fringe | Payroll | Demolition
|  | Benefits | Factor | Benefits | Burden | Estimate
| Trade | ($/hr) |  | ($/hr) | (%) | ($/hr)
1 | Operating engineers:
2 | Crane operator | 33.21 | 1.02 | 33.8742 | 25 | 42.3428
3 | Heavy equipment | 29.2 | 1.02 | 29.784 | 25 | 37.23
4 | Small equipment | 25.57 | 1.02 | 26.0814 | 25 | 32.6018
5 | Pipefitter/welder | 40.82 | 1.02 | 41.6364 | 25 | 52.0455
6 | Pipefitter/welder helper | 28.574 | 1.02 | 29.1455 | 25 | 36.4318
7 | Electrician | 38.3 | 1.02 | 39.066 | 25 | 48.8325
8 | Electrician helper | 26.81 | 1.02 | 27.3462 | 25 | 34.1827
9 | Teamster | 29.2 | 1.02 | 29.784 | 25 | 37.23
10 | Laborer | 18.55 | 1.02 | 18.921 | 25 | 23.6513
11 | Foreman | 41.82 | 1.02 | 42.6564 | 25 | 53.3205
B. | Pipeline company inspection costs
Estimated
Cost per day
| Allowance includes direct labor cost, payroll burden, overhead, and transportation |  |  |  |  | 600
Notes
1 | Hourly union pay scales, September 2005, Baltimore, Maryland (ENR September 26, 2005)
2 | Escalation factor based on ENR construction cost indices September 2005 of 7540 and March 2006
of 7692 per ENR 3/20/06.
3 | FICA, unemployment compensation, and workers compensation insurance that employers must pay.

## Pipeline Equipment Rates
Exhibit No. DCP-29
Page 61 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
Pipeline Contractor Equipment Rates
|  | (Note 1) | (Note 2)
|  | August 2005 |  | March 2006
|  | Equipment | Escalation | Equipment
|  | Rate | Factor | Rate
| Equipment Description | ($/hr) |  | ($/hr)
1 | air compressor, 160 cfm with hose | 13.92 | 1.03 | 14.3376
2 | paving breaker | 0.7 | 1.03 | 0.721
3 | concrete pump trailer mounted 25 cy/hr | 12.85 | 1.03 | 13.2355
4 | concrete pump trailer mounted 67 cy/hr | 53.23 | 1.03 | 54.8269
5 | crane, 15 ton, Grove hydrocrane 110 hp | 27.25 | 1.03 | 28.0675
6 | crane, 25 ton, Grove hydrocrane 152 hp | 47.8 | 1.03 | 49.234
7 | crane, 30 ton, Grove hydrocrane 152 hp | 53.74 | 1.03 | 55.3522
8 | crane, 50 ton, Grove 400 hp | 102.33 | 1.03 | 105.3999
9 | motor grader, Cat 135-H, 135 hp | 35.65 | 1.03 | 36.7195
10 | hydraulic excavator, Bobcat 53, 0.10 cy | 11.09 | 1.03 | 11.4227
11 | hydraulic excavator, Cat 325B, 1.75 cy | 64.17 | 1.03 | 66.0951
12 | hydraulic excavator, Cat 312C, 0.68 cy | 29.3 | 1.03 | 30.179
13 | hydraulic hammer, 1330-ft-lb | 12.27 | 1.03 | 12.6381
14 | hydraulic grapple, Labounty 140 TW | 6.89 | 1.03 | 7.0967
15 | lights, 6/1000W, 8 KW gen, trailer mtd. | 5.55 | 1.03 | 5.7165
16 | tractor, Cat D-6, 165 hp | 74.64 | 1.03 | 76.8792
17 | winch for D-6 dozer | 6.92 | 1.03 | 7.1276
18 | dump truck 8 cy | 21.05 | 1.03 | 21.6815
19 | dump truck 12 cy | 33.53 | 1.03 | 34.5359
20 | flatbed truck | 21.29 | 1.03 | 21.9287
21 | pipe truck | 44.35 | 1.03 | 45.6805
22 | lowboy 50 ton | 49.67 | 1.03 | 51.1601
23 | 1/2 ton pickup, 4wd | 8.13 | 1.03 | 8.3739
24 | 3/4 ton pickup, 4wd | 8.7 | 1.03 | 8.961
25 | welder, trailer mtd. | 9.87 | 1.03 | 10.1661
Notes
1 | Hourly Equipment Rates from August 2005, US Army Corps of Engineers
Construction Equipment Ownership and Operating Expense Schedule, Region II.
2 | Escalation factor based on ENR construction cost indices August 2005 of 7479 and March 2006 of 7692
per ENR 3/20/06.

## Workpapers
Exhibit No. DCP-29
Page 62 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
A. |  | Inspector days during abandonment of pipeline facilities
[7 empty] | No. of | Days per | Total
[7 empty] | Sites | Site | Days
| 1 |  | Purge and clean pipeline
| 2 |  | Uncased highway crossings |  |  |  | 118 | 5 | 590
| 3 |  | Cased highway crossings |  |  |  | 35 | 6 | 210
| 4 |  | Cased railroad crossings |  |  |  | 4 | 6 | 24
| 5 |  | Small stream crossings |  |  |  | 27 | 5 | 135
| 6 |  | River crossings
|  |  | a. | Hunting Creek |  |  | 1 | 8 | 8
|  |  | b. | St. Leonards Creek |  |  | 1 | 8 | 8
|  |  | c. | Patuxent River |  |  | 1 | 9 | 9
|  |  | d. | Potomac River |  |  | 1 | 11 | 11
| 7 |  | Remote mainline valves |  |  |  | 13 | 3 | 39
| 8 |  | Pipeline drips |  |  |  | 3 | 3 | 9
| 9 |  | Cathodic protection sites |  |  |  | 3 | 2 | 6
| 10 |  | Pipeline markers |  |  |  | 0 | 0 | 0
| 11 |  | M&R sites
|  |  | a. | Loudon M&R |  |  | 1 | 26 | 26
|  |  | b. | Pleasant Valley M&R |  |  | 1 | 18 | 18
|  |  | c. | Ox M&R |  |  | 1 | 8 | 8
| 12 |  | Compressor stations
|  |  | a. | Loudon station |  |  | 1 | 67 | 67
|  |  | b. | Pleasant Valley station |  |  | 1 | 47 | 47
1215
[6 empty] | Remote sites |  |  | 1049
[6 empty] | M&R stations |  |  | 52
[6 empty] | Compressor stations |  |  | 114
[6 empty] | Total: |  |  | 1215
Exhibit No. DCP-29
Page 63 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
B. |  | Number of environmental tests pre-abandonment
[7 empty] | No. of | Tests per
[7 empty] | Sites | Site | Total
| 1 |  | Purge and clean pipeline
| 2 |  | Uncased highway crossings |  |  |  | 0 | 0 | 0
| 3 |  | Cased highway crossings |  |  |  | 0 | 0 | 0
| 4 |  | Cased railroad crossings |  |  |  | 0 | 0 | 0
| 5 |  | Small stream crossings |  |  |  | 27 | 1 | 27
| 6 |  | River crossings
|  |  | a. | Hunting Creek |  |  | 1 | 2 | 2
|  |  | b. | St. Leonards Creek |  |  | 1 | 2 | 2
|  |  | c. | Patuxent River |  |  | 1 | 2 | 2
|  |  | d. | Potomac River |  |  | 1 | 2 | 2
| 7 |  | Remote mainline valves |  |  |  | 13 | 1 | 13
| 8 |  | Pipeline drips |  |  |  | 3 | 1 | 3
| 9 |  | Cathodic protection sites |  |  |  | 3 | 1 | 3
| 10 |  | Pipeline markers |  |  |  | 0 | 0 | 0
| 11 |  | M&R sites
|  |  | a. | Loudon M&R |  |  | 1 | 10 | 10
|  |  | b. | Pleasant Valley M&R |  |  | 1 | 10 | 10
|  |  | c. | Ox M&R |  |  | 1 | 5 | 5
| 12 |  | Compressor stations
|  |  | a. | Loudon station |  |  | 1 | 50 | 50
|  |  | b. | Pleasant Valley station |  |  | 1 | 50 | 50
179
[6 empty] | Remote sites |  |  | 54
[6 empty] | M&R stations |  |  | 25
[6 empty] | Compressor stations |  |  | 100
[6 empty] | Total: |  |  | 179
Exhibit No. DCP-29
Page 64 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
C. |  | Number of environmental tests during abandonment
[7 empty] | No. of | Tests per
[7 empty] | Sites | Site | Total
| 1 |  | Purge and clean pipeline
| 2 |  | Uncased highway crossings |  |  |  | 118 | 1 | 118
| 3 |  | Cased highway crossings |  |  |  | 35 | 1 | 35
| 4 |  | Cased railroad crossings |  |  |  | 4 | 1 | 4
| 5 |  | Small stream crossings |  |  |  | 27 | 1 | 27
| 6 |  | River crossings
|  |  | a. | Hunting Creek |  |  | 1 | 2 | 2
|  |  | b. | St. Leonards Creek |  |  | 1 | 2 | 2
|  |  | c. | Patuxent River |  |  | 1 | 2 | 2
|  |  | d. | Potomac River |  |  | 1 | 2 | 2
| 7 |  | Remote mainline valves |  |  |  | 13 | 1 | 13
| 8 |  | Pipeline drips |  |  |  | 3 | 1 | 3
| 9 |  | Cathodic protection sites |  |  |  | 3 | 1 | 3
| 10 |  | Pipeline markers |  |  |  | 0 | 0 | 0
| 11 |  | M&R sites
|  |  | a. | Loudon M&R |  |  | 1 | 10 | 10
|  |  | b. | Pleasant Valley M&R |  |  | 1 | 10 | 10
|  |  | c. | Ox M&R |  |  | 1 | 5 | 5
| 12 |  | Compressor stations
|  |  | a. | Loudon station |  |  | 1 | 50 | 50
|  |  | b. | Pleasant Valley station |  |  | 1 | 50 | 50
336
[6 empty] | Remote sites |  |  | 211
[6 empty] | M&R stations |  |  | 25
[6 empty] | Compressor stations |  |  | 100
[6 empty] | Total: |  |  | 336
Exhibit No. DCP-29
Page 65 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
D. |  | Calculation of pipeline volume
Total
[5 empty] | Length | Length | Dia | Cu. Ft/Ft | Volume
[5 empty] | (mile) | (ft) | (ft) | (cf) | (cf)
| 1 |  | TL 522 |  | 87.759 | 463367.52 | 3 | 7.0686 | 3275351.9927
| 2 |  | TL 523 |  |  | 11025 | 3 | 7.0686 | 77931.1328
| 3 |  | TL 530 |  |  | 1070 | 2 | 3.1416 | 3361.5041
| 4 |  | TL 531 |  |  | 1000 | 1.3333 | 1.3962 | 1396.1936
| 5 |  | TL 538 |  |  | 280 | 2.5 | 4.9087 | 1374.4468
|  |  |  | Total: |  | 476742.52 |  |  | 3359415.27
E. |  | Calculation of recoverable linepack
| 1 |  | Calculate number of moles of line pack at 60 degrees F and 200 psig in Cove Point pipelines
[5 empty] | P2 = | 214.7 | psia
[5 empty] | V2 = | 3359415 | cf
[5 empty] | T2 = | 520 | Degrees Rankine = 60 degrees F
[5 empty] | R = | 10.73 | Universal Gas Constant
[5 empty] | n = | ? | No. of moles
[5 empty] | z(2) = | 0.97 | Compressibility Factor
|  |  |  | Equation of state | PV = znRT
(P2)(V2)/(z2)(T2) = nR
[5 empty] | 1429949.2476 | = nR
[5 empty] | 133266.4723 | = n
| 2 |  | Calculate equivalent volume of natural gas in Cove Point pipelines at standard conditions
[5 empty] | P1 = | 14.7 | psia
[5 empty] | V1 = | ? | cf
[5 empty] | T1 = | 520 | Degrees Rankine = 60 Degrees F
[5 empty] | R = | 10.73 | Universal Gas Constant
[5 empty] | n = | 133266.4723 | No. of moles
[5 empty] | z1 = | 1 | Compressibility factor
[5 empty] | V1 = | (z1)(n1)R(T1)/(P1)
[5 empty] | V1 = | 50583238.6914 | cf
|  |  |  | Volume of unrecoverable line pack (scf) = V1 = |  | 50583.2387 | Mcf
|  |  |  | Heat content per cu ft of pipeline gas = |  | 1000 | Btu
|  |  |  | Heat content of unrecoverable line pack = |  | 50583.2387 | Dth
Exhibit No. DCP-29
Page 66 of 66
Dominion Cove Point LNG, LP
Final Abandonment Estimate Transmission Facilities
| 3 |  | Calculation of compressibility factor (z)
|  |  |  | Equation of State: | PV = znRT
|  |  |  | 60 degrees F equivalent to 520 degrees Rankine |  |  | 520 | degrees Rankine
|  |  |  | Critical Temperature of Methane = |  |  | 343.3 | degrees Rankine
|  |  |  | Reduced Temperature = 520/343.3 = |  |  | 1.5147 | reduced temperature
At 400 psig = 414.7 psia:
|  |  |  | Critical Pressure of Methane = |  |  | 673.1 | psia
|  |  |  | Reduced Pressure = 214.7/673.1 = |  |  | 0.31897 | reduced pressure
[7 empty] | 0.97 | z factor from chart
| 4 |  |  | Recoverable line pack
Abandonment pressure assumed to be 200 psig.
|  |  |  | Capitalized line pack (Dth) |  |  |  |  | 184721
|  |  |  | Flex account line pack 12/31/05 (Dth) |  |  |  |  | 81687
|  |  |  | Cove Point transmission line pack (Dth) |  |  |  | Subtotal: | 266408
|  |  |  | Unrecoverable line pack (Dth) |  |  |  |  | 50583.2387
|  |  |  | Recoverable Cove Point transmission line pack (Dth) |  |  |  | Total: | 215824.7613
|  |  |  | Spot price of gas April 3, 2006 (Dth) |  |  |  |  | 7.31
|  |  |  | Value of recoverable line pack April 3, 2006: |  |  |  |  | 1577679.0052