## Summary Option I
Exhibit No. PNG-18
Page 1 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option I
(Minimum pipe removal footage)
Estimated Cost (February 2010$)
[5 empty] | Option I (a) | Option I (b) | Option I
[5 empty] | (100% PNGTS) | (33.24% PNGTS)
I. | Pipeline Retirement |  |  |  | Subtotal | Subtotal | Total
| A. | Clean and purge pipelines |  |  | 234725 | 44209.2 | 278934.2
| B. | Fill pipelines with nitrogen |  |  | 4931700 | 1099293.336 | 6030993.336
| C. | Pipe removal |  |  | 413658 |  | 413658
| D. | Pipe handling and storage |  |  | 38282.9 |  | 38282.9
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  | 10187526 | 2432710.95 | 12620236.95
|  | 2 | Uncased railroad crossings |  | 58549 | 77846.7504 | 136395.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  | 2200475 | 789952.9212 | 2990427.9212
|  | 2 | Cased railroad crossings |  | 792171 | 204802.6092 | 996973.6092
| G. | Small stream crossings |  |  | 11007212 | 2062938.8856 | 13070150.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  | 1517556 | 294254.1084 | 1811810.1084
|  | 2 | Trench crossings |  | 2087504 | 390311.0604 | 2477815.0604
| I. | Remote valve sites |  |  | 470850 | 166944.576 | 637794.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  | 122754 | 26538.816 | 149292.816
|  | 2 | Remove rectifiers |  | 19936 | 11360.1024 | 31296.1024
| K. | Pipeline markers |  |  | 176532 | 33245.3184 | 209777.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  | 883986 | 440755.4196 | 1324741.4196
|  | 2 | Medium M&R stations |  | 298383 | 297547.5276 | 595930.5276
|  |  |  | Total I: | 35441800 | 8372712 | 43814511
II. | Salvage
| A. | Scrap steel |  |  | -359270 | -123725.928 | -482995.928
| B. | Line pack |  |  | -1076369.22 | -243065.4059 | -1319434.6259
|  |  |  | Total II: | -1435639 | -366791 | -1802431
III. | Contingency (10% of I above)
[5 empty] | 3544180 | 837271.1581 | 4381451.1581
|  |  |  | Total III: | 3544180 | 837271 | 4381451
|  |  |  | Grand Total III: | 37550341 | 8843192 | 46393531

## Summary Option I(a)
Exhibit No. PNG-18
Page 2 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option I (a) - 24" Mainline
(100% PNGTS ownership)
Option I (a)
Estimated
I. | Pipeline Retirement |  |  |  | PNGTS Cost
| A. | Clean and purge pipelines |  |  | 234725
| B. | Fill pipelines with nitrogen |  |  | 4931700
| C. | Pipe removal |  |  | 413658
| D. | Pipe handling and storage |  |  | 38282.9
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  | 10187526
|  | 2 | Uncased railroad crossings |  | 58549
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  | 2200475
|  | 2 | Cased railroad crossings |  | 792171
| G. | Small stream crossings |  |  | 11007212
| H. | River and large stream crossings
|  | 1 | HDD crossings |  | 1517556
|  | 2 | Trench crossings |  | 2087504
| I. | Remote valve sites |  |  | 470850
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  | 122754
|  | 2 | Remove rectifiers |  | 19936
| K. | Pipeline markers |  |  | 176532
| L. | M&R stations
|  | 1 | Small M&R stations |  | 883986
|  | 2 | Medium M&R stations |  | 298383
|  |  |  | Total I: | 35441800
II. | Salvage
| A. | Scrap steel |  |  | -359270
| B. | Line pack |  |  | -1076369.22
|  |  |  | Total II: | -1435639
III. | Contingency (10% of I above)
3544180
|  |  |  | Total III: | 3544180
|  |  |  | Grand Total III: | 37550341

## Summary Option I(b)
Exhibit No. PNG-18
Page 3 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option I (b) - 30" Mainline
(33.24% PNGTS Ownership)
1/
[6 empty] | Option I (b) | Option I (b)
[6 empty] | Estimated | Estimated
I. | Pipeline Retirement |  |  |  |  | Total cost | PNGTS Cost
| A. | Clean and purge pipelines |  |  |  | 133000 | 44209.2
| B. | Fill pipelines with nitrogen |  |  |  | 3307140 | 1099293.336
| C. | Pipe removal
| D. | Pipe handling and storage
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  |  | 7318625 | 2432710.95
|  | 2 | Uncased railroad crossings |  |  | 234196 | 77846.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  |  | 2376513 | 789952.9212
|  | 2 | Cased railroad crossings |  |  | 616133 | 204802.6092
| G. | Small stream crossings |  |  |  | 6206194 | 2062938.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  |  | 885241 | 294254.1084
|  | 2 | Trench crossings |  |  | 1174221 | 390311.0604
| I. | Remote valve sites |  |  |  | 502240 | 166944.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  |  | 79840 | 26538.816
|  | 2 | Remove rectifiers |  |  | 34176 | 11360.1024
| K. | Pipeline markers |  |  |  | 100016 | 33245.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  |  | 1325979 | 440755.4196
|  | 2 | Medium M&R stations |  |  | 895149 | 297547.5276
[5 empty] | Total I: | 25188663 | 8372712
II. | Salvage
| A. | Scrap steel |  |  |  | -372220 | -123725.928
| B. | Line pack |  |  |  | -731243.7 | -243065.4059
[5 empty] | Total II: | -1103464 | -366791
III. | Contingency (10% of I above)
[6 empty] | 2518866.3 | 837271.1581
[5 empty] | Total III: | 2518866 | 837271
[5 empty] | Grand Total III: | 26604065 | 8843192
Note 1: PNGTS percentage ownership: |  |  |  | 33.24%

## Summary Option II
Exhibit No. PNG-18
Page 4 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option II
(Maximum pipe removal footage)
Estimated Cost (February 2010$)
[5 empty] | Option II (a) | Option II (b) | Option II
[5 empty] | (100% PNGTS) | (33.24% PNGTS)
I. | Pipeline Retirement |  |  |  | Subtotal | Subtotal | Total
| A. | Clean and purge pipelines |  |  | 234725 | 44209.2 | 278934.2
| B. | Fill pipelines with nitrogen (Not applicable)
| C. | Pipe removal |  |  | 28722666 | 7680153.1896 | 36402819.1896
| D. | Pipe handling and storage |  |  | 2661379.3 | 489885.436 | 3151264.736
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  | 10187526 | 2432710.95 | 12620236.95
|  | 2 | Uncased railroad crossings |  | 58549 | 77846.7504 | 136395.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  | 2200475 | 789952.9212 | 2990427.9212
|  | 2 | Cased railroad crossings |  | 792171 | 204802.6092 | 996973.6092
| G. | Small stream crossings |  |  | 11007212 | 2062938.8856 | 13070150.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  | 1517556 | 294254.1084 | 1811810.1084
|  | 2 | Trench crossings |  | 2087504 | 390311.0604 | 2477815.0604
| I. | Remote valve sites |  |  | 470850 | 166944.576 | 637794.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  | 122754 | 26538.816 | 149292.816
|  | 2 | Remove rectifiers |  | 19936 | 11360.1024 | 31296.1024
| K. | Pipeline markers |  |  | 176532 | 33245.3184 | 209777.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  | 883986 | 440755.4196 | 1324741.4196
|  | 2 | Medium M&R stations |  | 298383 | 297547.5276 | 595930.5276
|  |  |  | Total I: | 61442204 | 15443457 | 76885661
II. | Salvage
| A. | Scrap steel |  |  | -7693410 | -3028640.994 | -10722050.994
| B. | Line pack |  |  | -1076369.22 | -243065.4059 | -1319434.6259
|  |  |  | Total II: | -8769779 | -3271706 | -12041486
III. | Contingency (10% of I above)
[5 empty] | 6144220.4 | 1544345.7 | 7688566.1
|  |  |  | Total III: | 6144220 | 1544346 | 7688566
|  |  |  | Grand Total III: | 58816645 | 13716097 | 72532741

## Summary Option II(a)
Exhibit No. PNG-18
Page 5 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option II (a) - 24" Mainline
(100% PNGTS ownership)
Option II (a)
Estimated
I. | Pipeline Retirement |  |  |  |  | PNGTS Cost
| A. | Clean and purge pipelines |  |  |  | 234725
| B. | Fill pipelines with nitrogen |  | (Not applicable)
| C. | Pipe removal |  |  |  | 28722666
| D. | Pipe handling and storage |  |  |  | 2661379.3
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  |  | 10187526
|  | 2 | Uncased railroad crossings |  |  | 58549
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  |  | 2200475
|  | 2 | Cased railroad crossings |  |  | 792171
| G. | Small stream crossings |  |  |  | 11007212
| H. | River and large stream crossings
|  | 1 | HDD crossings |  |  | 1517556
|  | 2 | Trench crossings |  |  | 2087504
| I. | Remote valve sites |  |  |  | 470850
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  |  | 122754
|  | 2 | Remove rectifiers |  |  | 19936
| K. | Pipeline markers |  |  |  | 176532
| L. | M&R stations
|  | 1 | Small M&R stations |  |  | 883986
|  | 2 | Medium M&R stations |  |  | 298383
[5 empty] | Total I: | 61442204
II. | Salvage
| A. | Scrap steel |  |  |  | -7693410
| B. | Line pack |  |  |  | -1076369.22
[5 empty] | Total II: | -8769779
III. | Contingency (10% of I above)
6144220.4
[5 empty] | Total III: | 6144220
[5 empty] | Grand Total III: | 58816645

## Summary Option II(b)
Exhibit No. PNG-18
Page 6 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option II (b) - 30" Mainline
(33.24% PNGTS Ownership)
1/
[6 empty] | Option II (b) | Option II (b)
[6 empty] | Estimated | Estimated
I. | Pipeline Retirement |  |  |  |  | Total cost | PNGTS Cost
| A. | Clean and purge pipelines |  |  |  | 133000 | 44209.2
| B. | Fill pipelines with nitrogen |  | (Not applicable)
| C. | Pipe removal |  |  |  | 23105154 | 7680153.1896
| D. | Pipe handling and storage |  |  |  | 1473782.9 | 489885.436
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  |  | 7318625 | 2432710.95
|  | 2 | Uncased railroad crossings |  |  | 234196 | 77846.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  |  | 2376513 | 789952.9212
|  | 2 | Cased railroad crossings |  |  | 616133 | 204802.6092
| G. | Small stream crossings |  |  |  | 6206194 | 2062938.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  |  | 885241 | 294254.1084
|  | 2 | Trench crossings |  |  | 1174221 | 390311.0604
| I. | Remote valve sites |  |  |  | 502240 | 166944.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  |  | 79840 | 26538.816
|  | 2 | Remove rectifiers |  |  | 34176 | 11360.1024
| K. | Pipeline markers |  |  |  | 100016 | 33245.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  |  | 1325979 | 440755.4196
|  | 2 | Medium M&R stations |  |  | 895149 | 297547.5276
[5 empty] | Total I: | 46460460 | 15443457
II. | Salvage
| A. | Scrap steel |  |  |  | -9111435 | -3028640.994
| B. | Line pack |  |  |  | -731243.7 | -243065.4059
[5 empty] | Total II: | -9842679 | -3271706
III. | Contingency (10% of I above)
[6 empty] | 4646046 | 1544345.6904
[5 empty] | Total III: | 4646046 | 1544346
[5 empty] | Grand Total III: | 41263827 | 13716097
Note 1: PNGTS percentage ownership: |  |  |  | 33.24%

## Summary Option III
Exhibit No. PNG-18
Page 7 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option III
(Intermediate pipe removal footage)
Estimated Cost (February 2010$)
[5 empty] | Option III (a) | Option III (b) | Option III
[5 empty] | (100% PNGTS) | (33.24% PNGTS)
I. | Pipeline Retirement |  |  |  | Subtotal | Subtotal | Total
| A. | Clean and purge pipelines |  |  | 234725 | 44209.2 | 278934.2
| B. | Fill pipelines with nitrogen |  |  | 4467540 | 960435.2304 | 5427975.2304
| C. | Pipe removal |  |  | 2708002 | 938912.9952 | 3646914.9952
| D. | Pipe handling and storage |  |  | 250963.1 | 62196.6271 | 313159.7271
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  | 10187526 | 2432710.95 | 12620236.95
|  | 2 | Uncased railroad crossings |  | 58549 | 77846.7504 | 136395.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  | 2200475 | 789952.9212 | 2990427.9212
|  | 2 | Cased railroad crossings |  | 792171 | 204802.6092 | 996973.6092
| G. | Small stream crossings |  |  | 11007212 | 2062938.8856 | 13070150.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  | 1517556 | 294254.1084 | 1811810.1084
|  | 2 | Trench crossings |  | 2087504 | 390311.0604 | 2477815.0604
| I. | Remote valve sites |  |  | 470850 | 166944.576 | 637794.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  | 122754 | 26538.816 | 149292.816
|  | 2 | Remove rectifiers |  | 19936 | 11360.1024 | 31296.1024
| K. | Pipeline markers |  |  | 176532 | 33245.3184 | 209777.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  | 883986 | 440755.4196 | 1324741.4196
|  | 2 | Medium M&R stations |  | 298383 | 297547.5276 | 595930.5276
|  |  |  | Total I: | 37484664 | 9234963 | 46719627
II. | Salvage
| A. | Scrap steel |  |  | -953675 | -475717.584 | -1429392.584
| B. | Line pack |  |  | -1076369.22 | -243065.4059 | -1319434.6259
|  |  |  | Total II: | -2030044 | -718783 | -2748827
III. | Contingency (10% of I above)
[5 empty] | 3748466.4 | 923496.3 | 4671962.7
|  |  |  | Total III: | 3748466 | 923496 | 4671963
|  |  |  | Grand Total III: | 39203086 | 9439676 | 48642763

## Summary Option III(a)
Exhibit No. PNG-18
Page 8 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option III (a) - 24" Mainline
(100% PNGTS ownership)
Option III (a)
Estimated
I. | Pipeline Retirement |  |  |  | PNGTS Cost
| A. | Clean and purge pipelines |  |  | 234725
| B. | Fill pipelines with nitrogen |  |  | 4467540
| C. | Pipe removal |  |  | 2708002
| D. | Pipe handling and storage |  |  | 250963.1
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  | 10187526
|  | 2 | Uncased railroad crossings |  | 58549
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  | 2200475
|  | 2 | Cased railroad crossings |  | 792171
| G. | Small stream crossings |  |  | 11007212
| H. | River and large stream crossings
|  | 1 | HDD crossings |  | 1517556
|  | 2 | Trench crossings |  | 2087504
| I. | Remote valve sites |  |  | 470850
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  | 122754
|  | 2 | Remove rectifiers |  | 19936
| K. | Pipeline markers |  |  | 176532
| L. | M&R stations
|  | 1 | Small M&R stations |  | 883986
|  | 2 | Medium M&R stations |  | 298383
|  |  |  | Total I: | 37484664
II. | Salvage
| A. | Scrap steel |  |  | -953675
| B. | Line pack |  |  | -1076369.22
|  |  |  | Total II: | -2030044
III. | Contingency (10% of I above)
|  |  |  | Total III: | 3748466.4
3748466
|  |  |  | Grand Total III: | 39203086

## Summary Option III(b)
Exhibit No. PNG-18
Page 9 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Summary Option III (b) - 30" Mainline
(33.24% PNGTS Ownership)
1/
[6 empty] | Option III (b) | Option III (b)
[6 empty] | Estimated | Estimated
I. | Pipeline Retirement |  |  |  |  | Total cost | PNGTS Cost
| A. | Clean and purge pipelines |  |  |  | 133000 | 44209.2
| B. | Fill pipelines with nitrogen |  |  |  | 2889396 | 960435.2304
| C. | Pipe removal |  |  |  | 2824648 | 938912.9952
| D. | Pipe handling and storage |  |  |  | 187113.8 | 62196.6271
| E. | Uncased highway/railroad crossings
|  | 1 | Uncased highway crossings |  |  | 7318625 | 2432710.95
|  | 2 | Uncased railroad crossings |  |  | 234196 | 77846.7504
| F. | Cased highway/railroad crossings
|  | 1 | Cased highway crossings |  |  | 2376513 | 789952.9212
|  | 2 | Cased railroad crossings |  |  | 616133 | 204802.6092
| G. | Small stream crossings |  |  |  | 6206194 | 2062938.8856
| H. | River and large stream crossings
|  | 1 | HDD crossings |  |  | 885241 | 294254.1084
|  | 2 | Trench crossings |  |  | 1174221 | 390311.0604
| I. | Remote valve sites |  |  |  | 502240 | 166944.576
| J. | Cathodic protection facilities
|  | 1 | Remove test sites |  |  | 79840 | 26538.816
|  | 2 | Remove rectifiers |  |  | 34176 | 11360.1024
| K. | Pipeline markers |  |  |  | 100016 | 33245.3184
| L. | M&R stations
|  | 1 | Small M&R stations |  |  | 1325979 | 440755.4196
|  | 2 | Medium M&R stations |  |  | 895149 | 297547.5276
[5 empty] | Total I: | 27782681 | 9234963
II. | Salvage
| A. | Scrap steel |  |  |  | -1431160 | -475717.584
| B. | Line pack |  |  |  | -731243.7 | -243065.4059
[5 empty] | Total II: | -2162404 | -718783
III. | Contingency (10% of I above)
[6 empty] | 2778268.1 | 923496.3164
[5 empty] | Total III: | 2778268 | 923496
[5 empty] | Grand Total III: | 28398545 | 9439676
Note 1: PNGTS Percentage ownership: |  |  |  | 33.24%

## Clean and Purge Pipe
Exhibit No. PNG-18
Page 10 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
A. Clean and purge pipelines
Description of Work:
Prior to its last delivery, PNGTS conducts a series of pigging operations to ensure that its pipelines are clean
and free of liquids. After the last delivery to its customers, PNGTS operating staff isolates the pipeline system
from gas supply inputs and delivery points. Abandonment pressure is estimated to be 200 psig. Unrecovered
line pack is evacuated by flaring or venting. At this point pipeline is filled with natural gas at atmospheric
pressure. PNGTS staff evacuates sections of pipeline using pipeline evacuation equipment. At this point
pipeline is filled with air at atmospheric pressure. Pipeline is ready for demolition work.
1 |  | Estimated cost to clean and purge 100-mile transmission pipeline segment of hydrocarbons:
[6 empty] | Unit | No. | Days | Rate | Total
| a. |  | Pigging operation prior to final shutdown |  |  | each | 2 |  | 10000 | 20000
| b. |  | Isolate pipeline from input and delivery points |  |  | person | 3 | 5 | 1000 | 15000
| c. |  | Blowdown system at M/L valves (10 sites) |  |  | person | 3 | 10 | 1000 | 30000
| d. |  | Pipeline evacuation (10 sites) |  |  | person | 3 | 20 | 1000 | 60000
125000
[7 empty] | Estimated cost per mile: |  |  | 1250
2 |  | Estimated cost to clean and purge transmission pipelines:
Cost Per
| a. |  | Wholly-owned facilities (24" mainline and associated facilities) |  |  |  |  | Miles | Mile | Total
|  |  | 24 | " | Mainline |  |  | 143.83 | 1250 | 179787.5
|  |  | 8 | " | Groveton Lateral |  |  | 0.66 | 1250 | 825
|  |  | 12 | " | Rumford lateral |  |  | 26.51 | 1250 | 33137.5
|  |  | 12 | " | Jay lateral |  |  | 16.78 | 1250 | 20975
[8 empty] | 187.78 |  | 234725
| b. |  | Jointly-owned facilities (30" mainline and associated facilities)
|  |  | 30 | " | Mainline |  |  | 100.56 | 1250 | 125700
|  |  | 12 | " | Westbrook lateral |  |  | 3.84 | 1250 | 4800
|  |  | 16 | " | Newington lateral |  |  | 1.2 | 1250 | 1500
|  |  | 20 | " | Haverhill lateral |  |  | 0.8 | 1250 | 1000
[8 empty] | 106.4 |  | 133000

## Fill Pipe w Nitrogen
Exhibit No. PNG-18
Page 11 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
B. Fill pipelines with nitrogen
Description of Work:
Detailed cost estimate below reflects work required to fill capped segments between road crossings, river
crossings, stream crossings, etc. with nitrogen. Each segment is assumed to be 1/2 mile in length. Estimate
includes cost of pigs, pipe fittings, and nitrogen. Work is done in conjunction with crossing crews. Estimate
also includes environmental inspection, pipeline company inspection, and pipeline company management and
overhead costs.
1. Fill segment with nitrogen (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
3/4 ton pick-up with trailer |  |  |  | 2 | 5 | 27.8585 | 278.5849
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 80.7129
[6 empty] | Subtotal: | 605.2415
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 59.003 | 295.0149
pipefitter/welder |  |  |  | 2 | 5 | 93.7967 | 937.9668
helper |  |  |  | 2 | 5 | 56.278 | 562.7801
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 4035.6434
Material | [6 empty] | Total
pig |  |  |  | 1 | each | 400 | 400
fittings |  |  |  | 2 | each | 500 | 1000
nitrogen |  |  |  | 15000 | cu ft | 0.01 | 150
transportation and pumping charges |  |  |  | 5 | hours | 150 | 750
Sales tax @ | 5% | [5 empty] | 115
[6 empty] | Subtotal: | 2415
|  |  |  | Total Direct Costs (1) = |  |  | 7055.8849
Exhibit No. PNG-18
Page 12 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. B. Fill pipelines with nitrogen (continued)
Summary: Fill Pipelines with Nitrogen
A. Pipeline contractor costs
1. Fill segment with nitrogen
|  |  |  | Pipeline contractor direct costs: |  |  | 7055.8849
|  |  |  | 5% Mobilization |  |  | 352.7942
[6 empty] | Subtotal: | 7408.6792
|  |  |  | 15% Contractor overhead: |  |  | 1111.3019
[6 empty] | Subtotal: | 8519.9811
|  |  |  | 10% Contractor profit: |  |  | 851.9981
|  |  |  | Total pipeline contractor costs: |  |  | 9371.9792
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 468.599
|  |  |  | Total environmental contractor costs: |  |  | 468.599
C. Pipeline company inspection costs
1. Number of days per segment | [6 empty] | 0.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total co. inspection cost per segment: |  |  | 250
D. Pipeline company management and overhead costs (15% of A + B + C)
1513.5867
|  |  |  | Total management and overhead cost: |  |  | 1513.5867
|  | Total cost to fill one segment with nitrogen (A + B + C + D): |  |  |  |  | 11604
Wholly-owned facilities - Number of segments assuming no pipe removed: | [6 empty] | 425
Jointly-owned facilities - Number of segments assuming no pipe removed: | [6 empty] | 285
Total Estimated Cost to Fill Pipe with Nitrogen (Option I)
A. Wholly-owned facilities (24" mainline and associated laterals)
|  | No. of segments: |  |  |  |  | 419
| Item B. | Total estimated cost to fill pipelines with nitrogen |  |  |  |  | 4931700
B. Jointly-owned facilities (30"mainline and associated laterals)
|  | No. of segments: |  |  |  |  | 285
| Item B. | Total estimated cost to fill pipelines with nitrogen |  |  |  |  | 3307140
Exhibit No. PNG-18
Page 13 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. B. Fill pipelines with nitrogen (continued)
Total Estimated Cost to Fill Pipe with Nitrogen (Option III)
A. Wholly-owned facilities (24" mainline and associated laterals)
|  | No. of segments: |  |  |  |  | 385
| Item B. | Total estimated cost to fill pipelines with nitrogen |  |  |  |  | 4467540
B. Jointly-owned facilities (30"mainline and associated laterals)
|  | No. of segments: |  |  |  |  | 249
| Item B. | Total estimated cost to fill pipelines with nitrogen |  |  |  |  | 2889396

## Pipe Removal
Exhibit No. PNG-18
Page 14 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
C. Pipe removal
Description of Work:
Detailed cost estimate below reflects work required to remove a 24" diameter pipeline. Work includes
trench excavation, cutting pipe into 40-ft sections, loading pipe onto pipe trucks and hauling to temporary
storage yard, backfilling trench, and restoration of area. Time to achieve each task is based on the removal of
one mile of 24" dia. pipe. Removal costs are adjusted for pipe diameters greater than or less than 24".
Estimate also includes environmental inspection, pipeline company inspection, ROW damage payments, and
pipeline company management and overhead costs.
1. Excavate trench (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, Cat D-6R |  |  |  | 1 | 10 | 96.5008 | 965.0076
backhoe, Cat 320D |  |  |  | 4 | 10 | 48.6641 | 1946.5628
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 184.7588
[6 empty] | Subtotal: | 3588.2167
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 5 | 10 | 81.563 | 4078.1477
teamster |  |  |  | 1 | 10 | 59.003 | 590.0299
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 11 |  | 90 | 990
[6 empty] | Subtotal: | 9237.9408
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 184.7588
[6 empty] | Subtotal: | 184.7588
|  |  |  | Total Direct Costs (1) = |  |  | 13010.9163
2. Remove pipe from trench, cut pipe, load on trucks, and haul to storage yard (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove, 30 ton |  |  |  | 1 | 10 | 71.8307 | 718.3071
pipelayer, Cat, 572-R, 20' boom |  |  |  | 3 | 10 | 80.5182 | 2415.546
pipe truck |  |  |  | 5 | 10 | 61.9526 | 3097.63
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
lowboy |  |  |  | 1 | 10 | 65.4034 | 654.0338
3/4 ton pick-up with trailer |  |  |  | 4 | 10 | 27.8585 | 1114.3396
1/2 ton pickup with 4wd |  |  |  | 4 | 10 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 442.5218
[6 empty] | Subtotal: | 9164.9232
Exhibit No. PNG-18
Page 15 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. C. Pipe removal (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (hydrocrane) |  |  |  | 1 | 10 | 81.8785 | 818.7848
operator |  |  |  | 3 | 10 | 81.563 | 2446.8886
teamster |  |  |  | 7 | 10 | 59.003 | 4130.2092
pipefitter/welder |  |  |  | 4 | 10 | 93.7967 | 3751.8672
helper |  |  |  | 4 | 10 | 56.278 | 2251.1203
laborer |  |  |  | 8 | 10 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 28 |  | 90 | 2520
[6 empty] | Subtotal: | 22126.0877
Material | [6 empty] | Total
Miscellaneous 2% of labor | [6 empty] | 442.5218
[6 empty] | Subtotal: | 442.5218
|  |  |  | Total Direct Costs (2) = |  |  | 31733.5326
3. Backfill trench (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, Cat D-6R |  |  |  | 1 | 10 | 96.5008 | 965.0076
track loader, Cat 953D |  |  |  | 2 | 10 | 65.9684 | 1319.3684
dump truck 14 cy |  |  |  | 6 | 10 | 45.2839 | 2717.0352
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 216.5366
[6 empty] | Subtotal: | 5448.6052
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 3 | 10 | 81.563 | 2446.8886
teamster |  |  |  | 6 | 10 | 59.003 | 3540.1793
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 14 |  | 90 | 1260
[6 empty] | Subtotal: | 10826.8311
Material | [6 empty] | Total
Backfill (cy) | 10 | 675 | cy |  |  |  | 6750
Sales tax @ | 5% | [5 empty] | 337.5
Miscellaneous (2% of labor) | [6 empty] | 216.5366
[6 empty] | Subtotal: | 7304.0366
|  |  |  | Total Direct Costs (3) = |  |  | 23579.4729
Exhibit No. PNG-18
Page 16 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. C. Pipe removal (continued)
4. Restore site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, Cat D-6R |  |  |  | 2 | 10 | 96.5008 | 1930.0152
track loader, Cat 953D |  |  |  | 1 | 10 | 65.9684 | 659.6842
flatbed truck |  |  |  | 2 | 10 | 26.123 | 522.4602
dump truck 14 cy |  |  |  | 5 | 10 | 45.2839 | 2264.196
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 230.1372
[6 empty] | Subtotal: | 5837.1502
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 3 | 10 | 81.563 | 2446.8886
teamster |  |  |  | 7 | 10 | 59.003 | 4130.2092
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 15 |  | 90 | 1350
[6 empty] | Subtotal: | 11506.861
Material | [6 empty] | Total
allow $ 15,000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 15000
Sales tax @ | 5% | [5 empty] | 750
[6 empty] | Subtotal: | 15750
|  |  |  | Total Direct Costs (4) = |  |  | 33094.0112
Summary: Pipe Removal
A. Pipeline contractor costs
1. Excavate trench | [6 empty] | 13010.9163
2. Remove pipe from trench, cut pipe, load on trucks, and haul to storage yard | [6 empty] | 31733.5326
3. Backfill trench | [6 empty] | 23579.4729
4. Restore site | [6 empty] | 33094.0112
|  |  |  | Pipeline contractor direct costs: |  |  | 101417.933
|  |  |  | 5% Mobilization |  |  | 5070.8967
[6 empty] | Subtotal: | 106488.8297
|  |  |  | 15% Contractor overhead: |  |  | 15973.3245
[6 empty] | Subtotal: | 122462.1541
|  |  |  | 10% Contractor profit: |  |  | 12246.2154
|  |  |  | Total pipeline contractor costs: |  |  | 134708.3696
Exhibit No. PNG-18
Page 17 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. C. Pipe removal (continued)
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 6735.4185
|  |  |  | Total environmental contractor costs: |  |  | 6735.4185
C. Pipeline company inspection costs
1. Number of days per mile | [6 empty] | 2
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per mile: |  |  | 1000
D. ROW damages
|  |  |  | Total ROW damage costs per mile: |  |  | 21120
E. Pipeline company management and overhead costs (15% of A + B + C + D)
24534.5682
|  |  |  | Total management and overhead cost: |  |  | 24534.5682
| Total estimated cost to remove 1 mile of 24" dia. pipeline (A + B + C + D + E): | [5 empty] | 188098.3562
| Estimated cost per foot to remove 1 mile of 24" dia. pipeline: | [5 empty] | 36
I. Total Estimated Cost to Remove Pipe (Option I)
I (a) Wholly-Owned Facilities (24" Mainline and associated laterals)
(See Note)
Pipeline | Pipeline | Six-Tenths | Estimated | Pipeline | Adjusted | Pipeline | Estimated
Diameter | Volume | Factor | Removal | Removed | P/L Length | Removed | Removal
(in.) | (cu. in.) |  | Cost/ft | (mile) | (mile) | (ft) | Cost
8 | 50.2655 | 0.26758 | 10 | 0.01 | 0.01 | 53 | 530
12 | 113.0973 | 0.43528 | 16 | 0.62 | 0.57 | 3010 | 48160
16 | 201.0619 | 0.61474 | 22
20 | 314.1593 | 0.80349 | 29
24 | 452.3893 | 1 | 36 | 2.07 | 1.92 | 10138 | 364968
30 | 706.8583 | 1.307 | 47
|  |  | Total: | 2.7 | 2.5 | 13201 | 413658
Note: Pipeline length reduced to take crossings into consideration.
Exhibit No. PNG-18
Page 18 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. C. Pipe removal (continued)
II. Total Estimated Cost to Remove Pipe (Option II)
II (a) Wholly-Owned Facilities (24" Mainline and associated laterals)
(See Note)
Pipeline | Pipeline | Six-Tenths | Estimated | Pipeline | Adjusted | Pipeline | Estimated
Diameter | Volume | Factor | Removal | Removed | P/L Length | Removed | Removal
(in.) | (cu. in.) |  | Cost/ft | (mile) | (mile) | (ft) | Cost
8 | 50.2655 | 0.26758 | 10 | 0.66 | 0.61 | 3221 | 32210
12 | 113.0973 | 0.43528 | 16 | 43.29 | 40.07 | 211570 | 3385120
16 | 201.0619 | 0.61474 | 22
20 | 314.1593 | 0.80349 | 29
24 | 452.3893 | 1 | 36 | 143.83 | 133.13 | 702926 | 25305336
30 | 706.8583 | 1.307 | 47
|  |  | Total: | 187.78 | 173.81 | 917717 | 28722666
Note: Pipeline length reduced to take crossings into consideration.
II (b) Jointly-owned facilities (30" Mainline and associated laterals)
(See Note)
Pipeline | Pipeline | Six-Tenths | Estimated | Pipeline | Adjusted | Pipeline | Estimated
Diameter | Volume | Factor | Removal | Removed | P/L Length | Removed | Removal
(in.) | (cu. in.) |  | Cost/ft | (mile) | (mile) | (ft) | Cost
8 | 50.2655 | 0.26758 | 10
12 | 113.0973 | 0.43528 | 16 | 3.84 | 3.47 | 18322 | 293152
16 | 201.0619 | 0.61474 | 22 | 1.2 | 1.09 | 5755 | 126610
20 | 314.1593 | 0.80349 | 29 | 0.8 | 0.72 | 3802 | 110258
24 | 452.3893 | 1 | 36
30 | 706.8583 | 1.307 | 47 | 100.56 | 90.97 | 480322 | 22575134
|  |  | Total: | 106.4 | 96.25 | 508201 | 23105154
Note: Pipeline length reduced to take crossings into consideration.
Exhibit No. PNG-18
Page 19 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. C. Pipe removal (continued)
Total Estimated Cost to Remove Pipe (Option III)
III (a) Wholly-Owned Facilities (24" Mainline and associated laterals)
(See Note)
Pipeline | Pipeline | Six-Tenths | Estimated | Pipeline | Adjusted | Pipeline | Estimated
Diameter | Volume | Factor | Removal | Removed | P/L Length | Removed | Removal
(in.) | (cu. in.) |  | Cost/ft | (mile) | (mile) | (ft) | Cost
8 | 50.2655 | 0.26758 | 10 | 0.06 | 0.06 | 317 | 3170
12 | 113.0973 | 0.43528 | 16 | 4.08 | 3.78 | 19958 | 319328
16 | 201.0619 | 0.61474 | 22
20 | 314.1593 | 0.80349 | 29
24 | 452.3893 | 1 | 36 | 13.56 | 12.55 | 66264 | 2385504
30 | 706.8583 | 1.307 | 47
|  |  | Total: | 17.7 | 16.39 | 86539 | 2708002
Note: Pipeline length reduced to take crossings into consideration.
III (b) Jointly-owned facilities (30" Mainline and associated laterals)
(See Note)
Pipeline | Pipeline | Six-Tenths | Estimated | Pipeline | Adjusted | Pipeline | Estimated
Diameter | Volume | Factor | Removal | Removed | P/L Length | Removed | Removal
(in.) | (cu. in.) |  | Cost/ft | (mile) | (mile) | (ft) | Cost
8 | 50.2655 | 0.26758 | 10
12 | 113.0973 | 0.43528 | 16 | 1.4 | 1.27 | 6706 | 107296
16 | 201.0619 | 0.61474 | 22
20 | 314.1593 | 0.80349 | 29
24 | 452.3893 | 1 | 36
30 | 706.8583 | 1.307 | 47 | 12.1 | 10.95 | 57816 | 2717352
|  |  | Total: | 13.5 | 12.22 | 64522 | 2824648
Note: Pipeline length reduced to take crossings into consideration.

## Pipe Handling and Stor
Exhibit No. PNG-18
Page 20 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
D. Pipe handling and storage
Description of Work:
Detailed cost estimate below reflects work required to unload pipe from pipe trucks, store pipe in temporary
storage yards, and load pipe onto contract carriers for transport to scap yard. Estimate is based on handling
one mile of pipe per day. Estimate also includes environmental inspection, pipeline company inspection, and
pipeline company management and overhead costs.
1. Unload pipe from pipe trucks and stack in storage yard.
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove, 30 ton |  |  |  | 1 | 10 | 71.8307 | 718.3071
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 68.8964
[6 empty] | Subtotal: | 902.5322
Labor |  |  |  | No. | Hours | Rate | Total
operator (hydrocrane) |  |  |  | 1 | 10 | 81.8785 | 818.7848
laborer |  |  |  | 2 | 10 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 4 |  | 90 | 360
[6 empty] | Subtotal: | 3444.8208
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 68.8964
[6 empty] | Subtotal: | 68.8964
|  |  |  | Total Direct Costs (1) = |  |  | 4416.2494
2. Load pipe in storage yard onto contract carriers.
Equipment |  |  |  | No. | Hours | Rate | Total
hydrocrane, Grove, 30 ton |  |  |  | 1 | 10 | 71.8307 | 718.3071
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 68.8964
[6 empty] | Subtotal: | 902.5322
Labor |  |  |  | No. | Hours | Rate | Total
operator (hydrocrane) |  |  |  | 1 | 10 | 81.8785 | 818.7848
laborer |  |  |  | 2 | 10 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 4 |  | 90 | 360
[6 empty] | Subtotal: | 3444.8208
Exhibit No. PNG-18
Page 21 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. D. Pipe handling and storage (continued)
Line Item 2 (continued)
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 68.8964
[6 empty] | Subtotal: | 68.8964
|  |  |  | Total Direct Costs (2) = |  |  | 4416.2494
Summary: Pipe handling and storage
A. Pipeline contractor costs
1. Unload pipe from pipe trucks and stack in storage yard | [6 empty] | 4416.2494
2. Load pipe in storage yard onto contract carriers | [6 empty] | 4416.2494
|  |  |  | Pipeline contractor direct costs: |  |  | 8832.4988
|  |  |  | 5% Mobilization |  |  | 441.6249
[6 empty] | Subtotal: | 9274.1238
|  |  |  | 15% Contractor overhead: |  |  | 1391.1186
[6 empty] | Subtotal: | 10665.2423
|  |  |  | 10% Contractor profit: |  |  | 1066.5242
|  |  |  | Total pipeline contractor costs: |  |  | 11731.7666
B. Environmental contractor costs (5% of pipeline contractor costs)
This section reflects work performed by environmental contractor to monitor work and check
for presence of hazardous materials. Work involves inspection, sampling, evaluation, and report
writing. | [6 empty] | 586.5883
|  |  |  | Total environmental contractor costs: |  |  | 586.5883
C. Pipeline company inspection costs
1. Number of inspectors | [6 empty] | 2
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per mile: |  |  | 1000
D. Pipeline company management and overhead costs (15% of A + B + C)
1997.7532
|  |  |  | Total management and overhead cost: |  |  | 1997.7532
| Total estimated cost to handle and store 1 mile of pipeline (A + B + C + D): | [5 empty] | 15316.1081
| Estimated cost per foot to handle and store 1 mile of pipeline: | [5 empty] | 2.9
Exhibit No. PNG-18
Page 22 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. D. Pipe handling and storage (continued)
I. Total Estimated Pipe Handling and Storage Cost (Option I)
I (a) Wholly-owned facilities (24" Mainline and associated laterals)
|  | Pipeline | Pipeline |  | Total
|  | Diameter | Length | Estimated | Estimated
|  | (in.) | (ft) | Cost/ft | Cost
|  | 8 | 53 | 2.9 | 153.7
|  | 12 | 3010 | 2.9 | 8729
|  | 16 | 0 | 2.9 | 0
|  | 20 | 0 | 2.9 | 0
|  | 24 | 10138 | 2.9 | 29400.2
|  | 30 | 0 | 2.9 | 0
|  | Total: | 13201 |  | 38282.9
II. Total Estimated Pipe Handling and Storage Cost (Option II)
II (a) Wholly-owned facilities (24" Mainline and associated laterals)
|  | Pipeline | Pipeline |  | Total
|  | Diameter | Length | Estimated | Estimated
|  | (in.) | (ft) | Cost/ft | Cost
|  | 8 | 3221 | 2.9 | 9340.9
|  | 12 | 211570 | 2.9 | 613553
|  | 16 | 0 | 2.9 | 0
|  | 20 | 0 | 2.9 | 0
|  | 24 | 702926 | 2.9 | 2038485.4
|  | 30 | 0 | 2.9 | 0
|  | Total: | 917717 |  | 2661379.3
II (b) Jointly-owned facilities (30" Mainline and associated laterals)
|  | Pipeline | Pipeline |  | Total
|  | Diameter | Length | Estimated | Estimated
|  | (in.) | (ft) | Cost/ft | Cost
|  | 8 | 0 | 2.9 | 0
|  | 12 | 18322 | 2.9 | 53133.8
|  | 16 | 5755 | 2.9 | 16689.5
|  | 20 | 3802 | 2.9 | 11025.8
|  | 24 | 0 | 2.9 | 0
|  | 30 | 480322 | 2.9 | 1392933.8
|  | Total: | 508201 |  | 1473782.9
Exhibit No. PNG-18
Page 23 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. D. Pipe handling and storage (continued)
III. Total Estimated Pipe Handling and Storage Cost (Option III)
III (a) Wholly-owned facilities (24" Mainline and associated laterals)
|  | Pipeline | Pipeline |  | Total
|  | Diameter | Length | Estimated | Estimated
|  | (in.) | (ft) | Cost/ft | Cost
|  | 8 | 317 | 2.9 | 919.3
|  | 12 | 19958 | 2.9 | 57878.2
|  | 16 | 0 | 2.9 | 0
|  | 20 | 0 | 2.9 | 0
|  | 24 | 66264 | 2.9 | 192165.6
|  | 30 | 0 | 2.9 | 0
|  | Total: | 86539 |  | 250963.1
III (b) Jointly-owned facilities (30" Mainline and associated laterals)
|  | Pipeline | Pipeline |  | Total
|  | Diameter | Length | Estimated | Estimated
|  | (in.) | (ft) | Cost/ft | Cost
|  | 8 | 0 | 2.9 | 0
|  | 12 | 6706 | 2.9 | 19447.4
|  | 16 | 0 | 2.9 | 0
|  | 20 | 0 | 2.9 | 0
|  | 24 | 0 | 2.9 | 0
|  | 30 | 57816 | 2.9 | 167666.4
|  | Total: | 64522 |  | 187113.8

## Uncased Hwy-RR Crossings
Exhibit No. PNG-18
Page 24 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
E. Uncased highway/railroad crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical uncased highway/railroad crossing (100 ft).
Work includes ROW fence removal, excavation and shoring of trench, capping pipe ends, filling pipe with grout,
backfilling, and restoration of area. Estimate also includes environmental inspection, pipeline company inspection,
and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, cat D-6R |  |  |  | 1 | 5 | 96.5008 | 482.5038
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
lowboy |  |  |  | 1 | 5 | 65.4034 | 327.0169
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 1274.5189
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 2 | 5 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 5 | 93.7967 | 468.9834
helper |  |  |  | 1 | 5 | 56.278 | 281.39
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3988.0997
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 79.762
|  |  |  | Total Direct Costs (1) = |  |  | 5342.3806
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 291.8468
[6 empty] | Subtotal: | 2806.073
Exhibit No. PNG-18
Page 25 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. E. Uncased highway/railroad crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 14592.339
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 291.8468
[6 empty] | Subtotal: | 291.8468
|  |  |  | Total Direct Costs (2) = |  |  | 17690.2588
3. Fill pipe with grout, backfill trench, grade disturbed areas (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 10 | 48.6641 | 486.6407
dump truck 8 cy |  |  |  | 1 | 10 | 25.8304 | 258.304
grout pump, trailer mounted |  |  |  | 1 | 10 | 18.6968 | 186.9677
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 112.3085
[6 empty] | Subtotal: | 1274.8783
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
teamster |  |  |  | 1 | 10 | 59.003 | 590.0299
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 5615.4226
Material | [6 empty] | Total
Grout (cy) | 98 | 13 | cy | (Note: assumes 24" pipe) |  |  | 1274
Sales tax @ | 5% | [5 empty] | 63.7
Miscellaneous (2% of labor) | [6 empty] | 112.3085
[6 empty] | Subtotal: | 1450.0085
|  |  |  | Total Direct Costs (3) = |  |  | 8340.3093
Exhibit No. PNG-18
Page 26 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. E. Uncased highway/railroad crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 47.0979
[6 empty] | Subtotal: | 293.0417
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 59.003 | 295.0149
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 2354.8965
Material | [6 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 1000
sales tax @ | 5% | [5 empty] | 50
[6 empty] | Subtotal: | 1050
|  |  |  | Total Direct Costs (4) = |  |  | 3697.9382
Summary: Uncased Highway/Railroad Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 5342.3806
2. Excavate and cap pipe ends | [6 empty] | 17690.2588
3. Fill pipe with grout, backfill trench, grade disturbed areas | [6 empty] | 8340.3093
4. Restore sites | [6 empty] | 3697.9382
|  |  |  | Pipeline contractor direct costs: |  |  | 35070.8869
|  |  |  | 5% Mobilization |  |  | 1753.5443
[6 empty] | Subtotal: | 36824.4312
|  |  |  | 15% Contractor overhead: |  |  | 5523.6647
[6 empty] | Subtotal: | 42348.0959
|  |  |  | 10% Contractor profit: |  |  | 4234.8096
|  |  |  | Total pipeline contractor costs: |  |  | 46582.9055
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
2329.1453
|  |  |  | Total environmental contractor cost: |  |  | 2329.1453
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 4
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2000
Exhibit No. PNG-18
Page 27 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. E. Uncased highway/railroad crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
7636.8076
|  |  |  | Total management and overhead cost: |  |  | 7636.8076
|  | Total cost to retire an uncased crossing (A + B + C + D): |  |  |  |  | 58549
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of uncased highway crossings: |  |  |  |  | 174
| Item E. 1. | Total estimated cost to retire uncased highway crossings: |  |  |  |  | 10187526
|  | No. of uncased railroad crossings: |  |  |  |  | 1
| Item E. 2. | Total estimated cost to retire uncased railroad crossings: |  |  |  |  | 58549
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of uncased highway crossings |  |  |  |  | 125
| Item E. 1. | Total estimated cost to retire uncased highway crossings: |  |  |  |  | 7318625
|  | No. of uncased railroad crossings: |  |  |  |  | 4
| Item E. 2. | Total estimated cost to retire uncased railroad crossings: |  |  |  |  | 234196

## Cased Hwy-RR Crossings
Exhibit No. PNG-18
Page 28 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
F. Cased highway/railroad crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical cased highway/railroad crossing (100 feet).
Work includes ROW fence removal, excavation and shoring of trench, removal of pipe from casing, filling casing
with grout, removal of vent pipes, and restoration of area. Estimate also includes environmental inspection,
pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, cat D-6R |  |  |  | 1 | 5 | 96.5008 | 482.5038
lowboy |  |  |  | 1 | 5 | 65.4034 | 327.0169
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 1274.5189
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 2 | 5 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 5 | 93.7967 | 468.9834
helper |  |  |  | 1 | 5 | 56.278 | 281.39
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3988.0997
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 79.762
|  |  |  | Total Direct Costs (1) = |  |  | 5342.3806
2. Excavate and remove pipe from casing (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
dozer, Cat D-6R w winch |  |  |  | 1 | 20 | 104.9663 | 2099.3254
hydrocrane, Grove, 30 ton |  |  |  | 1 | 20 | 71.8307 | 1436.6142
pipe truck |  |  |  | 1 | 20 | 61.9526 | 1239.052
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 391.6245
[6 empty] | Subtotal: | 7680.8423
Exhibit No. PNG-18
Page 29 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. F. Cased highway/railroad crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator (dozer, backhoe) |  |  |  | 2 | 20 | 81.563 | 3262.5182
operator (hydrocrane) |  |  |  | 1 | 20 | 81.8785 | 1637.5696
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 12 |  | 90 | 2160
[6 empty] | Subtotal: | 19581.2274
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 391.6245
[6 empty] | Subtotal: | 391.6245
|  |  |  | Total Direct Costs (2) = |  |  | 27653.6943
3. Fill casing with grout, backfill trench, grade disturbed areas (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
dump truck 8 cy |  |  |  | 1 | 20 | 25.8304 | 516.608
grout pump, trailer mounted |  |  |  | 1 | 20 | 18.6968 | 373.9354
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 224.6169
[6 empty] | Subtotal: | 2549.7565
Labor |  |  |  | No. | Hours | Rate | Total
operator (backhoe) |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 7 |  | 90 | 1260
[6 empty] | Subtotal: | 11230.8452
Material | [6 empty] | Total
Grout (cy) | 98 | 13 | cy | (Note: assumes 24" pipe) |  |  | 1274
Sales tax @ | 5% | [5 empty] | 63.7
Miscellaneous 2% of labor | [6 empty] | 224.6169
[6 empty] | Subtotal: | 1562.3169
|  |  |  | Total Direct Costs (3) = |  |  | 15342.9186
Exhibit No. PNG-18
Page 30 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. F. Cased highway/railroad crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 47.0979
[6 empty] | Subtotal: | 293.0417
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 59.003 | 295.0149
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 2354.8965
Material | [6 empty] | Total
allow $2000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 2000
Sales tax @ | 5% | [5 empty] | 100
[6 empty] | Subtotal: | 2100
|  |  |  | Total Direct Costs (4) = |  |  | 4747.9382
Summary: Cased Highway/Railroad Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 5342.3806
2. Excavate and remove pipe from casing | [6 empty] | 27653.6943
3. Fill casing with grout, backfill trench, grade disturbed areas | [6 empty] | 15342.9186
4. Restore sites | [6 empty] | 4747.9382
|  |  |  | Pipeline contractor direct costs: |  |  | 53086.9317
|  |  |  | 5% Mobilization |  |  | 2654.3466
[6 empty] | Subtotal: | 55741.2783
|  |  |  | 15% Contractor overhead: |  |  | 8361.1917
[6 empty] | Subtotal: | 64102.4701
|  |  |  | 10% Contractor profit: |  |  | 6410.247
|  |  |  | Total pipeline contractor costs: |  |  | 70512.7171
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
3525.6359
|  |  |  | Total environmental contractor cost: |  |  | 3525.6359
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2500
Exhibit No. PNG-18
Page 31 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. F. Cased highway/railroad crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
11480.7529
|  |  |  | Total management and overhead cost: |  |  | 11480.7529
|  | Total cost to retire an uncased crossing (A + B + C + D): |  |  |  |  | 88019
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of cased highway crossings: |  |  |  |  | 25
| Item F. 1. | Total estimated cost to retire cased highway crossings: |  |  |  |  | 2200475
|  | No. of cased railroad crossings: |  |  |  |  | 9
| Item F. 2. | Total estimated cost to retire cased railroad crossings: |  |  |  |  | 792171
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of cased highway crossings |  |  |  |  | 27
| Item F. 1. | Total estimated cost to retire cased highway crossings: |  |  |  |  | 2376513
|  | No. of cased railroad crossings: |  |  |  |  | 7
| Item F. 2. | Total estimated cost to retire cased railroad crossings: |  |  |  |  | 616133

## Small Stream Crossings
Exhibit No. PNG-18
Page 32 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
G. Small stream crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical small stream crossing (100 feet).
River and large stream crossings are not included in this line item. Work includes, excavation and shoring of
trench, capping pipe ends, filling pipe with grout, and restoration of area. Estimate also includes environmental
inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, cat D-6R |  |  |  | 1 | 5 | 96.5008 | 482.5038
lowboy |  |  |  | 1 | 5 | 65.4034 | 327.0169
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 1274.5189
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 2 | 5 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 5 | 93.7967 | 468.9834
helper |  |  |  | 1 | 5 | 56.278 | 281.39
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3988.0997
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 79.762
|  |  |  | Total Direct Costs (1) = |  |  | 5342.3806
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 291.8468
[6 empty] | Subtotal: | 2806.073
Exhibit No. PNG-18
Page 33 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. G. Small stream crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 14592.339
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 291.8468
[6 empty] | Subtotal: | 291.8468
|  |  |  | Total Direct Costs (2) = |  |  | 17690.2588
3. Fill pipe with grout, backfill trench, grade disturbed areas (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 10 | 48.6641 | 486.6407
dump truck 8 cy |  |  |  | 1 | 10 | 25.8304 | 258.304
grout pump, trailer mounted |  |  |  | 1 | 10 | 18.6968 | 186.9677
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 112.3085
[6 empty] | Subtotal: | 1274.8783
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
teamster (dump) |  |  |  | 1 | 10 | 59.003 | 590.0299
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 5615.4226
Material | [6 empty] | Total
Grout (cy) | 98 | 13 | cy | (Note: assumes 24" pipe) |  |  | 1274
Sales tax @ | 5% | [5 empty] | 63.7
Miscellaneous (2% of labor) | [6 empty] | 112.3085
[6 empty] | Subtotal: | 1450.0085
|  |  |  | Total Direct Costs (3) = |  |  | 8340.3093
Exhibit No. PNG-18
Page 34 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. G. Small stream crossings (continued)
4. Restore sites (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 47.0979
[6 empty] | Subtotal: | 293.0417
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 59.003 | 295.0149
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 6 |  | 90 | 270
[6 empty] | Subtotal: | 2354.8965
Material | [6 empty] | Total
allow $ 1000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 1000
Sales tax @ | 5% | [5 empty] | 50
[6 empty] | Subtotal: | 1050
|  |  |  | Total Direct Costs (4) = |  |  | 3697.9382
Summary: Small Stream Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 5342.3806
2. Excavate and cap pipe ends | [6 empty] | 17690.2588
3. Fill pipe with grout, backfill trench, grade disturbed areas | [6 empty] | 8340.3093
4. Restore sites | [6 empty] | 3697.9382
|  |  |  | Pipeline contractor direct costs: |  |  | 35070.8869
|  |  |  | 5% Mobilization |  |  | 1753.5443
[6 empty] | Subtotal: | 36824.4312
|  |  |  | 15% Contractor overhead: |  |  | 5523.6647
[6 empty] | Subtotal: | 42348.0959
|  |  |  | 10% Contractor profit: |  |  | 4234.8096
|  |  |  | Total pipeline contractor costs: |  |  | 46582.9055
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
2329.1453
|  |  |  | Total environmental contractor cost: |  |  | 2329.1453
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 4
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 2000
Exhibit No. PNG-18
Page 35 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. G. Small stream crossings (continued)
D. Pipeline company management and overhead costs (15% of A + B + C)
7636.8076
|  |  |  | Total management and overhead cost: |  |  | 7636.8076
|  | Total cost to retire a small stream crossing (A + B + C + D): |  |  |  |  | 58549
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of small stream crossings: |  |  |  |  | 188
| Item G. | Total estimated cost to retire small stream crossings: |  |  |  |  | 11007212
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of small stream crossings: |  |  |  |  | 106
| Item G. | Total estimated cost to retire small stream crossings: |  |  |  |  | 6206194

## HDD Crossings
Exhibit No. PNG-18
Page 36 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
H. River and large stream crossings
1. HDD crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical HDD crossing. Work includes ROW
fence removal, excavation and shoring of trench, capping pipe ends, filling pipe with water, and restoration
of area. Estimate also includes environmental inspection, pipeline company inspection, and pipeline company
management and overhead.
1. Remove ROW fence and access work sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, cat D-6R |  |  |  | 1 | 20 | 96.5008 | 1930.0152
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 5098.0756
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 15952.3988
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 319.048
|  |  |  | Total Direct Costs (1) = |  |  | 21369.5223
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 4141.3418
Exhibit No. PNG-18
Page 37 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 1. HDD crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 15952.3988
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 319.048
|  |  |  | Total Direct Costs (2) = |  |  | 20412.7885
3. Fill pipe with water (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
water pump, 6" dia. with hose |  |  |  | 1 | 10 | 19.5544 | 195.5442
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
lights, trailer mounted |  |  |  | 1 | 10 | 8.294 | 82.9398
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 79.6114
[6 empty] | Subtotal: | 734.6542
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 67.4504 | 674.5043
teamster |  |  |  | 1 | 10 | 59.003 | 590.0299
laborer |  |  |  | 2 | 10 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 5 |  | 90 | 450
[6 empty] | Subtotal: | 3980.5701
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 79.6114
[6 empty] | Subtotal: | 79.6114
|  |  |  | Total Direct Costs (3) = |  |  | 4794.8357
Exhibit No. PNG-18
Page 38 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 1. HDD crossings (continued)
4. Backfill trench, grade disturbed areas (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
dump truck 8 cy |  |  |  | 1 | 20 | 25.8304 | 516.608
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 251.8181
[6 empty] | Subtotal: | 3511.0899
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 8 |  | 90 | 1440
[6 empty] | Subtotal: | 12590.905
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 251.8181
[6 empty] | Subtotal: | 251.8181
|  |  |  | Total Direct Costs (4) = |  |  | 16353.813
5. Restore sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 188.3917
[6 empty] | Subtotal: | 1172.1667
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 6 |  | 90 | 1080
[6 empty] | Subtotal: | 9419.5862
Material | [6 empty] | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 2000
Sales tax @ | 5% | [5 empty] | 100
[6 empty] | Subtotal: | 2100
|  |  |  | Total Direct Costs (5) = |  |  | 12691.7529
Exhibit No. PNG-18
Page 39 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 1. HDD crossings (continued)
Summary: River and Large Stream HDD Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 21369.5223
2. Excavate and cap pipe ends | [6 empty] | 20412.7885
3. Fill pipe with water | [6 empty] | 4794.8357
4. Backfill trench, grade disturbed areas | [6 empty] | 16353.813
5. Restore sites | [6 empty] | 12691.7529
|  |  |  | Pipeline contractor direct costs: |  |  | 75622.7124
|  |  |  | 5% Mobilization |  |  | 3781.1356
[6 empty] | Subtotal: | 79403.8481
|  |  |  | 15% Contractor overhead: |  |  | 11910.5772
[6 empty] | Subtotal: | 91314.4253
|  |  |  | 10% Contractor profit: |  |  | 9131.4425
|  |  |  | Total pipeline contractor costs: |  |  | 100445.8678
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
5022.2934
|  |  |  | Total environmental contractor cost: |  |  | 5022.2934
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 9
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 4500
D. Pipeline company management and overhead costs (15% of A + B + C)
16495.2242
|  |  |  | Total management and overhead cost: |  |  | 16495.2242
|  | Total cost to retire an HDD crossing (A + B + C + D): |  |  |  |  | 126463
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of HDD crossings: |  |  |  |  | 12
| Item H. 1. | Total estimated cost to retire HDD crossings: |  |  |  |  | 1517556
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of HDD crossings: |  |  |  |  | 7
| Item H. 1. | Total estimated cost to retire HDD crossings: |  |  |  |  | 885241

## Trench Crossings
Exhibit No. PNG-18
Page 40 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
H. River and large stream crossings
2. Trench crossings
Description of Work:
Detailed cost estimate below reflects work required to retire a typical trench crossing (125 feet). Work
includes ROW fence removal, excavation and shoring of trench, capping pipe ends, filling pipe with grout, and
restoration of area. Estimate also includes environmental inspection, pipeline company inspection, and pipeline
company management and overhead.
1. Remove ROW fence and access work sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
dozer, cat D-6R |  |  |  | 1 | 20 | 96.5008 | 1930.0152
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 5098.0756
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 15952.3988
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 319.048
|  |  |  | Total Direct Costs (1) = |  |  | 21369.5223
2. Excavate and cap pipe ends (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
3/4 ton pick-up with trailer |  |  |  | 1 | 20 | 27.8585 | 557.1698
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 4141.3418
Exhibit No. PNG-18
Page 41 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 2. Trench crossings (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
pipefitter/welder |  |  |  | 1 | 20 | 93.7967 | 1875.9336
helper |  |  |  | 1 | 20 | 56.278 | 1125.5602
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 10 |  | 90 | 1800
[6 empty] | Subtotal: | 15952.3988
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 319.048
[6 empty] | Subtotal: | 319.048
|  |  |  | Total Direct Costs (2) = |  |  | 20412.7885
3. Fill pipe with grout (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
grout pump, trailer mounted |  |  |  | 1 | 10 | 34.6591 | 346.5915
lights, trailer mounted |  |  |  | 1 | 10 | 8.294 | 82.9398
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 95.8853
[6 empty] | Subtotal: | 756.074
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 67.4504 | 674.5043
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 6 |  | 90 | 540
[6 empty] | Subtotal: | 4794.2675
Material | [6 empty] | Total
Grout (cy) | 98 | 16 | cy | (Note: assumes 24" pipe) |  |  | 1568
Sales tax @ | 5% | [5 empty] | 78.4
Miscellaneous (2% of labor) | [6 empty] | 95.8853
[6 empty] | Subtotal: | 1742.2853
|  |  |  | Total Direct Costs (3) = |  |  | 7292.6269
Exhibit No. PNG-18
Page 42 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 2. Trench crossings (continued)
4. Backfill trench, grade disturbed areas (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 20 | 48.6641 | 973.2814
dump truck 8 cy |  |  |  | 1 | 20 | 25.8304 | 516.608
lowboy |  |  |  | 1 | 20 | 65.4034 | 1308.0676
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 251.8181
[6 empty] | Subtotal: | 3511.0899
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 2 | 20 | 59.003 | 2360.1195
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 8 |  | 90 | 1440
[6 empty] | Subtotal: | 12590.905
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 251.8181
[6 empty] | Subtotal: | 251.8181
|  |  |  | Total Direct Costs (4) = |  |  | 16353.813
5. Restore sites (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 188.3917
[6 empty] | Subtotal: | 1172.1667
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 6 |  | 90 | 1080
[6 empty] | Subtotal: | 9419.5862
Material | [6 empty] | Total
allow $ 2000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 2000
Sales tax @ | 5% | [5 empty] | 100
[6 empty] | Subtotal: | 2100
|  |  |  | Total Direct Costs (5) = |  |  | 12691.7529
Exhibit No. PNG-18
Page 43 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. H. 2. Trench crossings (continued)
Summary: River and Large Stream Trench Crossings
A. Pipeline contractor costs
1. Remove ROW fence and access work sites | [6 empty] | 21369.5223
2. Excavate and cap pipe ends | [6 empty] | 20412.7885
3. Fill pipe with grout | [6 empty] | 7292.6269
4. Backfill trench, grade disturbed areas | [6 empty] | 16353.813
5. Restore sites | [6 empty] | 12691.7529
|  |  |  | Pipeline contractor direct costs: |  |  | 78120.5036
|  |  |  | 5% Mobilization |  |  | 3906.0252
[6 empty] | Subtotal: | 82026.5287
|  |  |  | 15% Contractor overhead: |  |  | 12303.9793
[6 empty] | Subtotal: | 94330.5081
|  |  |  | 10% Contractor profit: |  |  | 9433.0508
|  |  |  | Total pipeline contractor costs: |  |  | 103763.5589
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
5188.1779
|  |  |  | Total environmental contractor cost: |  |  | 5188.1779
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 9
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 4500
D. Pipeline company management and overhead costs (15% of A + B + C)
17017.7605
|  |  |  | Total management and overhead cost: |  |  | 17017.7605
|  | Total cost to retire a trench crossing (A + B + C + D): |  |  |  |  | 130469
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of trench crossings: |  |  |  |  | 16
| Item H. 2. | Total estimated cost to retire trench crossings: |  |  |  |  | 2087504
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of trench crossings: |  |  |  |  | 9
| Item H. 2. | Total estimated cost to retire trench crossings: |  |  |  |  | 1174221

## Remote Valve
Exhibit No. PNG-18
Page 44 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
I. Remote valve sites
Description of Work:
Detailed cost estimate below reflects work required to retire a typical remote valve site. Work includes
ROW fence removal, excavation, removal of valves and blowdowns, capping pipelines, excavation of gravel,
and restoration of area. Estimate also includes environmental inspection, pipeline company inspection, and
pipeline company management and overhead.
1. Remove ROW fence and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 5 | 48.6641 | 243.3203
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
lowboy |  |  |  | 1 | 5 | 65.4034 | 327.0169
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 11.5329 | 57.6643
small tools, 2% of labor | [6 empty] | 64.8247
[6 empty] | Subtotal: | 962.7338
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 2 | 5 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 5 | 93.7967 | 468.9834
helper |  |  |  | 1 | 5 | 56.278 | 281.39
laborer |  |  |  | 2 | 5 | 65.6864 | 656.8636
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 8 |  | 90 | 360
[6 empty] | Subtotal: | 3241.2361
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 64.8247
[6 empty] | Subtotal: | 64.8247
|  |  |  | Total Direct Costs (1) = |  |  | 4268.7946
2. Excavate, remove valves and blowdowns, cap pipe ends (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 10 | 48.6641 | 486.6407
crane, Grove 30 ton |  |  |  | 1 | 10 | 71.8307 | 718.3071
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 27.8585 | 278.5849
1/2 ton pickup with 4wd |  |  |  | 1 | 10 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 134.2245
[6 empty] | Subtotal: | 1994.316
Exhibit No. PNG-18
Page 45 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. I. Remote valve sites (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
operator (crane) |  |  |  | 1 | 10 | 81.8785 | 818.7848
teamster |  |  |  | 1 | 10 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 10 | 93.7967 | 937.9668
helper |  |  |  | 1 | 10 | 56.278 | 562.7801
laborer |  |  |  | 2 | 10 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 8 |  | 90 | 720
[6 empty] | Subtotal: | 6711.2271
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 134.2245
[6 empty] | Subtotal: | 134.2245
|  |  |  | Total Direct Costs (2) = |  |  | 8839.7677
3. Remove gravel and miscellaneous debris, grade disturbed area (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 5 | 48.6641 | 243.3203
dump truck, 8 cy |  |  |  | 1 | 5 | 25.8304 | 129.152
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 11.5329 | 57.6643
small tools, 2% of labor | [6 empty] | 41.217
[6 empty] | Subtotal: | 471.3537
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 1 | 5 | 59.003 | 295.0149
laborer |  |  |  | 2 | 5 | 65.6864 | 656.8636
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 5 |  | 90 | 225
[6 empty] | Subtotal: | 2060.8477
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 41.217
[6 empty] | Subtotal: | 41.217
|  |  |  | Total Direct Costs (3) = |  |  | 2573.4183
Exhibit No. PNG-18
Page 46 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. I. Remote valve sites (continued)
4. Restore site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 11.5329 | 57.6643
small tools, 2% of labor | [6 empty] | 34.4167
[6 empty] | Subtotal: | 222.6961
Labor |  |  |  | No. | Hours | Rate | Total
teamster |  |  |  | 1 | 5 | 81.563 | 407.8148
laborer |  |  |  | 2 | 5 | 65.6864 | 656.8636
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 4 |  | 90 | 180
[6 empty] | Subtotal: | 1720.8328
Material | [6 empty] | Total
allow $ 1000 for backfill, topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 1000
Sales tax @ | 5% | [5 empty] | 50
[6 empty] | Subtotal: | 1050
|  |  |  | Total Direct Costs (4) = |  |  | 2993.5288
Summary: Remote Valve Sites
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 4268.7946
2. Excavate, remove valves and blowdowns, cap pipe ends | [6 empty] | 8839.7677
3. Remove gravel and miscellaneous debris | [6 empty] | 2573.4183
4. Restore site | [6 empty] | 2993.5288
|  |  |  | Pipeline contractor direct costs: |  |  | 18675.5094
|  |  |  | 5% Mobilization |  |  | 933.7755
[6 empty] | Subtotal: | 19609.2849
|  |  |  | 15% Contractor overhead: |  |  | 2941.3927
[6 empty] | Subtotal: | 22550.6776
|  |  |  | 10% Contractor profit: |  |  | 2255.0678
|  |  |  | Total pipeline contractor costs: |  |  | 24805.7454
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence of
hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
1240.2873
|  |  |  | Total environmental contractor cost: |  |  | 1240.2873
Exhibit No. PNG-18
Page 47 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. I. Remote valve sites (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 2.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 1250
D. Pipeline company management and overhead costs (15% of A + B + C)
4094.4049
|  |  |  | Total management and overhead cost: |  |  | 4094.4049
|  | Total cost to retire a remote valve site (A + B + C + D): |  |  |  |  | 31390
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of remote valve sites: |  |  |  |  | 15
| Item I. | Total estimated cost to retire remote valves: |  |  |  |  | 470850
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of remote valve sites: |  |  |  |  | 16
| Item I. | Total estimated cost to retire remote valves: |  |  |  |  | 502240

## Cathodic Protection
Exhibit No. PNG-18
Page 48 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
J. Cathodic protection facilities
Description of Work:
Detailed cost estimate below reflects work required to remove cathodic protection test sites and rectifiers.
Work includes removal of test sites and rectifiers and associated electrical equipment. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove test sites
Equipment |  |  |  | No. | Hours | Rate | Total
1/2 ton pickup with 4wd |  |  |  | 1 | 1 | 11.5329 | 11.5329
small tools, 2% of labor | [6 empty] | 5.0721
[6 empty] | Subtotal: | 16.6049
Labor |  |  |  | No. | Hours | Rate | Total
laborer |  |  |  | 2 | 1 | 65.6864 | 131.3727
foreman |  |  |  | 1 | 1 | 95.2309 | 95.2309
per diem | 0.1 | day | crew size: | 3 |  | 90 | 27
[6 empty] | Subtotal: | 253.6036
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 5.0721
[6 empty] | Subtotal: | 5.0721
|  |  |  | Total Direct Costs (1) = |  |  | 275.2806
Summary: Remove Test Sites
A. Pipeline contractor costs
|  |  |  | Pipeline contractor direct costs: |  |  | 275.2806
|  |  |  | 5% Mobilization |  |  | 13.764
[6 empty] | Subtotal: | 289.0446
|  |  |  | 15% Contractor overhead: |  |  | 43.3567
[6 empty] | Subtotal: | 332.4013
|  |  |  | 10% Contractor profit: |  |  | 33.2401
|  |  |  | Total pipeline contractor costs: |  |  | 365.6415
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
18.2821
|  |  |  | Total environmental contractor cost: |  |  | 18.2821
Exhibit No. PNG-18
Page 49 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. J. Cathodic protection facilities (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 0.1
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 50
D. Pipeline company management and overhead costs (15% of A + B + C)
65.0885
|  |  |  | Total management and overhead cost: |  |  | 65.0885
|  |  | Total cost to remove a C.P. test site (A + B + C + D): |  |  |  | 499
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of cathodic protection test sites: |  |  |  |  | 246
| Item J.1 | Total estimated cost to retire cathodic protection test sites: |  |  |  |  | 122754
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of cathodic protection test sites: |  |  |  |  | 160
| Item J.1 | Total estimated cost to retire cathodic protection test sites: |  |  |  |  | 79840
2. Remove rectifiers
Equipment |  |  |  | No. | Hours | Rate | Total
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 1 | 5 | 11.5329 | 57.6643
small tools, 2% of labor | [6 empty] | 26.9093
[6 empty] | Subtotal: | 223.8661
Labor |  |  |  | No. | Hours | Rate | Total
electrician |  |  |  | 1 | 5 | 91.7888 | 458.944
helper |  |  |  | 1 | 5 | 55.0733 | 275.3664
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 3 |  | 90 | 135
[6 empty] | Subtotal: | 1345.4648
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 26.9093
[6 empty] | Subtotal: | 26.9093
|  |  |  | Total Direct Costs (1) = |  |  | 1596.2402
Exhibit No. PNG-18
Page 50 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. J. Cathodic protection facilities (continued)
Summary: Remove Rectifiers
A. Pipeline contractor costs
|  |  |  | Pipeline contractor direct costs: |  |  | 1596.2402
|  |  |  | 5% Mobilization |  |  | 79.812
[6 empty] | Subtotal: | 1676.0522
|  |  |  | 15% Contractor overhead: |  |  | 251.4078
[6 empty] | Subtotal: | 1927.46
|  |  |  | 10% Contractor profit: |  |  | 192.746
|  |  |  | Total pipeline contractor costs: |  |  | 2120.206
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
106.0103
|  |  |  | Total environmental contractor cost: |  |  | 106.0103
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 0.5
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 250
D. Pipeline company management and overhead costs (15% of A + B + C)
371.4325
|  |  |  | Total management and overhead cost: |  |  | 371.4325
|  |  | Total cost to remove a rectifier (A + B + C + D): |  |  |  | 2848
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of rectifiers |  |  |  |  | 7
| Item J. 2. | Total estimated cost to remove rectifiers: |  |  |  |  | 19936
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of rectifiers |  |  |  |  | 12
| Item J. 2. | Total estimated cost to remove rectifiers: |  |  |  |  | 34176

## Pipeline Marker
Exhibit No. PNG-18
Page 51 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
K. Pipeline markers
Description of Work:
Detailed cost estimate below reflects work required to remove a pipeline marker.
1. Remove pipeline marker
Equipment |  |  |  | No. | Hours | Rate | Total
1/2 ton pickup with 4wd |  |  |  | 1 | 0.25 | 11.5329 | 2.8832
small tools, 2% of labor | [6 empty] | 1.133
[6 empty] | Subtotal: | 4.0162
Labor |  |  |  | No. | Hours | Rate | Total
laborer |  |  |  | 2 | 0.25 | 65.6864 | 32.8432
foreman |  |  |  | 1 | 0.25 | 95.2309 | 23.8077
[6 empty] | Subtotal: | 56.6509
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1.133
[6 empty] | Subtotal: | 1.133
|  |  |  | Total Direct Costs (1) = |  |  | 61.8002
Summary: Pipeline Markers
A. Pipeline contractor costs
|  |  |  | Pipeline contractor direct costs: |  |  | 61.8002
[6 empty] | Subtotal: | 61.8002
|  |  |  | 5% Mobilization |  |  | 3.09
[6 empty] | Subtotal: | 64.8902
|  |  |  | 15% Contractor overhead: |  |  | 9.7335
[6 empty] | Subtotal: | 74.6237
|  |  |  | 10% Contractor profit: |  |  | 7.4624
|  |  |  | Total pipeline contractor costs: |  |  | 82.0861
B. Pipeline company management and overhead costs (15% of A) | [6 empty] | 12.3129
|  |  |  | Total management and overhead cost: |  |  | 12.3129
|  |  | Total cost to remove a pipeline marker (A + B): |  |  |  | 94
Exhibit No. PNG-18
Page 52 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. K. Pipeline markers (continued)
Wholly-owned facilities (24" mainline and associated laterals)
|  | No. of pipeline markers: |  |  |  |  | 1878
| Item K. | Total estimated cost to retire small M&R stations |  |  |  |  | 176532
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of pipeline markers: |  |  |  |  | 1064
| Item K. | Total estimated cost to retire small M&R stations |  |  |  |  | 100016

## Small M&R
Exhibit No. PNG-18
Page 53 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
L. M&R stations
1. Small M&R stations
Description of Work:
Detailed cost estimate below reflects work required to retire a typical small M&R station. Work includes
ROW fence removal, excavation, removal of valves, blowdowns, meter piping and equipment, removal of meter
and control building(s), capping pipelines, excavation of gravel, and restoration of area. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work site (1/2 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 5 | 48.6641 | 243.3203
flatbed truck |  |  |  | 1 | 5 | 26.123 | 130.615
lowboy |  |  |  | 1 | 5 | 65.4034 | 327.0169
3/4 ton pick-up with trailer |  |  |  | 1 | 5 | 27.8585 | 139.2925
1/2 ton pickup with 4wd |  |  |  | 2 | 5 | 11.5329 | 115.3287
small tools, 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 1035.3354
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 5 | 81.563 | 407.8148
teamster |  |  |  | 2 | 5 | 59.003 | 590.0299
pipefitter/welder |  |  |  | 1 | 5 | 93.7967 | 468.9834
helper |  |  |  | 1 | 5 | 56.278 | 281.39
laborer |  |  |  | 4 | 5 | 65.6864 | 1313.7272
foreman |  |  |  | 1 | 5 | 95.2309 | 476.1544
per diem | 0.5 | day | crew size: | 10 |  | 90 | 450
[6 empty] | Subtotal: | 3988.0997
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 79.762
[6 empty] | Subtotal: | 79.762
|  |  |  | Total Direct Costs (1) = |  |  | 5103.1971
2. Excavate, remove valves and blowdowns, cap pipe ends, demolish meter and control building(s), remove
meter run (5 days).
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D w hammer |  |  |  | 1 | 50 | 67.0581 | 3352.907
hydrocrane, Grove 30 ton |  |  |  | 1 | 50 | 71.8307 | 3591.5355
flatbed truck |  |  |  | 1 | 50 | 26.123 | 1306.1505
3/4 ton pick-up with trailer |  |  |  | 2 | 50 | 27.8585 | 2785.849
1/2 ton pickup with 4wd |  |  |  | 2 | 50 | 11.5329 | 1153.287
small tools, 2% of labor | [6 empty] | 988.5701
[6 empty] | Subtotal: | 13178.2991
Exhibit No. PNG-18
Page 54 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 1. Small M&R stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 50 | 81.563 | 4078.1477
operator (hydrocrane) |  |  |  | 1 | 50 | 81.8785 | 4093.9239
teamster |  |  |  | 1 | 50 | 59.003 | 2950.1494
pipefitter/welder |  |  |  | 2 | 50 | 93.7967 | 9379.668
helper |  |  |  | 2 | 50 | 56.278 | 5627.8008
laborer |  |  |  | 4 | 50 | 65.6864 | 13137.272
foreman |  |  |  | 1 | 50 | 95.2309 | 4761.544
per diem | 5 | days | crew size: | 12 |  | 90 | 5400
[6 empty] | Subtotal: | 49428.5058
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 988.5701
[6 empty] | Subtotal: | 988.5701
|  |  |  | Total Direct Costs (2) = |  |  | 63595.375
3. Remove gravel and miscellaneous debris (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953D |  |  |  | 1 | 10 | 65.9684 | 659.6842
dump truck 14 cy |  |  |  | 2 | 10 | 45.2839 | 905.6784
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 125.909
[6 empty] | Subtotal: | 1921.929
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
teamster |  |  |  | 2 | 10 | 59.003 | 1180.0598
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 8 |  | 90 | 720
[6 empty] | Subtotal: | 6295.4525
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 125.909
[6 empty] | Subtotal: | 125.909
|  |  |  | Total Direct Costs (3) = |  |  | 8343.2906
Exhibit No. PNG-18
Page 55 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 1. Small M&R stations (continued)
4. Restore site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953D |  |  |  | 1 | 10 | 65.9684 | 659.6842
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 112.3085
[6 empty] | Subtotal: | 1263.8802
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
teamster |  |  |  | 1 | 10 | 59.003 | 590.0299
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 7 |  | 90 | 630
[6 empty] | Subtotal: | 5615.4226
Material | [6 empty] | Total
allow $ 5000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 5000
Sales tax @ | 5% | [5 empty] | 250
[6 empty] | Subtotal: | 5250
|  |  |  | Total Direct Costs (4) = |  |  | 12129.3028
Summary: Small M&R Stations
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 5103.1971
2. Excavate, remove valves and blowdowns, cap pipe ends | [6 empty] | 63595.375
3. Remove gravel and miscellaneous debris | [6 empty] | 8343.2906
4. Restore site | [6 empty] | 12129.3028
|  |  |  | Pipeline contractor direct costs: |  |  | 89171.1655
|  |  |  | 5% Mobilization |  |  | 4458.5583
[6 empty] | Subtotal: | 93629.7238
|  |  |  | 15% Contractor overhead: |  |  | 14044.4586
[6 empty] | Subtotal: | 107674.1824
|  |  |  | 10% Contractor profit: |  |  | 10767.4182
|  |  |  | Total pipeline contractor costs: |  |  | 118441.6006
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
5922.08
|  |  |  | Total environmental contractor cost: |  |  | 5922.08
Exhibit No. PNG-18
Page 56 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 1. Small M&R stations (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 7.5
2. Company cost per day | [6 empty] | 500
|  | Total company inspection cost per site: |  |  |  |  | 3750
D. Pipeline company management and overhead costs (15% of A + B + C)
19217.0521
|  |  |  | Total management and overhead cost: |  |  | 19217.0521
|  | Total cost to retire a small M&R station (A + B + C + D): |  |  |  |  | 147331
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of small M&R stations |  |  |  |  | 6
| Item L. 1. | Total estimated cost to retire small M&R stations |  |  |  |  | 883986
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of small M&R stations |  |  |  |  | 9
| Item L. 1. | Total estimated cost to retire small M&R stations: |  |  |  |  | 1325979

## Medium M&R
Exhibit No. PNG-18
Page 57 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. Pipeline Retirement
L. M&R stations
2. Medium M&R stations
Description of Work:
Detailed cost estimate below reflects work required to retire a typical medium M&R station. Work includes
ROW fence removal, excavation, removal of valves, blowdowns, meter piping and equipment, removal of meter
and control building(s), capping pipelines, excavation of gravel, and restoration of area. Estimate also includes
environmental inspection, pipeline company inspection, and pipeline company management and overhead.
1. Remove ROW fence and access work site (1 day)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D |  |  |  | 1 | 10 | 48.6641 | 486.6407
flatbed truck |  |  |  | 1 | 10 | 26.123 | 261.2301
lowboy |  |  |  | 1 | 10 | 65.4034 | 654.0338
3/4 ton pick-up with trailer |  |  |  | 1 | 10 | 27.8585 | 278.5849
1/2 ton pickup with 4wd |  |  |  | 2 | 10 | 11.5329 | 230.6574
small tools, 2% of labor | [6 empty] | 159.524
[6 empty] | Subtotal: | 2070.6709
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 10 | 81.563 | 815.6295
teamster |  |  |  | 2 | 10 | 59.003 | 1180.0598
pipefitter/welder |  |  |  | 1 | 10 | 93.7967 | 937.9668
helper |  |  |  | 1 | 10 | 56.278 | 562.7801
laborer |  |  |  | 4 | 10 | 65.6864 | 2627.4544
foreman |  |  |  | 1 | 10 | 95.2309 | 952.3088
per diem | 1 | day | crew size: | 10 |  | 90 | 900
[6 empty] | Subtotal: | 7976.1994
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 159.524
[6 empty] | Subtotal: | 159.524
|  |  |  | Total Direct Costs (1) = |  |  | 10206.3943
2. Excavate, remove valves, blowdowns, cap pipe ends, demolish control bldgs and meter runs (10 days)
Equipment |  |  |  | No. | Hours | Rate | Total
backhoe, Cat 320D w hammer |  |  |  | 1 | 100 | 67.0581 | 6705.814
hydrocrane, Grove 30 ton |  |  |  | 1 | 100 | 71.8307 | 7183.071
flatbed truck |  |  |  | 1 | 100 | 26.123 | 2612.301
3/4 ton pick-up with trailer |  |  |  | 2 | 100 | 27.8585 | 5571.698
1/2 ton pickup with 4wd |  |  |  | 2 | 100 | 11.5329 | 2306.574
small tools, 2% of labor | [6 empty] | 1977.1402
[6 empty] | Subtotal: | 26356.5982
Exhibit No. PNG-18
Page 58 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 2. Medium M&R stations (continued)
Line Item 2 (continued)
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 100 | 81.563 | 8156.2954
operator (hydrocrane) |  |  |  | 1 | 100 | 81.8785 | 8187.8478
teamster |  |  |  | 1 | 100 | 59.003 | 5900.2988
pipefitter/welder |  |  |  | 2 | 100 | 93.7967 | 18759.336
helper |  |  |  | 2 | 100 | 56.278 | 11255.6016
laborer |  |  |  | 4 | 100 | 65.6864 | 26274.544
foreman |  |  |  | 1 | 100 | 95.2309 | 9523.088
per diem | 10 | days | crew size: | 12 |  | 90 | 10800
[6 empty] | Subtotal: | 98857.0116
Material | [6 empty] | Total
allow 2% of labor | [6 empty] | 1977.1402
[6 empty] | Subtotal: | 1977.1402
|  |  |  | Total Direct Costs (2) = |  |  | 127190.7501
3. Remove gravel and miscellaneous debris (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953D |  |  |  | 1 | 20 | 65.9684 | 1319.3684
dump truck 14 cy |  |  |  | 3 | 20 | 45.2839 | 2717.0352
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 279.0193
[6 empty] | Subtotal: | 4776.7377
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 3 | 20 | 59.003 | 3540.1793
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 9 |  | 90 | 1620
[6 empty] | Subtotal: | 13950.9648
Material | [6 empty] | Total
Miscellaneous (2% of labor) | [6 empty] | 279.0193
[6 empty] | Subtotal: | 279.0193
|  |  |  | Total Direct Costs (3) = |  |  | 19006.7218
Exhibit No. PNG-18
Page 59 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 2. Medium M&R stations (continued)
4. Restore site (2 days)
Equipment |  |  |  | No. | Hours | Rate | Total
track loader, Cat 953D |  |  |  | 1 | 20 | 65.9684 | 1319.3684
flatbed truck |  |  |  | 1 | 20 | 26.123 | 522.4602
1/2 ton pickup with 4wd |  |  |  | 2 | 20 | 11.5329 | 461.3148
small tools, 2% of labor | [6 empty] | 224.6169
[6 empty] | Subtotal: | 2527.7603
Labor |  |  |  | No. | Hours | Rate | Total
operator |  |  |  | 1 | 20 | 81.563 | 1631.2591
teamster |  |  |  | 1 | 20 | 59.003 | 1180.0598
laborer |  |  |  | 4 | 20 | 65.6864 | 5254.9088
foreman |  |  |  | 1 | 20 | 95.2309 | 1904.6176
per diem | 2 | days | crew size: | 7 |  | 90 | 1260
[6 empty] | Subtotal: | 11230.8452
Material | [6 empty] | Total
allow $ 10,000 for topsoil, seed, fertilizer, straw bales, etc. | [6 empty] | 10000
Sales tax @ | 5% | [5 empty] | 500
[6 empty] | Subtotal: | 10500
|  |  |  | Total Direct Costs (4) = |  |  | 24258.6055
Summary: Medium M&R Stations
A. Pipeline contractor costs
1. Remove ROW fence and access work site | [6 empty] | 10206.3943
2. Excavate, remove valves and blowdowns, cap pipe ends | [6 empty] | 127190.7501
3. Remove gravel and miscellaneous debris | [6 empty] | 19006.7218
4. Restore site | [6 empty] | 24258.6055
|  |  |  | Pipeline contractor direct costs: |  |  | 180662.4716
|  |  |  | 5% Mobilization |  |  | 9033.1236
[6 empty] | Subtotal: | 189695.5952
|  |  |  | 15% Contractor overhead: |  |  | 28454.3393
[6 empty] | Subtotal: | 218149.9345
|  |  |  | 10% Contractor profit: |  |  | 21814.9934
|  |  |  | Total pipeline contractor costs: |  |  | 239964.9279
B. Environmental contractor costs (5% of pipeline contractor costs)
This section of estimate reflects work performed by environmental contractor to check for the presence
of hazardous materials. Work involves inspection, sampling, evaluation, and report writing.
11998.2464
|  |  |  | Total environmental contractor cost: |  |  | 11998.2464
Exhibit No. PNG-18
Page 60 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
I. L. 2. Medium M&R stations (continued)
C. Pipeline company inspection costs
1. Number of days per site | [6 empty] | 15
2. Company cost per day | [6 empty] | 500
|  |  |  | Total company inspection cost per site: |  |  | 7500
D. Pipeline company management and overhead costs (15% of A + B + C)
38919.4761
|  |  |  | Total management and overhead cost: |  |  | 38919.4761
|  | Total cost to retire a medium M&R station (A + B + C + D): |  |  |  |  | 298383
Wholly-owned facilities (24" Mainline and associated laterals)
|  | No. of medium M&R stations: |  |  |  |  | 1
| Item L. 2. | Total estimated cost to retire medium M&R stations |  |  |  |  | 298383
Jointly-owned facilities (30" Mainline and associated laterals)
|  | No. of medium M&R stations: |  |  |  |  | 3
| Item L. 2. | Total estimated cost to retire medium M&R stations: |  |  |  |  | 895149

## Salvage Scrap
Exhibit No. PNG-18
Page 61 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
II. Salvage
A. Scrap steel
|  |  | Estimated carbon steel scrap value on-site: |  |  |  | -185 | per ton
| 1 | Wholly-owned facilities
[7 empty] | Weight/ | Total | Scrap | Estimated
|  |  |  | Wholly-owned facilities |  |  | Valve | Weight | Value | Salvage
|  | a. | Remote valves |  |  | No. | (ton) | (ton) | (ton) | ($)
|  |  | 1 | Mainline 24" |  | 11 | 4 | 44 | -185 | -8140
|  |  | 2 | Laterals (8", 3-12") |  | 4 | 1 | 4 | -185 | -740
[5 empty] | Total: | 15 |  | 48 |  | -8880
[7 empty] | Weight/ | Total | Scrap | Estimated
|  |  |  | Wholly-owned facilities |  |  | Station | Weight | Value | Salvage
|  | b. | M&R stations (valves, pipe) |  |  | No. | (ton) | (ton) | (ton) | ($)
|  |  | 1 | Small M&R station |  | 6 | 10 | 60 | -185 | -11100
|  |  | 2 | Medium M&R station |  | 1 | 20 | 20 | -185 | -3700
[5 empty] | Total: | 7 |  | 80 |  | -14800
[6 empty] | Length | Wt/ft
[6 empty] | of Pipe | 24-inch | Total | Total | Estimated
|  |  |  | Wholly-owned facilities |  | Removed | Pipe | Weight | Weight | Salvage
|  | c. | Pipe (misc. removal) |  | No. | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | Uncased hwy crossings | 174 | 40 | 103.79 | 722378.4 | 361 | -66785
|  |  | 2 | Uncased RR crossings | 1 | 40 | 103.79 | 4151.6 | 2 | -370
|  |  | 3 | Cased hwy crossings | 25 | 240 | 103.79 | 622740 | 311 | -57535
|  |  | 4 | Cased RR crossings | 9 | 240 | 103.79 | 224186.4 | 112 | -20720
|  |  | 5 | Small stream crossings | 188 | 40 | 103.79 | 780500.8 | 390 | -72150
|  |  | 6 | HDD crossings | 12 | 40 | 103.79 | 49819.2 | 25 | -4625
|  |  | 7 | Trench crossings | 16 | 40 | 103.79 | 66425.6 | 33 | -6105
[5 empty] | Total: |  |  |  | 1234 | -228290
[6 empty] | Length |  | Total | Total | Estimated
|  |  |  | Wholly-owned facilities |  | Removed | Wt/ft | Weight | Weight | Salvage
|  | d. | Pipe removal Option I (a) |  |  | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | 8" |  | 53 | 22.36 | 1185.08 | 1 | -185
|  |  | 2 | 12" |  | 3010 | 35.07 | 105560.7 | 53 | -9805
|  |  | 3 | 24" |  | 10138 | 103.79 | 1052223.02 | 526 | -97310
[5 empty] | Total: | 13201 |  |  | 580 | -107300
[6 empty] | Length |  | Total | Total | Estimated
|  |  |  | Wholly-owned facilities |  | Removed | Wt/ft | Weight | Weight | Salvage
|  | e. | Pipe removal Option II (a) |  |  | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | 8" |  | 3221 | 22.36 | 72021.56 | 36 | -6660
|  |  | 2 | 12" |  | 211570 | 35.07 | 7419759.9 | 3710 | -686350
|  |  | 3 | 24" |  | 702926 | 103.79 | 72956689.54 | 36478 | -6748430
[5 empty] | Total: | 917717 |  |  | 40224 | -7441440
Exhibit No. PNG-18
Page 62 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
II. A. Steel scrap (continued)
| 1 | Wholly-owned facilities (continued)
[6 empty] | Length |  | Total | Total | Estimated
|  |  |  | Wholly-owned facilities |  | Removed | Wt/ft | Weight | Weight | Salvage
|  | f. | Pipe removal Option III (a) |  |  | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | 8" |  | 317 | 22.36 | 7088.12 | 4 | -740
|  |  | 2 | 12" |  | 19958 | 35.07 | 699927.06 | 350 | -64750
|  |  | 3 | 24" |  | 66264 | 103.79 | 6877540.56 | 3439 | -636215
[5 empty] | Total: | 86539 |  |  | 3793 | -701705
| 2 | Jointly-owned facilities (33.24%)
[7 empty] | Weight/ | Total | Scrap | Estimated
|  |  |  | Jointly-owned facilities |  |  | Valve | Weight | Value | Salvage
|  | a. | Remote valves |  |  | No. | (ton) | (ton) | (ton) | ($)
|  |  | 1 | Mainline 30" |  | 13 | 7 | 91 | -185 | -16835
|  |  | 2 | Laterals (12",16",20") |  | 3 | 2 | 6 | -185 | -1110
[5 empty] | Total: | 13 |  | 97 |  | -17945
[7 empty] | Weight/ | Total | Scrap | Estimated
|  |  |  | Jointly-owned facilities |  |  | Station | Weight | Value | Salvage
|  | b. | Remote M&R stations (valves, pipe) |  |  | No. | (ton) | (ton) | (ton) | ($)
|  |  | 1 | Small M&R station |  | 9 | 10 | 90 | -185 | -16650
|  |  | 2 | Medium M&R station |  | 3 | 20 | 60 | -185 | -11100
[5 empty] | Total: | 12 |  | 150 |  | -27750
[6 empty] | Length | Wt/ft
[6 empty] | of Pipe | 30-inch | Total | Total | Estimated
|  |  |  | Jointly-owned facilities |  | Removed | Pipe | Weight | Weight | Salvage
|  | c. | Pipe (misc. removal) |  | No. | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | Uncased hwy crossings | 125 | 40 | 193.93 | 969650 | 485 | -89725
|  |  | 2 | Uncased RR crossings | 4 | 40 | 193.93 | 31028.8 | 16 | -2960
|  |  | 3 | Cased hwy crossings | 27 | 240 | 193.93 | 1256666.4 | 628 | -116180
|  |  | 4 | Cased RR crossings | 7 | 240 | 193.93 | 325802.4 | 163 | -30155
|  |  | 5 | Small stream crossings | 106 | 40 | 193.93 | 822263.2 | 411 | -76035
|  |  | 6 | HDD crossings | 7 | 40 | 193.93 | 54300.4 | 27 | -4995
|  |  | 7 | Trench crossings | 9 | 40 | 193.93 | 69814.8 | 35 | -6475
[5 empty] | Total: |  |  |  | 1765 | -326525
[6 empty] | Length |  | Total | Total | Estimated
|  |  |  | Jointly-owned facilities |  | Removed | Wt/ft | Weight | Weight | Salvage
|  | d. | Pipe removal Option II (b) |  |  | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | 12" |  | 18322 | 35.07 | 642552.54 | 321 | -59385
|  |  | 2 | 16" |  | 5755 | 62.58 | 360147.9 | 180 | -33300
|  |  | 3 | 20" |  | 3802 | 86.19 | 327694.38 | 164 | -30340
|  |  | 4 | 30" |  | 480322 | 193.93 | 93148845.46 | 46574 | -8616190
[5 empty] | Total: | 508201 |  |  | 47239 | -8739215
Exhibit No. PNG-18
Page 63 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
II. A. Steel scrap (continued)
[6 empty] | Length |  | Total | Total | Estimated
|  |  |  | Jointly-owned facilities |  | Removed | Wt/ft | Weight | Weight | Salvage
|  | d. | Pipe removal Option III (b) |  |  | (ft) | (lbs) | (lbs) | (ton) | ($)
|  |  | 1 | 12" |  | 6706 | 35.07 | 235179.42 | 118 | -21830
|  |  | 2 | 16" |  | 0 | 62.58 | 0 | 0 | 0
|  |  | 3 | 20" |  | 0 | 86.19 | 0 | 0 | 0
|  |  | 4 | 30" |  | 57816 | 193.93 | 11212256.88 | 5606 | -1037110
[5 empty] | Total: | 64522 |  |  | 5724 | -1058940
Summary Scrap Steel Salvage
I | Wholly-owned facilities
| A |  | Option I (a) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -8880
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -14800
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -228290
|  | 4 |  | Pipe removal | [5 empty] | -107300
[9 empty] | Total: | -359270
| B. |  | Option II (a) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -8880
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -14800
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -228290
|  | 4 |  | Pipe removal | [5 empty] | -7441440
[9 empty] | Total: | -7693410
| C. |  | Option III (a) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -8880
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -14800
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -228290
|  | 4 |  | Pipe removal | [5 empty] | -701705
[9 empty] | Total: | -953675
Exhibit No. PNG-18
Page 64 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
II. B. Scrap steel (continued)
Summary Scrap Steel Salvage
II. | Jointly-owned facilities (33.24%)
| A |  | Option I (b) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -17945
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -27750
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -326525
|  | 4 |  | Pipe removal | (No pipe removed)
[9 empty] | Total: | -372220
| B. |  | Option II (b) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -17945
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -27750
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -326525
|  | 4 |  | Pipe removal | [5 empty] | -8739215
[9 empty] | Total: | -9111435
| C. |  | Option III (b) | [6 empty] | Salvage
|  | 1 |  | Remote valves | [5 empty] | -17945
|  | 2 |  | Remote M&R stations (valves, pipe) | [5 empty] | -27750
|  | 3 |  | Pipe (misc. removal) | [5 empty] | -326525
|  | 4 |  | Pipe removal | [5 empty] | -1058940
[9 empty] | Total: | -1431160

## Salvage Line Pack
Exhibit No. PNG-18
Page 65 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
II. Salvage
C. Line pack
| 1 | Wholly-owned facilities
|  | a. | Amount of recoverable line pack
|  |  | 1 | Abandonment pressure assumed to be 200 psig.
|  |  | 2 | Wholly-owned PNGTS transmission line pack (Dth) |  |  | 245000
|  |  | 3 | Unrecoverable line pack (Dth) | (Ref: Workpapers - Line pack calculation) |  | 38799
|  |  | 4 | Recoverable PNGTS transmission line pack (Dth) |  | Total: | 206201
|  | b. | Value of wholly-owned recoverable line pack
|  |  | 1 | Spot price, Gas Daily, Dracut, MA, February 28, 2010: |  |  | 5.22
|  |  | 2 | Value of wholly-owned recoverable line pack: |  |  | -1076369.22
| 2 | Jointly-owned facilities (33.24%)
|  | a. | Amount of recoverable line pack
|  |  | 1 | Abandonment pressure assumed to be 200 psig.
|  |  | 2 | Jointly-owned PNGTS transmission line pack (Dth) |  |  | 180000
|  |  | 3 | Unrecoverable line pack (Dth) | (Ref: Workpapers - Line pack calculation) |  | 39915
|  |  | 4 | Recoverable PNGTS transmission line pack (Dth) |  | Total: | 140085
|  | b. | Value of jointly-owned recoverable line pack
|  |  | 1 | Spot price, Gas Daily, Dracut, MA, February 28, 2010: |  |  | 5.22
|  |  | 2 | Value of partially-owned recoverable line pack: |  |  | -731243.7

## Pipeline Labor Rates
Exhibit No. PNG-18
Page 66 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Pipeline Contractor Labor Rates and Company Inspection Costs
A | Pipeline contractor labor rates
|  | (Note 1) | (Note 2) |  | (Note 3) |  | (Note 4)
|  | Sep 2009 |  | Feb 2010 |  | Feb 2010 | Labor | Feb 2010
|  | Labor Rate |  | Labor Rate |  | Labor Rate | Overhead | Labor Rate
|  | Including |  | Including |  | Adjusted | 25% of | Pipeline
|  | Fringe | Escalation | Fringe | Overtime | for | Feb 2010 | Demolition
|  | Benefits | Factor | Benefits | Factor | Overtime | Base Rate | Estimate
| Trade | ($/hr) |  | ($/hr) |  | ($/hr) | (%) | ($/hr)
1 | Operating engineers:
2 | Crane operator | 57.09 | 1.01 | 57.6609 | 1.17 | 67.4633 | 14.4152 | 81.8785
3 | Heavy equipment | 56.87 | 1.01 | 57.4387 | 1.17 | 67.2033 | 14.3597 | 81.563
4 | Small equipment | 47.03 | 1.01 | 47.5003 | 1.17 | 55.5754 | 11.8751 | 67.4504
5 | Pipefitter/welder | 65.4 | 1.01 | 66.054 | 1.17 | 77.2832 | 16.5135 | 93.7967
6 | Pipefitter/welder helper | 39.24 | 1.01 | 39.6324 | 1.17 | 46.3699 | 9.9081 | 56.278
7 | Electrician | 64 | 1.01 | 64.64 | 1.17 | 75.6288 | 16.16 | 91.7888
8 | Electrician helper | 38.4 | 1.01 | 38.784 | 1.17 | 45.3773 | 9.696 | 55.0733
9 | Teamster | 41.14 | 1.01 | 41.5514 | 1.17 | 48.6151 | 10.3879 | 59.003
10 | Laborer | 45.8 | 1.01 | 46.258 | 1.17 | 54.1219 | 11.5645 | 65.6864
11 | Foreman | 66.4 | 1.01 | 67.064 | 1.17 | 78.4649 | 16.766 | 95.2309
| Labor overhead factor: | 25%
| Per diem: | 90 | IRS Publication 1542, "Per Diem Rates"
B. | Pipeline company inspection costs
Estimated
Cost/day
1 | Pipeline and M&R stations | [6 empty] | 500
Note: Inspection costs include direct labor, per diem, and transportation costs.
Notes
1 | Hourly union pay scales, September 2009, Boston, Massachusetts (ENR September 28, 2009).
2 | Escalation factor based on ENR construction cost indices September 2009 of 8586 and February 2010
of 8672 per ENR 3/29/10.
3 | Work 6-day week, 10-hr day. See workpapers for calculation of overtime factor.
4 | FICA, unemployment compensation, and workers compensation insurance that employers must pay.

## Pipeline Equipment Rates
Exhibit No. PNG-18
Page 67 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Pipeline Contractor Equipment Rates
|  | (Note 1) | (Note 2)
|  | Nov 2009 |  | Feb 2010
|  | Equipment | Escalation | Equipment
|  | Rate | Factor | Rate
| Equipment Description | ($/hr) |  | ($/hr)
1 | air compressor 160G, 160 cfm | 17.01 | 1.009 | 17.1631
2 | air hose, 1-inch, 100 ft | 1.28 | 1.009 | 1.2915
3 | paving breaker, 80-90 Lb | 0.86 | 1.009 | 0.86774
4 | crane, 30 ton, Grove, RT530E, hydrocrane 152 hp | 71.19 | 1.009 | 71.8307
5 | crane, 50 ton, Grove, RT750E, hydrocrane 240 hp | 120.02 | 1.009 | 121.1002
6 | fork lift | 22.15 | 1.009 | 22.3494
7 | motor grader, Cat 135-H, 135 hp | 46.49 | 1.009 | 46.9084
8 | hydraulic excavator, Bobcat, 0.10 cy | 13.66 | 1.009 | 13.7829
9 | hydraulic excavator, Cat 312D, 0.68 cy | 36.29 | 1.009 | 36.6166
10 | hydraulic excavator, Cat 320D, 1.50 cy | 48.23 | 1.009 | 48.6641
11 | hydraulic excavator, Cat 320DL, 0.80 cy | 63.14 | 1.009 | 63.7083
12 | hydraulic hammer, Kent, 4000 ft-lb | 18.23 | 1.009 | 18.3941
13 | hydraulic grapple, Labounty, 120 TR | 7.36 | 1.009 | 7.4262
14 | hydraulic shears, 27", Labounty, MSD 40-III SV | 37.29 | 1.009 | 37.6256
15 | lights, 6/1000W, 8 KW gen, trailer mtd. | 8.22 | 1.009 | 8.294
16 | pipelayer, Cat 561M, 18 ft boom, 40,000 lbs capacity | 42.23 | 1.009 | 42.6101
17 | pipelayer, Cat 572R, 20 ft boom, 90,000 lbs capacity | 79.8 | 1.009 | 80.5182
18 | pump, grout, trailer mounted, 1134 cf/hr | 18.53 | 1.009 | 18.6968
19 | pump, grout, trailer mounted, 2295 cf/hr | 34.35 | 1.009 | 34.6591
20 | pump, water, skid-mounted, 6" dia, 1165 gpm | 15.86 | 1.009 | 16.0027
21 | pump, hose, 6" dia, 100' length | 3.52 | 1.009 | 3.5517
22 | tractor, Cat D-6R, 165 hp | 95.64 | 1.009 | 96.5008
23 | winch for D-6R dozer | 8.39 | 1.009 | 8.4655
24 | track loader, Cat 953D, 2.25 cy | 65.38 | 1.009 | 65.9684
25 | dump truck, 8 cy | 25.6 | 1.009 | 25.8304
26 | dump truck, 14 cy | 44.88 | 1.009 | 45.2839
27 | flatbed truck | 25.89 | 1.009 | 26.123
28 | pipe truck | 61.4 | 1.009 | 61.9526
29 | lowboy, 50 ton | 64.82 | 1.009 | 65.4034
30 | 1/2 ton pickup, crew, G 4wd | 11.43 | 1.009 | 11.5329
31 | 3/4 ton pickup, crew, G 4wd | 14.16 | 1.009 | 14.2874
32 | welder, trailer mounted, 45 hp | 13.45 | 1.009 | 13.571
Notes
1 | Hourly Equipment Rates from November 2009, US Army Corps of Engineers
Construction Equipment Ownership and Operating Expense Schedule, Region I.
2 | Escalation factor based on ENR construction cost indices November 2009 of 8592 and February 2010 of
8672 per ENR 3/29/10.

## Workpapers-General
Exhibit No. PNG-18
Page 68 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General
A. | Quantities
| 1 | Total pipeline miles per PNGTS schematic
|  | a. | Wholly-owned facilities PNGTS ownership: |  | 100% |  |  | Miles
|  |  | 1 | 24" mainline |  |  |  | 143.83
|  |  | 2 | 8" Groveton lateral |  |  |  | 0.66
|  |  | 3 | 12" Rumford lateral |  |  |  | 26.51
|  |  | 4 | 12" Jay lateral |  |  |  | 16.78
[7 empty] | Total: | 187.78
|  | b. | Jointly-owned facilities PNGTS ownership: |  | 33.24%
|  |  | 1 | 30" mainline |  |  |  | 100.56
|  |  | 2 | 12" Westbrook lateral |  |  |  | 3.84
|  |  | 3 | 16" Newington lateral |  |  |  | 1.2
|  |  | 4 | 20" Haverhill lateral |  |  |  | 0.8
[7 empty] | Total: | 106.4
| 2 | No. of uncased railroad/highway crossings
|  | a. | Wholly-owned facilities (24" and laterals)
|  |  | 1 | Uncased highway crossings |  |  |  | No.
|  |  |  | a. 24" mainline |  |  |  | 130
|  |  |  | b. 12" Rumford/Jay lateral |  |  |  | 44
[7 empty] | Total: | 174
|  |  | 2 | Uncased RR crossings
|  |  |  | a. 24" mainline |  |  |  | 1
|  |  |  | b. 12" Rumford/Jay lateral |  |  |  | 0
[7 empty] | Total: | 1
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Uncased highway crossings |  |  |  | No.
|  |  |  | a. 30" mainline |  |  |  | 119
|  |  |  | b. 12" Westbrook lateral |  |  |  | 2
|  |  |  | c. 16" Newington lateral |  |  |  | 4
[7 empty] | Total: | 125
|  |  | 2 | Uncased RR crossings
|  |  |  | a. 30" mainline |  |  |  | 2
|  |  |  | b. 12" Westbrook lateral |  |  |  | 2
[7 empty] | Total: | 4
| 3 | No. of cased railroad/highway crossings
|  | a. | Wholly-owned facilities (24" and laterals)
|  |  | 1 | Cased highway crossings |  |  |  | No.
|  |  |  | a. 24" mainline |  |  |  | 22
|  |  |  | b. 8" Groveton lateral |  |  |  | 1
|  |  |  | c. 12" Rumford/Jay lateral |  |  |  | 2
[7 empty] | Total: | 25
|  |  | 2 | Cased RR crossings
|  |  |  | a. 24" mainline |  |  |  | 6
|  |  |  | b. 8" Groveton lateral |  |  |  | 2
|  |  |  | c. 12" Rumford/Jay lateral |  |  |  | 1
[7 empty] | Total: | 9
Exhibit No. PNG-18
Page 69 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General - (continued)
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Cased highway crossings |  |  |  | No.
|  |  |  | a. 30" mainline |  |  |  | 25
|  |  |  | b. 12" Westbrook lateral |  |  |  | 2
[7 empty] | Total: | 27
|  |  | 2 | Cased RR crossings
|  |  |  | a. 30" mainline |  |  |  | 7
[7 empty] | Total: | 7
| 4 | No. of small stream crossings
|  | a. | Wholly-owned facilities (24" and laterals) |  |  |  |  | No.
|  |  | 1 | Situations where grouting required |  |  |  | 188
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Situations where grouting required |  |  |  | 106
| 5 | No. of HDD crossings
|  | a. | Wholly-owned facilities (24" and laterals) |  | Dia. |  |  | Length
|  |  | 1 | Connecticut River | 24" |  |  | 984
|  |  | 2 | Mohawk River | 24" |  |  | 908
|  |  | 3 | Huckins Ponds | 24" |  |  | 1352
|  |  | 4 | Upper Ammonoosuc | 24" |  |  | 887
|  |  | 5 | Upper Ammonoosuc | 24" |  |  | 981
|  |  | 6 | Androscoggin | 24" |  |  | 845
|  |  | 7 | Androscoggin | 24" |  |  | 1095
|  |  | 8 | Androscoggin | 24" |  |  | 862
|  |  | 9 | Androscoggin | 24" |  |  | 952
|  |  | 10 | Crooked | 24" |  |  | 1196
|  |  | 11 | Androscoggin | 24" |  |  | 1656
|  |  | 12 | Androscoggin | 24" |  |  | 1391
[6 empty] | Average crossing length: |  | 1092.4167
[7 empty] | Say: | 1100
|  | b. | Jointly-owned facilities (30" and laterals) |  | Dia. |  |  | Length
|  |  | 1 | Squamscott River | 30" |  |  | 1374
|  |  | 2 | Piscataqua River | 30" |  |  | 2838
|  |  | 3 | Great Works River | 30" |  |  | 1050
|  |  | 4 | Great Works River | 30" |  |  | 1529
|  |  | 5 | Saco River | 30" |  |  | 1872
|  |  | 6 | Presumscott River | 30" |  |  | 1753
|  |  | 7 | Presumscott River (Westbrook Lateral) | 12" |  |  | 700
[6 empty] | Average crossing length: |  | 1588
[7 empty] | Say: | 1600
Exhibit No. PNG-18
Page 70 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
| 6 | No. of river and large stream trench crossings
|  | a. | Wholly-owned facilities (24" and laterals) |  | Dia. |  |  | Length (ft)\
|  |  | 1 | Sims Stream | 24" |  |  | 39
|  |  | 2 | Philips Brook | 24" |  |  | 89
|  |  | 3 | Peabody River | 24" |  |  | 169
|  |  | 4 | Androscoggin River (lobe) | 24" |  |  | 130
|  |  | 5 | Pleasant River | 24" |  |  | 47
|  |  | 6 | Pleasant River | 24" |  |  | 28
|  |  | 7 | Crooked River | 24" |  |  | 29
|  |  | 8 | Crooked River | 24" |  |  | 48
|  |  | 9 | Crooked River | 24" |  |  | 120
|  |  | 10 | Crooked River | 24" |  |  | 45
|  |  | 11 | Crooked River | 24" |  |  | 58
|  |  | 12 | Crooked River | 24" |  |  | 93
|  |  | 13 | Jordan River | 24" |  |  | 85
|  |  | 14 | Pleasant River | 24" |  |  | 55
|  |  | 15 | Concord River (Rum/Jay Lateral) | 12" |  |  | 59
|  |  | 16 | Spear Stream (Rum/Jay Lateral) | 12" |  |  | 46
[6 empty] | Average crossing length: |  | 71.25
[7 empty] | Say: | 100
|  | b. | Jointly-owned facilities (30" and laterals) |  | Dia. |  |  | Length (ft)\
|  |  | 1 | Pow Wow River | 30" |  |  | 413
|  |  | 2 | Exeter River | 30" |  |  | 95
|  |  | 3 | Little River | 30" |  |  | 66
|  |  | 4 | Winnicut River | 30" |  |  | 20
|  |  | 5 | Merriland River | 30" |  |  | 50
|  |  | 6 | Branch Brook | 30" |  |  | 24
|  |  | 7 | Mausam River | 30" |  |  | 332
|  |  | 8 | Kennebunk River | 30" |  |  | 56
|  |  | 9 | Nonesuch River | 30" |  |  | 165
[6 empty] | Average crossing length: |  | 135.6667
[7 empty] | Say: | 150
| 7 | Pipe to be removed - Option I
|  | a. | Wholly-owned facilities (24" and laterals) |  |  | Pipeline Dia. | Length | Length
|  |  | 1 | Location of pipe segments removed |  | (in) | (ft) | (miles)
|  |  |  | a. St. Lawrence and Atlantic RR (14 properties) |  | 24 | 7257 | 1.37
|  |  |  | b. White Mountain National Forest (4 parcels) |  | 24 | 7004 | 1.33
[6 empty] | Total: | 14261 | 2.7
|  |  |  | Option I (a) | Diameter | P/L Length | Allocation | Length
|  |  |  | Allocation of pipe segments removed | (in) | (miles) | Factor | (miles)
|  |  | 1 | 24" mainline | 24 | 143.83 | 76.59% | 2.07
|  |  | 2 | 8" Groveton lateral | 8 | 0.66 | 0.3515% | 0.01
|  |  | 3 | 12" Rumford/Jay lateral | 12 | 43.29 | 23.05% | 0.62
[5 empty] | Total: | 187.78 | 100% | 2.7
Exhibit No. PNG-18
Page 71 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
| 8 | Pipe to be removed - Option III
|  | a. | Wholly-owned facilities (24" and laterals) |  |  | Pipeline Dia. | Length | Length
|  |  | 1 | Segments removed - Option III (a): |  | (in) | (ft) | (miles)
|  |  |  | a. St. Lawrence and Atlantic RR (14 properties) |  | 24 | 7257 | 1.37
|  |  |  | b. White Mountain National Forest (4 parcels) |  | 24 | 7004 | 1.33
[6 empty] | Total: | 14261 | 2.7
|  |  |  | Option III (a) | Diameter | P/L Length | Allocation | Length
|  |  |  | Allocation of pipe segments removed | (in) | (miles) | Factor | (miles)
|  |  |  | 24" mainline | 24 | 143.83 | 76.59% | 2.07
|  |  |  | 8" Groveton lateral | 8 | 0.66 | 0.3515% | 0.01
|  |  |  | 12" Rumford/Jay lateral | 12 | 43.29 | 23.05% | 0.62
[5 empty] | Total: | 187.78 | 100% | 2.7
|  |  | 2 | Class 3 pipe removed - Option III (a) | 15 | miles
[5 empty] | Diameter | P/L Length | Allocation | Length
|  |  |  | Allocation of Class III pipe removed | (in) | (miles) | Factor | (miles)
|  |  |  | a. 24" mainline | 24 | 143.83 | 76.59% | 11.49
|  |  |  | b. 8" Groveton lateral | 8 | 0.66 | 0.3515% | 0.05
|  |  |  | c. 12" Rumford/Jay lateral | 12 | 43.29 | 23.05% | 3.46
[5 empty] | Total: | 187.78 | 100% | 15
|  |  | 3 | Total pipe removed - Option III (a) |  |  | Pipeline Dia. | Length
[7 empty] | (in) | (miles)
|  |  |  | a. 24" mainline |  |  | 24 | 13.56
|  |  |  | b. 8" Groveton lateral |  |  | 8 | 0.06
|  |  |  | c. 12" Rumford/Jay lateral |  |  | 12 | 4.08
[7 empty] | Total: | 17.7
|  | b. | Jointly-owned facilities (30" and laterals) |  |  |  | Pipeline Dia. | Length
|  |  | 1 | Total pipe removed - Option III (b) |  |  | (in) | (miles)
|  |  |  | a. 30" mainline |  |  | 30 | 12.1
|  |  |  | b. 12" Westbrook lateral |  |  | 12 | 1.4
[7 empty] | Total: | 13.5
| 9 | Pipe removal crossing adjustment factors (all Options) |  |  |  | Estimated | Average length | Length
|  | a. | Wholly-owned facilities (24" and laterals) |  |  | No. | (ft) | (ft)
|  |  | 1 | Uncased hwy crossings (all diameters) |  | 174 | 140 | 24360
|  |  | 2 | Uncased RR crossings (all diameters) |  | 1 | 140 | 140
|  |  | 3 | Cased hwy crossings (all diameters) |  | 25 | 240 | 6000
|  |  | 4 | Cased RR crossings (all diameters) |  | 9 | 240 | 2160
|  |  | 5 | Small stream crossings |  | 188 | 140 | 26320
|  |  | 6 | River and large stream crossings
|  |  | 7 | a. HDD crossings |  | 12 | 1100 | 13200
|  |  | 8 | b. Trenched crossings |  | 16 | 100 | 1600
|  |  | 9 |  | Total: | 425 |  | 73780
Exhibit No. PNG-18
Page 72 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
| 9 | a. | Wholly-owned facilities (24" and laterals) - (continued)
|  |  | 10 | Total crossing length (ft) |  |  |  | 73780
|  |  | 11 | Crossing length (miles) |  |  |  | 13.97
|  |  | 12 | Total pipe length (miles) |  |  |  | 187.78
|  |  | 13 | Adjusted pipe removal length (miles) |  |  |  | 173.81
|  |  | 14 | Wholly-owned facilities crossing reduction factor |  |  |  | 0.9256
| 9 | Pipe removal crossing adjustment factors (all Options)
|  | b. | Jointly-owned facilities (30" and laterals) |  |  | Estimated | Average length | Length
[6 empty] | No. | (ft) | (ft)
|  |  | 1 | Uncased hwy crossings (all diameters) |  | 125 | 140 | 17500
|  |  | 2 | Uncased RR crossings (all diameters) |  | 4 | 140 | 560
|  |  | 3 | Cased hwy crossings (all diameters) |  | 27 | 240 | 6480
|  |  | 4 | Cased RR crossings (all diameters) |  | 7 | 240 | 1680
|  |  | 5 | Small stream crossings |  | 106 | 140 | 14840
|  |  | 6 | River and large stream crossings
|  |  | 7 | a. HDD crossings |  | 7 | 1600 | 11200
|  |  | 8 | b. Trenched crossings |  | 9 | 150 | 1350
|  |  | 9 |  | Total: | 285 |  | 53610
|  |  | 10 | Total crossing length (ft): |  |  |  | 53610
|  |  | 11 | Crossing length (miles) |  |  |  | 10.15
|  |  | 12 | Total pipe length (miles) |  |  |  | 106.4
|  |  | 13 | Adjusted pipe removal length (miles) |  |  |  | 96.25
|  |  | 14 | Jointly-owned facilities crossing reduction factor |  |  |  | 0.9046
| 10 | Fill pipelines with nitrogen (assuming all pipelines are abandoned in-place)
|  | a. | Wholly-owned facilities (24" and laterals)
|  |  | 1 | No. of crossings |  |  |  | 425
[7 empty] | No. of segments for nitrogen fill: | 425
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | No. of crossings |  |  |  | 285
[7 empty] | No. of segments for nitrogen fill: | 285
| 11 | Fill pipelines with nitrogen -- nitrogen fill reduction factor for Option I
|  | a. | Wholly-owned facilities (24" and laterals)
|  |  | 1 | Total pipeline mileage |  |  |  | 187.78
|  |  | 2 | Pipeline to be removed |  |  |  | 2.7
|  |  | 3 | Pipelines to be abandoned in-place |  |  |  | 185.08
|  |  | 4 | Nitrogen fill reduction factor Option I (a) |  |  |  | 0.9856
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Total pipeline mileage |  |  |  | 106.4
|  |  | 2 | Pipeline to be removed |  |  |  | 0
|  |  | 3 | Pipelines to be abandoned in-place |  |  |  | 106.4
|  |  | 4 | Nitrogen fill reduction factor Option I (b) |  |  |  | 1
Exhibit No. PNG-18
Page 73 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
| 12 | Fill pipelines with nitrogen -- nitrogen fill reduction factor for Option III
|  | a. | Wholly-owned facilities (24" and laterals)
|  |  | 1 | Total pipeline mileage |  |  |  | 187.78
|  |  | 2 | Pipeline to be removed |  |  |  | 17.7
|  |  | 3 | Pipelines to be abandoned in-place |  |  |  | 170.08
|  |  | 4 | Nitrogen fill reduction factor Option III (a) |  |  |  | 0.9057
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Total pipeline mileage |  |  |  | 106.4
|  |  | 2 | Pipeline to be removed |  |  |  | 13.5
|  |  | 3 | Pipelines to be abandoned in-place |  |  |  | 92.9
|  |  | 4 | Nitrogen fill reduction factor Option III (b) |  |  |  | 0.8731
| 13 | Remote valve sites (i.e. not located at M&R stations)
|  | a. | Wholly-owned facilities (24" and laterals) |  |  |  |  | No.
|  |  | 1 | M/L remote valve sites (MLV 1,2,3,4,5,6,8,9,10,11,12) |  |  |  | 11
|  |  | 2 | Lateral remote valve sites (Groveton, R/J-1, R/J-2, R/J-3) |  |  |  | 4
[6 empty] | Total remote valve sites: |  | 15
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | M/L remote valve sites (MLV 1 through MLV 1-100) |  |  |  | 13
|  |  | 2 | Lateral remote valve sites (Haverhill, Newington, Westbrook) |  |  |  | 3
[6 empty] | Total remote valve sites: |  | 16
| 14 | Cathodic protection facilities
|  | a. | Wholly-owned facilities (24" and laterals) |  |  |  |  | No.
|  |  | 1 | Test sites |  |  |  | 246
|  |  | 2 | Rectifiers
|  |  |  | a. 24" mainline |  |  |  | 5
|  |  |  | b. 12" Rumford/Jay lateral |  |  |  | 2
[7 empty] | Total: | 7
|  | b. | Jointly-owned facilities (30" and laterals) |  |  | Pipeline miles | Test sites/mile | Total
|  |  | 1 | Test sites |  | 106.4 | 1.5 | 160
|  |  | 2 | Rectifiers
|  |  |  | a. 30" mainline |  |  |  | 12
[7 empty] | Total: | 12
| 15 | No. of pipeline markers per PNGTS
|  | a. | Wholly-owned facilities (24" and laterals) |  |  | Pipeline miles | Markers/mile | Total
|  |  | 1 | Pipeline markers |  | 187.78 | 10 | 1878
|  | b. | Jointly-owned facilities (30" and laterals) |  |  | Pipeline miles | Markers/mile | Total
|  |  | 1 | Pipeline markers |  | 106.4 | 10 | 1064
Exhibit No. PNG-18
Page 74 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
| 16 | No. of M&R stations
|  | a. | Wholly-owned facilities (24" and laterals) |  |  |  |  | No.
|  |  | 1 | Small (Groveton (2), Berlin, Rumford (2), Windham) |  |  |  | 6
|  |  | 2 | Medium (Jay) |  |  |  | 1
|  | b. | Jointly-owned facilities (30" and laterals)
|  |  | 1 | Small (Westbrook, Gorham, Eliott, Newington (4), Haverhill (2)) |  |  |  | 9
|  |  | 2 | Medium (Westbrook interchange, Mathuen, Dracut) |  |  |  | 3
| 17 | ROW damages related to pipe removal
|  |  | 1 | Use $4 per foot for 24" pipe |  |  |  | 4
|  |  | 2 | Cost per mile |  |  |  | 21120
B. | Overtime factor for six 10-hour days worked per week |  |  |  |  | Hours | Overtime
[6 empty] | Worked | Factor | Pay units
|  |  |  | Straight-time 8 hours/day M-F |  | 40 | 1 | 40
|  |  |  | Overtime 2 hours/day M-F |  | 10 | 1.5 | 15
|  |  |  | Overtime Saturday |  | 10 | 1.5 | 15
[5 empty] | Total: | 60 |  | 70
|  |  |  | Overtime factor: |  | 1.17
C. | Estimated no. of pipe trucks required during 24" pipe removal. A temporary pipe storage yard is estimated
to be located every 50 miles.
| 1 | Average miles of haul to temporary pipe storage yard (one-way) | [5 empty] | 12.5
| 2 | Pipe truck travel time and unloading time (hours)
|  | a. | Highway travel time round trip (hr) |  |  | 25 | mph | 1
|  | b. | Time to load truck at work site (hr) |  |  | 30 | min. | 0.5
[7 empty] | Total: | 1.5
| 3 | Time to unload pipe truck at storage yard (hr) |  |  |  | 15 | min. | 0.25
[7 empty] | Total: | 0.25
| 4 | No. of loads per day per pipe truck 10/((2)+(3)) | [5 empty] | 5.7143
| 5 | No. of pipe trucks required to keep one crane productive at storage yard (2)/(3) | [5 empty] | 6
| 6 | Total no. of pipe truck loads required per day
|  | a. | Length of pipe removed per day (ft) |  |  |  |  | 5280
|  | b. | Pipe hauled per truck @ 6 pipe sections per load (ft) |  |  | 6 | x 40 ft | 240
|  | c. | No. of loads required per day (a)/(b) |  |  |  |  | 22
| 7 | Total number of pipe trucks required at 5 loads per truck per day | [5 empty] | 4.4
Estimate that 5 pipe trucks are required.
Exhibit No. PNG-18
Page 75 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - General (continued)
D. | Estimated no. of dump trucks required during 24" pipe removal
| 1 | Average miles of haul to borrow site (one-way) | [5 empty] | 12.5
| 2 | Pipe truck travel time, loading, and unloading time (hr)
|  | a. | Highway travel time (hr) |  |  | 25 | mph | 1
|  | b. | Time to load truck (hr) |  |  | 10 | min. | 0.16667
|  | c. | Time to unload (hr) |  |  | 5 | min. | 0.08
[7 empty] | Total: | 1.2467
| 3 | No. of loads per day per dump truck (10-hr day) | [5 empty] | 8
| 4 | Total no. of loads required per day
|  | a. | Amount of borrow required per day (cy) |  |  |  |  | 675
|  | b. | Capacity of dump trucks (cy) |  |  |  |  | 14
|  |  | Total no. of loads required per day (a)/(b) |  |  |  |  | 48.2143
| 5 | Total number of trucks required at 8 loads per truck per day | [5 empty] | 6.0268
Estimate that 6 dump trucks (14 cy) required
E. | PNGTS pipe located in wetlands
[6 empty] | Pipeline Dia. | Length | Length
|  | a. | Wholly-owned facilities (24" and laterals) |  |  | (in) | (mile) | (ft)
|  |  | 1 | Wetlands - mainline |  | 24 | 44.37 | 234265
|  |  | 2 | Wetlands - laterals |  | 12 | 6.24 | 32931.2
[6 empty] | Total: | 50.61 | 267196.2
|  | b. | Jointly-owned facilities (30" and laterals) |  |  | Pipeline Dia. | Length | Length
[6 empty] | (in) | (mile) | (ft)
|  |  | 1 | Wetlands - mainline |  | 30 | 28.65 | 151272
|  |  | 2 | Wetlands - laterals
|  |  |  | a. Westbrook |  | 12 | 0.5 | 2640
|  |  |  | b. Newington |  | 16 | 0.17 | 897.6
|  |  |  | c. Haverhill |  | 20 | 0.14 | 739.2
[6 empty] | Total: | 29.46 | 155548.8
F. | Miscellaneous
| 1 | Sales tax rate | [5 empty] | 5%
| 2 | Grout cost per cy | [5 empty] | 98
| 3 | Backfill material per cy | [5 empty] | 10
| 4 | Book cost of line pack | [5 empty] | 826503
| 5 | Estimated scrap steel value at job site | [5 empty] | 210
| 6 | ENR construction cost index September 2001 |  |  | (per ENR 3/29/10) |  |  | 6391
| 7 | ENR construction cost index February 2010 |  |  | (per ENR 3/29/10) |  |  | 8672
| 8 | Escalation factor September 2001 - February 2010 | [5 empty] | 1.36

## Workpapers-Line Pack
Exhibit No. PNG-18
Page 76 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - Line pack calculation
I | Wholly-owned facilities
| A. | Calculate pipeline volume
[6 empty] | Length | Length | Dia | Vol/ft | Volume
[6 empty] | (mile) | (ft) | (ft) | (cf) | (cf)
| 1 | 24" pipeline (mainline) |  |  |  | 143.83 | 759422.4 | 2 | 3.1416 | 2385795.8328
| 2 | Laterals
|  | a. |  | 8" Groveton |  | 0.66 | 3484.8 | 0.66667 | 0.34907 | 1216.4247
|  | b. |  | 12" Rumford |  | 26.51 | 139972.8 | 1 | 0.7854 | 109934.38
|  | c. |  | 12" Jay |  | 16.78 | 88598.4 | 1 | 0.7854 | 69585.0206
[5 empty] | Total: | 187.78 | 991478.4 |  |  | 2566531.6582
| B. | Calculate volume of unrecoverable line pack at 200 psig abandonment pressure
| 1 | Calculate number of moles of line pack at 60 degrees F and 200 psig in pipelines
[6 empty] | P2 = | 214.7 | psia
[6 empty] | V2 = | 2566531.6582 | cf
[6 empty] | T2 = | 520 | Degrees Rankine = 60 degrees F
[6 empty] | R = | 10.73 | Universal Gas Constant
[6 empty] | n = | ? | No. of moles
[5 empty] | (See Part III below) | z(2) = | 0.97 | Compressibility Factor
[5 empty] | Equation of state: | PV = znRT
(P2)(V2)/(z2)(T2) = nR
[6 empty] | 1092455.0892 | = nR
[6 empty] | 101813.149 | = n
| 2 | Calculate equivalent volume of natural gas in pipelines at standard conditions
[6 empty] | P1 = | 14.7 | psia
[6 empty] | V1 = | ? | cf
[6 empty] | T1 = | 520 | Degrees Rankine = 60 Degrees F
[6 empty] | R = | 10.73 | Universal Gas Constant
[6 empty] | n = | 101813.149 | No. of moles
[6 empty] | z1 = | 1 | Compressibility factor
[6 empty] | V1 = | (z1)(n1)(R)(T1)/(P1)
[6 empty] | V1 = | 38644669.8232 | cf
|  |  | Volume of unrecoverable line pack (scf) = V1 = |  |  |  | 38644.6698 | Mcf
|  |  | Heat content per cu ft of line pack gas = |  |  |  | 1004 | Btu
|  |  | Heat content of unrecoverable line pack = |  |  |  | 38799 | Dth
Exhibit No. PNG-18
Page 77 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - Line pack calculation (continued)
II. | Jointly-owned facilities (33.24%)
| A. | Calculate pipeline volume
[6 empty] | Length | Length | Dia | Vol/ft | Volume
[6 empty] | (mile) | (ft) | (ft) | (cf) | (cf)
| 1 | 30" pipeline (mainline) |  |  |  | 100.56 | 530956.8 | 2.5 | 4.9087 | 2606328.0973
| 2 | Laterals
|  | a. |  | 12" Westbrook |  | 3.84 | 20275.2 | 1 | 0.7854 | 15924.1048
|  | b. |  | 16" Newington |  | 1.2 | 6336 | 1.3333 | 1.3963 | 8846.7249
|  | c. |  | 20" Haverhill |  | 0.8 | 4224 | 1.6667 | 2.1817 | 9215.3385
[5 empty] | Total: | 106.4 | 561792 |  |  | 2640314.2655
| B. | Calculate volume of unrecoverable line pack at 200 psig abandonment pressure
| 1 | Calculate number of moles of line pack at 60 degrees F and 200 psig in pipelines
[6 empty] | P2 = | 214.7 | psia
[6 empty] | V2 = | 2640314.2655 | cf
[6 empty] | T2 = | 520 | Degrees Rankine = 60 degrees F
[6 empty] | R = | 10.73 | Universal Gas Constant
[6 empty] | n = | ? | No. of moles
[5 empty] | (See Part III below) | z(2) = | 0.97 | Compressibility Factor
[5 empty] | Equation of state: | PV = znRT
(P2)(V2)/(z2)(T2) = nR
[6 empty] | 1123860.9691 | = nR
[6 empty] | 104740.0717 | = n
| 2 | Calculate equivalent volume of natural gas in pipelines at standard conditions
[6 empty] | P1 = | 14.7 | psia
[6 empty] | V1 = | ? | cf
[6 empty] | T1 = | 520 | Degrees Rankine = 60 Degrees F
[6 empty] | R = | 10.73 | Universal Gas Constant
[6 empty] | n = | 104740.0717 | No. of moles
[6 empty] | z1 = | 1 | Compressibility factor
[6 empty] | V1 = | (z1)(n1)(R)(T1)/(P1)
[6 empty] | V1 = | 39755626.1167 | cf
|  |  | Volume of unrecoverable line pack (scf) = V1 = |  |  |  | 39755.6261 | Mcf
|  |  | Heat content per cu ft of line pack gas = |  |  |  | 1004 | Btu
|  |  | Heat content of unrecoverable line pack = |  |  |  | 39915 | Dth
Exhibit No. PNG-18
Page 78 of 78
Portland Natural Gas Transmission System
Final Abandonment Estimate
Workpapers - Line pack calculation (continued)
III. | Calculation of compressibility factor (z)
[5 empty] | Equation of State: | PV = znRT
[5 empty] | 60 degrees F equivalent to 520 degrees Rankine |  |  | 520 | degrees Rankine
[5 empty] | Critical Temperature of Methane = |  |  | 343.3 | degrees Rankine
[5 empty] | Reduced Temperature = 520/343.3 = |  |  | 1.5147 | reduced temperature
[7 empty] | 200 psig = | 214.7 | psia
[5 empty] | Critical Pressure of Methane = |  |  | 673.1 | psia
[5 empty] | Reduced Pressure = 214.7/673.1 = |  |  | 0.31897 | reduced pressure
[8 empty] | 0.97 | z factor from chart